## Sheet1
FISHERY IMPROVEMENT PROGRAMME
Ongoing plans for monitoring, assessment and research with the objective to improve and manage the wider broads fishery.
Workstream | Description | Why required? | Indicative cost | Organistation leading | Named workstream manager | Potential funding streams | Time frame
Create Hoveton Monitoring Advisory group (HMAG) | Purpose: (a) To provide technical management of monitoring and evaluating processes. (b) Evaluating the outcome of assessments and making recommendations to Hoveton Project Steering Group as necessary. (c ) to commisson Resources 4 Change (R4C) to conduct up to date socio-economic analysis of the value to Norfolk Broads of fisheries and survey user views on fisheries assemblage | This would have national and local EA & NE membership as well as representation from Broads Authority. Actual membership to be agreed with Area Directors of EA / NE. This group would provide scientific, factual, unbiased management of the following monitoring & assessment plan whislt exploring opportunities to identify new opportunities for the research. It would be the group that monitors the impact of biomanipulation on the wider fishery and can factually report on a regular basis on this to relevant groups. R4C work to update figures quoted about tourism value of fisheries in partnership with EA and guide decision making based on user interation surveys and evaluation. This also serves to supply evidence for NHLF funding. | Staff time within NE & EA budgets as part of current contracts | NE | CT to establish group and then at first meeting elect a chair | Costs from current operating budgets wihtin NE / EA and committed to this for project life cycle. | Write TOR for group in December 2019. First meeting in January 2020.
Spawning habitat monitoring of the Upper Bure and Ant | Following the methodology developed and employed by Fishtrack for the project, we would carry out further spawning habitat surveys of the Upper Bure and the Ant. | The original survey by Fishtrack focused on HGB, HB and the surrounding Bure broads. By expanding this survey using the same method, we can greatly build our understanding of the available spawning habitat for bream. The surveys will also be used to identify areas where additional bank management could enhance the littoral margin. Additionally incorporating BFAP rhond areas that the BA can manage for fish habitat. We can then work with partners to target on-going management and maintenance works to specifically benefit fish. | £5K | NE | SH to write Project Brief for works and liaise with EA / BA on its implementation | HGB Budget to fund works to 2021, post project in afterLIFE funding | To be agreed by HMAG
Spring spawning side scanner SONAR surveys COMPLETED BUT INCLUDED IN THIS TO EVIDENCE PRIOR ACTIONS | Spawning side scanner SONAR surveys during day / night to cover HGB, Hudsons Bay, Wroxham, Salhouse, Decoy, HLB and Pound End, Ranworth. These surveys have been conducted already to show pre insallation activity, | This will provide some information of fish community spawning behaviour in the wider system and the role of HGB in that system. It will also help develop understanding on how closing off HGB and HB has affected spawning behaviour and areas used. Importantly, | staff time | EA | RS
Design & Implement Post Barrier Installtion Project to identify fish spawning behviour in the Bure system | The scope of this project is to be agreed but it will work to follow up on the principles identified from the side scanner surveys already conducted and provide systematic assessments of spawning patterns across the Bure system. | This would be a community science project. The methodology would be agreed with EA / NE through the HMAG with final sign off with the Porject Steering Group. It will also help develop a better understand of habitat preference that can be used in future fisheries management interventions. . | unknown at this stage | NE & EA | RS & SH | Costs from current operating budgets wihtin Project and committed to this for project life cycle. EA will need to allocate resources | exact dates of surveys to be agreed but proposed surveys over 3 years to see initial impact, and ongoing behaviours in years 2 and 3 intially. HMAG to recommend to Steering Group additional surveys as required.
Ongoing water and macrophyte sampling | Zooplankton, phytoplankton, water quality and macrophyte sampling for the duration of the project (when barriers are in situ). | This will need to be reported as part of the AfterLIFE work and will inform us on the impacts on water quality after fish are removed. | no additional cost | NE & EA | SH | Costs from current operating budgets wihtin NE / EA and committed to this for project life cycle. | monthly water sampling
ARIS camera monitoring of barriers | ARIS camera work at the barriers for two days once they are in place. | This will provide evidence of efficacy of the barriers, and evidence of potential for further passive biomanipulation. This will also provide information on fish behaviour post isolation. Analysis of this information will be managed by HMAG. This is a Broads Authority requirement. It will provide additional infomration about acctivity in the river system. | Staff time | NE & EA | SH | Costs from current operating budgets wihtin project and committed to this for project life cycle. EA will need to allocate resources | May each year
Maintain PhD Studies and research - Support additional PhD studies | Commit to a continuation of the current PhD work being undertaken in partnership with Bournemouth University. Commit to additional PhD's if opportunities exist. | This will allow us to continue to track the movement of bream & pike (tagged fish) in the important period post biomanipulation and answer some of the questions remaining about learned migration patterns. It will help identify spawning habitat and changes in migration spawning activities wihch will help spawning habitat management | Currently project pays for PhD. £50K | NE | Hoveton Project Steering Group | Costs to be met through afterLIFe funding. CT working on bid / funding applications | 2021 - 2024
Additional fish tracking receivers to support monitoring in place ALREADY DONE AND IN PLACE TO BE USED | Additional acoustic receivers within the Bure broads system | These allow us to better understand at a spatial scale how fish move around the system. Analysis of the additional data analysis could be picked up within the PhD. |  | EA
Edge Habitat manadement | To improve fish habitat availability in consideration with other conservation objectives. | Enhance the littoral margin for spawning fish. It should be noted that any works would need to be balanced against other water user objectives including SSSI requirments. |  | NE & NNR | NNR Team | Costs from current operating budgets wihtin NE / EA and committed to this for project life cycle. AfterLIFE funding to meet addiitonal costs | To be advised by HMAG
Dredging Hoveton Marshes | The project boat trail will be dredging ~1.5km of silted up dyke system. | Dredging will restore silted up dyke system recreating spawning and nursery habitat that had been lost. It is the NNR's and Hoveton Estates ambition to improve and create any open water habitat - for example: little fry bays will link to main river networks. EA Fisheries to contribute to discussions on this process. | Covered in Project spend | NE | SH & DA | within boat trail budget | Autumn 2020
Fen pond creation | Fen vegetation will be used to top the sediment geo-tubes following sediment removal works. Turf due to be cut from from fen adjacent to Decoy Broad | By creating and connecting two ponds (1000m2) ponds to Decoy Broad and the fen dyke we will create additional nursery areas for fish. It is predicted these will remain open for 12 years under normal succession rates of fen. Creation of deeper water will also improve spawning habitat - ponds will be 30 - 50 cm deep | covered in project spend | NE | DA | within sediment removal budget