## Introduction
ENVIRONMENT AGENCY (March 2017)
© Environment Agency copyright and/or database right 2015. All rights reserved |  | This document may be downloaded from gov.uk :- | Programme of flood and coastal risk management projects
Flood and Coastal Erosion Risk Management Programmes of Work for the financial year 2017 to 2018 Consented by Regional Flood & Coastal Committees
There are 12 Regional Flood & Coastal Committees (RFCCs) in England. The Environment Agency must consult with RFCCs about flood and coastal erosion risk management work in their region and take their comments into consideration. RFCCs are required to consent the programme covering their region. RFCCs are composed of a chairperson appointed by the Secretary of State and members appointed by lead local flood authorities, and by the Environment Agency.
You can download a map showing RFCC boundaries from gov.uk :- | Regional Flood and Coastal Committees map
What information is provided on the Programme?
The 2017-18 to 2020-21 Programme tab provides information on the latest flood and coastal erosion risk management (FCERM) programme. The Completed Projects tab shows projects which have better protected homes from flooding or coastal erosion (some of these projects arent entirely complete but delivring in phases). The programme is split into three stages reflecting increasing levels of certainty around the development and delivery of individual schemes. The visibility that this provides will enable the construction industry to better support the Environment Agency and its partners in identifying where additional efficiencies or delivery improvements could be introduced.
The programme of works indentified in the 2017-18 to 2020-21 Programme tab indentifies project in three stages: 1) construction programme, 2) development programme or 3) pipeline programme.
Construction programme: - Projects already in construction
Development programme: - Projects in development, expected to start construction in future years, subject to approval of a full business case.
Pipeline programme: The pipeline programme lists project proposals that are likely to qualify for some government funding before 2021 and have been given an indicative allocation. However they have not yet identified sufficient contributions and/or do not have a sufficiently well-developed case to enter the development programme at this stage.
In addition to the programme of works, the completed projects tab shows completed projects to date since the start of the 2015/16 - 2020/21 programme. This tab shows projects which have better protected homes from flooding or coastal erosion since the beginning of the programme - April 1st 2015. Although most are complete, some projects will also appear in the Capital Programme as these projects may protect homes in stages and are funded to protect more homes later in the programme.
Commitments to specific allocations of central government funding (FCERM Grant in Aid - GiA) to projects will be reviewed at least annually. This is based on prioritised submissions from all Risk Management Authorities which are approved by the Environment Agency in January. The amounts payable beyond the 2017 to 2018 financial year will be confirmed and allocated on a project by project basis. Local authority and internal drainage board project payments will be in line with the Department for Communities and Local Government rules for the allocation of funding. For schemes entering the construction programme an indicative funding allocation is made through to completion. The indicative funding is subject to change and may be re-profiled to ensure the overall programme remains affordable and efficient. This will ensure that any unused contingency and efficiencies can be effectively applied to support accelerated delivery of the programme. These programmes are subject to change during the year and projects may be subject to delay (for example through extreme weather events) or brought forward (for example in response to additional funding). New projects not on these lists may also start during the year where for example emergency works are required.
Projects are only introduced into the development programme if they have a case for government support in the construction phase. Confirmation of the timing and amount of grant in aid for the construction phase of a scheme is subject to assurance and approvals. As a general rule the maximum funding available for the development phase of a project is 20% of the eligible total grant in aid for that scheme.
Projects in the pipeline programme may move into the development, and potentially construction, programme at any time subject to meeting the normal criteria. The pipeline projects will be regularly reviewed to take full advantage of any opportunities to accelerate their delivery.
The projects listed aim to reduce the risk of flooding from rivers, sea, groundwater or surface water and/or to reduce the risks from coastal erosion. They do not include work to reduce the risks of flooding from sewers which is funded exclusively by water companies.
The projects listed are those that contain an indicative allocation of FCERM grant in aid funding within the 2017 to 2021 period. For further information around any potential projects that will be funded purely from third party funding (or projects that are planned for after 2021), please contact your local Area Flood and Coastal Risk Manager.
All cost information is provided in £k.
The project information in these programmes has been provided by the Environment Agency, local authorities, internal drainage boards, water companies and highways authorities, who all have responsibilities for flood and coastal erosion risk management in England. These programmes are made up of the programmes consented by the RFCCs at their January 2017 meetings. All information is correct as at January 2017. The published cost figures are based on the current most likely costs at 2017/18 prices. The final figures for costs, GiA contributions and other funding contributions will be updated as the projects progress.
How can I find out about a project near me?
The 2017-18 to 2020-21 Programme tab is ordered alphabetically and sorted by Regional Committee, Local Authority and then by Project stage.
You can contact your local Environment Agency office for more information on any of these projects by calling 03708 506 506 or by email to: |  |  | enquiries@environment-agency.gov.uk
You can also use the interactive map on gov.uk to search for projects by location or postcode :- |  | interactive map
Understanding the information provided
These tables are used for a wide range of purposes. A brief explanation has been provided below including links to where you can find out more information on how funding is allocated and how the outcomes of the projects are assessed.
Lead Risk Management Authority - This column specifies which risk management authority is leading the project. They are either a local authority (LA), internal drainage board (IDB) or the Environment Agency (EA). Water companies (WC) and Highways Authorities (HA) are also risk management authorities and may lead projects in the programme.
Outcomes and funding The numbers of households with a better level of protection are initially estimated using local engineering knowledge and experience from previous flooding. As projects progress in their development the estimate is refined using modelled data. The table shows, for each project, the number of households that are expected to have a better level of protection within the next 6 years, and from the project overall once it is complete.
Where 'contributions' is listed against projects these contributions will need to be forthcoming to enable the projects to continue to progress.
More information on how outcomes of projects are assessed and how grant in aid funding for projects is calculated can be found on gov.uk :- |  |  | Partnership Funding and Outcome measures
Reference: LIT_10059

## 2017-18 to 2020-21 Programme
Flood and Coastal Erosion Risk Management (FCERM) Programme - England
January RFCC consented programme (updated February 2017)
Project Name | Office of National Statistics Region | Regional Flood and Coastal Committee | Environment Agency Area | Parlimentary Constituency | Location | Local Authority | Lead Risk Management Authority Name | Project Stage | Total Project Cost (£k) | Total Grant In-Aid (£k) | Total Contributions (£k) | Grant In-Aid 2017/18 (£k) | Grant In-Aid (Indicative) 2018/19 - 2020/21 (£k) | Forecast Construction Start Date | Forecast Completion Date | Total homes better protected from Flooding by 2020/21 (since 2015/16) | Total homes better protected from Coastal Erosion by 2020/21 (since 2015/16) | Total homes better protected from Flooding on scheme completion | Total homes better protected from Coastal Erosion on scheme completion
Fitzwillam Playing Field Surface Water Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | Cambridge | Arbury and Castle Ward, Cambridge | Cambridge | Cambridgeshire County Council | Construction | 342 | 158 | 184 | 72.5 | 0 | By April 2017 | By April 2019 | 95 | 0 | 95 | 0
Brunswick Surface Water Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | Cambridge | Cambridge | Cambridge | Cambridge City Council | Development | 60 | 20 | 40 | 20 | 0 | 2017-2019 | By April 2019 | 4 | 0 | 4 | 0
Kelvin Close Surface Water Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | Cambridge | Cambridge | Cambridge | Cambridge City Council | Development | 95 | 60 | 35 | 40 | 20 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Eaton Bray Flood Risk Management Scheme | East of England | Anglian Central | East Anglia | South West Bedfordshire | Eaton Bray & Eddlesborough, River Ouzel | Central Bedfordshire | Buckingham and River Ouzel IDB | Development | 666 | 415 | 251 | 70 | 336.25 | 2019-2021 | By April 2021 | 150 | 0 | 150 | 0
Ouse Washes Reservoir Study and Works | East of England | Anglian Central | East Anglia | North East Cambridgeshire | River Great Ouse | East Cambridgeshire | Environment Agency | Pipeline | 9956.156 | 9956.156 | 0 | 4500 | 4520 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
March Surface Water Flood Alleviation Scheme - Phase 1 | East of England | Anglian Central | East Anglia | North East Cambridgeshire | Morton Avenue, March | Fenland | Cambridgeshire County Council | Construction | 95 | 28.647 | 66.353 | 10 | 0 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Middle Level Commissioners Bank Raising Scheme | East of England | Anglian Central | East Anglia | North East Cambridgeshire | Thoughout the MLC District | Fenland | Middle Level Commissioners | Development | 5895 | 3240 | 2655 | 500 | 1500 | 2017-2019 | Beyond 2021 | 0 | 0 | 2000 | 0
Newmarket Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | West Suffolk | Newmarket | Forest Heath | Suffolk County Council | Construction | 420 | 285 | 135 | 150 | 100 | By April 2017 | By April 2019 | 215 | 0 | 215 | 0
Barton Mills Sluice Improvements | East of England | Anglian Central | East Anglia | West Suffolk | River Lark, Barton Mills, Cambridgeshire | Forest Heath | Environment Agency | Pipeline | 500 | 500 | 0 | 30 | 470 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
St Neots Brook Street Flood Risk Management Scheme | East of England | Anglian Central | East Anglia | Huntingdon | St Neots - Brook Street | Huntingdonshire | Environment Agency | Development | 340 | 340 | 0 | 0 | 300 | Beyond 2021 | Beyond 2021 | 0 | 0 | 265 | 0
Godmanchester Surface Water Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | Huntingdon | Godmanchester | Huntingdonshire | Cambridgeshire County Council | Development | 110 | 80 | 30 | 0 | 80 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Great Fen - Upstream Storage Scheme | East of England | Anglian Central | East Anglia | North West Cambridgeshire | Great Fen project area | Huntingdonshire | Middle Level Commissioners | Development | 3265 | 2265 | 1000 | 0 | 235 | Beyond 2021 | Beyond 2021 | 0 | 0 | 500 | 0
Fenstanton Flood Risk Management Scheme | East of England | Anglian Central | East Anglia | Huntingdon | Fenstanton | Huntingdonshire | Environment Agency | Pipeline | 714 | 160 | 554 | 0 | 20 | 2019-2021 | By April 2021 | 0 | 0 | 90 | 0
Wash East Coastal Management Strategy - Works arising | East of England | Anglian Central | East Anglia | North West Norfolk | Wash East | King's Lynn and West Norfolk | Environment Agency | Construction | 5068.8 | 1605 | 3463.8 | 60 | 310 | By April 2017 | Beyond 2021 | 250 | 0 | 500 | 0
Crabbes Abbey Pumping Station - Inlet Refurbishment and Pump Replacement | East of England | Anglian Central | East Anglia | North West Norfolk | Stow Bridge | King's Lynn and West Norfolk | Kings Lynn IDB | Development | 130 | 128.7 | 1.3 | 9.9 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 70 | 0
Green Bank Pumping Station - Pump Refurbishment | East of England | Anglian Central | East Anglia | North West Norfolk | Broad Fen | King's Lynn and West Norfolk | Kings Lynn IDB | Development | 80 | 77 | 3 | 0 | 77 | 2017-2019 | By April 2019 | 280 | 0 | 280 | 0
Islington Catchment Flood Risk Management Scheme | East of England | Anglian Central | East Anglia | North West Norfolk | Tilney Cum Islington | King's Lynn and West Norfolk | Kings Lynn IDB | Development | 12297.35 | 3373.05 | 8924.3 | 1998.9 | 883.8 | 2017-2019 | By April 2021 | 760 | 0 | 760 | 0
North Lynn Pumping Station - Pump Refurbishment | East of England | Anglian Central | East Anglia | North West Norfolk | North Lynn | King's Lynn and West Norfolk | Kings Lynn IDB | Development | 70 | 50 | 20 | 0 | 50 | 2017-2019 | By April 2019 | 300 | 0 | 300 | 0
Stow Fen 1950's pumping station - Pumping station replacement | East of England | Anglian Central | East Anglia | South West Norfolk | Downham Market | King's Lynn and West Norfolk | Downham & Stow Bardolph Idb | Development | 1515 | 1200 | 315 | 1050 | 70 | 2017-2019 | By April 2019 | 170 | 0 | 170 | 0
Wolferton Catchment Flood Risk Management Scheme | East of England | Anglian Central | East Anglia | North West Norfolk | Wolferton | King's Lynn and West Norfolk | Kings Lynn IDB | Development | 4321.6 | 356 | 3965.6 | 356 | 0 | 2017-2019 | By April 2019 | 265 | 0 | 265 | 0
A1101 Wash Road Welney Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | South West Norfolk | Wash Road, The Hundred Foot Washes, Old Bedford River | King's Lynn and West Norfolk | Norfolk County Council | Pipeline | 1150 | 50 | 1100 | 50 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Caldecotte Flood Risk Management Scheme | South East | Anglian Central | East Anglia | Milton Keynes South | Walnut Tree & Browne Wood Milton Keynes, Caldecotte | Milton Keynes | Buckingham and River Ouzel IDB | Development | 734 | 94 | 640 | 94 | 0 | 2019-2021 | By April 2021 | 270 | 0 | 270 | 0
Histon/Impington Surface Water Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | South East Cambridgeshire | Histon and Impington Ward | South Cambridgeshire | Cambridgeshire County Council | Development | 503 | 113 | 390 | 0 | 113 | 2017-2019 | By April 2021 | 120 | 0 | 120 | 0
Brackley Flood Risk Management Scheme | East Midlands | Anglian Central | East Anglia | South Northamptonshire | Brackley | South Northamptonshire | Environment Agency | Pipeline | 594.794 | 132 | 462.794 | 10 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 10 | 0
Saffron Walden Culvert Improvements | East of England | Anglian Central | East Anglia | Saffron Walden | Saffron Walden, Slades | Uttlesford | Environment Agency | Pipeline | 2058 | 200 | 1858 | 0 | 50 | 2017-2019 | By April 2021 | 0 | 0 | 140 | 0
Boxford Flood Risk Management Project | East of England | Anglian Eastern | East Anglia | South Suffolk | Boxford, Suffolk - ordinary water course | Babergh | Suffolk County Council | Development | 100 | 100 | 0 | 14.452 | 85.548 | 2017-2019 | By April 2021 | 40 | 0 | 40 | 0
Sudbury Great Cornard Flood Risk Management Project | East of England | Anglian Eastern | East Anglia | South Suffolk | Sudbury & Great Cornard | Babergh | Suffolk County Council | Development | 1060.004 | 1040 | 20.004 | 64.703 | 831.307 | 2017-2019 | By April 2021 | 0 | 0 | 390 | 0
Halstead Mill Bypass Gate Replacement - Townsford Mill | East of England | Anglian Eastern | East Anglia | Braintree | Halstead, Essex | Braintree | Environment Agency | Development | 462.1 | 462.1 | 0 | 44.44 | 351.196 | 2017-2019 | By April 2021 | 190 | 0 | 190 | 0
Coggeshall and Kelvedon Community Flood Alleviation | East of England | Anglian Eastern | East Anglia | Braintree | Coggeshall , Feering and Kelvedon | Braintree | Environment Agency | Pipeline | 5104.776 | 689.54 | 4415.236 | 99.999 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 50 | 0
Heybridge (near Ingatestone) Community Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Brentwood and Ongar | Heybridge (near Ingatestone) , Ingatestone Brook. | Brentwood | Environment Agency | Development | 176.003 | 176.003 | 0 | 0 | 2.006 | Beyond 2021 | Beyond 2021 | 0 | 0 | 40 | 0
Cantley Pumping Station Replacement | East of England | Anglian Eastern | East Anglia | Broadland | Cantley CP | Broadland | Broads (2006) IDB | Development | 90.002 | 40.001 | 50.001 | 7.551 | 32.45 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Postwick Pumping Station Replacement | East of England | Anglian Eastern | East Anglia | Broadland | Postwick with Witton CP | Broadland | Broads (2006) IDB | Development | 80.002 | 35.102 | 44.9 | 0 | 5.387 | 2019-2021 | By April 2021 | 0 | 0 | 5 | 0
Upton Boat Dyke Culvert Replacement | East of England | Anglian Eastern | East Anglia | Broadland | Upton with Fishley CP | Broadland | Broads (2006) IDB | Development | 90.001 | 9.001 | 81 | 0 | 3.26 | Beyond 2021 | Beyond 2021 | 0 | 0 | 2 | 0
Acle Landspring and Pumping Station Works | East of England | Anglian Eastern | East Anglia | Broadland | Acle CP | Broadland | Broads (2006) IDB | Development | 39.998 | 19.998 | 20 | 3.155 | 14.759 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Canvey Island Drainage Network Appraisal and Works | East of England | Anglian Eastern | East Anglia | Castle Point | Canvey Island, Essex | Castle Point | Environment Agency | Development | 3489.985 | 2876.73 | 613.255 | 0 | 536.818 | Beyond 2021 | Beyond 2021 | 0 | 0 | 200 | 0
Castle Point Surface Water Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Castle Point | Castle Point | Castle Point | Essex County Council | Development | 751.001 | 366 | 385.001 | 45.018 | 294.573 | 2017-2019 | By April 2021 | 85 | 0 | 85 | 0
Chelmsford Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Chelmsford | Chelmsford, Essex | Chelmsford | Environment Agency | Development | 11382.278 | 2573.298 | 8808.98 | 0 | 2573.298 | 2019-2021 | By April 2021 | 370 | 0 | 495 | 0
Anglian Regional Habitat Creation Programme (ARHCP) | East of England | Anglian Eastern | East Anglia | TBC | Various | Colchester | Environment Agency | Pipeline | 11511.069 | 11511.069 | 0 | 105.813 | 155.833 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Gorleston Coast Protection Scheme | East of England | Anglian Eastern | East Anglia | Great Yarmouth | Coastline of Gorleston Great Yarmouth south of harbour | Great Yarmouth | Great Yarmouth Borough Council | Development | 11489 | 11489 | 0 | 0 | 143.39 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 500
Great Yarmouth Flood Defences – Epoch 2 – 2016 to 2021 | East of England | Anglian Eastern | East Anglia | Great Yarmouth | Great Yarmouth | Great Yarmouth | Environment Agency | Development | 24066.02 | 17720.005 | 6346.015 | 106.075 | 17586.331 | 2019-2021 | Beyond 2021 | 1415 | 0 | 1415 | 0
Hemsby Flood Risk Mitigation Project | East of England | Anglian Eastern | East Anglia | Great Yarmouth | Hemsby, NR29 4NH | Great Yarmouth | Norfolk County Council | Development | 325.003 | 185.005 | 139.998 | 14.291 | 142.916 | 2017-2019 | By April 2021 | 90 | 0 | 90 | 0
Martham Boat Dyke Culvert Replacement | East of England | Anglian Eastern | East Anglia | Great Yarmouth | Martham CP | Great Yarmouth | Broads (2006) IDB | Development | 90 | 1.099 | 88.901 | 0 | 1.099 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Thurne Boat Dyke Culvert Replacement | East of England | Anglian Eastern | East Anglia | Great Yarmouth | Thurne CP | Great Yarmouth | Broads (2006) IDB | Development | 90.001 | 30 | 60.001 | 0 | 8.461 | 2019-2021 | Beyond 2021 | 0 | 0 | 5 | 0
Broads IDB Pumping Station Telemetry Improvements | East of England | Anglian Eastern | East Anglia | N Norf, Gt Yarmouth; Broadland | Various | Great Yarmouth | Broads (2006) IDB | Development | 89.998 | 59.997 | 30.001 | 0 | 9.113 | Beyond 2021 | Beyond 2021 | 0 | 0 | 25 | 0
Ipswich Flood Defence Management Strategy: Tidal Barrier | East of England | Anglian Eastern | East Anglia | Ipswich | River Orwell, Ipswich, Suffolk | Ipswich | Environment Agency | Construction | 58164.996 | 19511.997 | 38652.999 | 920.5 | 920.5 | By April 2017 | By April 2019 | 1010 | 0 | 1010 | 0
Norwich Oak Lane Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Norwich North | King's Lynn | King's Lynn and West Norfolk | Anglian Water | Development | 1116.796 | 10 | 1106.796 | 0 | 1.285 | Beyond 2021 | Beyond 2021 | 0 | 0 | 30 | 0
Heybridge Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Maldon | Heybridge, Essex | Maldon | Environment Agency | Pipeline | 9940.374 | 629.982 | 9310.392 | 84.161 | 0 | 2019-2021 | Beyond 2021 | 0 | 0 | 135 | 0
Debenham Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Central Suffolk North Ipswich | Centrall Suffolk & North Ipswich | Mid Suffolk | Environment Agency | Pipeline | 1548.467 | 377.998 | 1170.469 | 46.301 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 10 | 0
Needham Market flood risk management project | East of England | Anglian Eastern | East Anglia | Bury St. Edmunds | Needham Market | Mid Suffolk | Environment Agency | Pipeline | 262.201 | 160.04 | 102.161 | 14.891 | 105.818 | 2017-2019 | By April 2021 | 0 | 0 | 20 | 0
Chapelfield Drainage Improvements | East of England | Anglian Eastern | East Anglia | North Norfolk | Chapelfield, Stalham, Norfolk. River Ant | North Norfolk | Broads (2006) IDB | Development | 40.001 | 7.001 | 33 | 0 | 7.001 | 2019-2021 | By April 2021 | 1 | 0 | 1 | 0
Cromer Coast Protection Scheme | East of England | Anglian Eastern | East Anglia | North Norfolk | Cromer | North Norfolk | North Norfolk District Council | Development | 8140.049 | 8140.049 | 0 | 80 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 315
Hickling Drainage Improvements | East of England | Anglian Eastern | East Anglia | North Norfolk | Hickling, Norfolk. | North Norfolk | Broads (2006) IDB | Development | 40 | 4.5 | 35.5 | 0 | 4.5 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Horse Fen Pumping Station Replacement | East of England | Anglian Eastern | East Anglia | North Norfolk | Ludham CP | North Norfolk | Broads (2006) IDB | Development | 100.001 | 50.001 | 50 | 0 | 7.481 | Beyond 2021 | Beyond 2021 | 0 | 0 | 15 | 0
Horsey Pumping Station Replacement | East of England | Anglian Eastern | East Anglia | North Norfolk | Horsey CP | North Norfolk | Broads (2006) IDB | Development | 80 | 39.999 | 40.001 | 6.417 | 30.001 | 2017-2019 | By April 2021 | 20 | 0 | 20 | 0
Irstead Pumping Station Replacement | East of England | Anglian Eastern | East Anglia | North Norfolk | Barton Turf CP | North Norfolk | Broads (2006) IDB | Development | 79.999 | 29.107 | 50.892 | 0 | 5.282 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Mundesley Coast Protection Scheme | East of England | Anglian Eastern | East Anglia | North Norfolk | Mundesley | North Norfolk | North Norfolk District Council | Development | 1868.001 | 1561 | 307.001 | 143.089 | 1417.911 | 2019-2021 | By April 2021 | 0 | 270 | 0 | 270
Tonnage Pumping Station Replacement | East of England | Anglian Eastern | East Anglia | North Norfolk | Dilham CP | North Norfolk | Broads (2006) IDB | Development | 80 | 5 | 75 | 0 | 5 | 2019-2021 | By April 2021 | 1 | 0 | 1 | 0
Cromer Flood Surface Water Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | North Norfolk | Cromer | North Norfolk | Norfolk County Council | Development | 825.005 | 766.007 | 58.998 | 18.578 | 144.752 | 2017-2019 | By April 2021 | 0 | 0 | 350 | 0
Eccles to Winterton Coastal Management Stage 2 - Protection of Designated Sites & Properties | East of England | Anglian Eastern | East Anglia | North Norfolk | Happisburgh to Winterton, Norfolk | North Norfolk | Environment Agency | Development | 16518.999 | 16518.999 | 0 | 42.763 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 60 | 0
North Walsham Surface Water Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | North Norfolk | North Walsham | North Norfolk | Norfolk County Council | Development | 524.995 | 364.996 | 159.999 | 21.779 | 290.354 | 2017-2019 | By April 2021 | 0 | 0 | 220 | 0
Bacton Gas Terminal to Ostend Coastal Management Scheme | East of England | Anglian Eastern | East Anglia | North Norfolk | Bacton, Walcott and Ostend, Norfolk | North Norfolk | North Norfolk District Council | Pipeline | 27400.002 | 1800.002 | 25600 | 310.85 | 1489.152 | 2017-2019 | By April 2021 | 0 | 240 | 0 | 240
Hickling Reedbeed Habitat Creation | East of England | Anglian Eastern | East Anglia | North Norfolk | Potter Heigham and Hickling | North Norfolk | Environment Agency | Pipeline | 1357.235 | 1357.235 | 0 | 41.644 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Norwich: Catton Grove and Sewell Surface Water Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Norwich North | Norwich, Catton Grove and Sewell | Norwich | Norfolk County Council | Development | 384.999 | 280 | 104.999 | 0 | 60.939 | 2019-2021 | Beyond 2021 | 0 | 0 | 130 | 0
Norwich: Nelson and Town Close Surface Water Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Norwich South | Norwich, Nelson and Town Close | Norwich | Norfolk County Council | Development | 385.001 | 280.002 | 104.999 | 0 | 60.939 | 2019-2021 | Beyond 2021 | 0 | 0 | 130 | 0
Rawreth and Rawreth Shot Community Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Rayleigh and Wickford | Wickford, River Crouch | Rochford | Environment Agency | Pipeline | 629.007 | 265.008 | 363.999 | 30.847 | 0 | 2019-2021 | Beyond 2021 | 0 | 0 | 25 | 0
Haddiscoe Pump Replacement | East of England | Anglian Eastern | East Anglia | South Norfolk | Thorpe and Haddiscoe Marshes | South Norfolk | Waveney, Lower Yare and Lothingland IDB | Development | 258.004 | 258.004 | 0 | 0 | 195.683 | 2019-2021 | Beyond 2021 | 0 | 0 | 35 | 0
Langley Double Pump Replacement and Improvements | East of England | Anglian Eastern | East Anglia | South Norfolk | Langley and Hardley Marshes | South Norfolk | Waveney, Lower Yare and Lothingland IDB | Development | 234.303 | 234.303 | 0 | 53.968 | 155.458 | 2017-2019 | By April 2021 | 25 | 0 | 25 | 0
Iken Pumping Station Refurbishment | East of England | Anglian Eastern | East Anglia | Suffolk Coastal | Iken Village and Marshes | Suffolk Coastal | East Suffolk IDB | Development | 165.997 | 75.999 | 89.998 | 6.847 | 46.733 | 2017-2019 | By April 2021 | 15 | 0 | 15 | 0
Sudbourne Pumping Station Refurbishment | East of England | Anglian Eastern | East Anglia | Suffolk Coastal | Sudbourne, Boulge Hall and Town Maeshes | Suffolk Coastal | East Suffolk IDB | Development | 166.001 | 146 | 20.001 | 24.687 | 115.503 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Jaywick Beach Management Scheme | East of England | Anglian Eastern | East Anglia | Clacton | Jaywick | Tendring | Environment Agency | Development | 7773.64 | 7773.64 | 0 | 0 | 25.31 | Beyond 2021 | Beyond 2021 | 0 | 0 | 2475 | 0
West Clacton to Jaywick Sea Defences Improvements | East of England | Anglian Eastern | East Anglia | Clacton | Coast | Tendring | Environment Agency | Development | 6014.999 | 6014.999 | 0 | 0 | 19.584 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Seawick Sea Defence Improvements | East of England | Anglian Eastern | East Anglia | Clacton | Seawick, Essex | Tendring | Environment Agency | Pipeline | 967.994 | 735.897 | 232.097 | 46.309 | 64.471 | 2017-2019 | By April 2021 | 0 | 0 | 90 | 0
Thames Estuary Asset Management 2100 Programme (Essex works only) | East of England | Anglian Eastern | East Anglia | Thurrock | Canvey Island, Leigh and Southend, East Tilbury, Shellhaven and Fobbing, Purfleet, Bowers Marshes and Hadleigh | Thurrock | Environment Agency | Construction | 69333.551 | 67410.154 | 1923.397 | 5064 | 32569 | By April 2017 | Beyond 2021 | 2270 | 0 | 21695 | 0
Stanford-le-Hope Surface Water Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | South Basildon and East Thurrock | Stanford-le-Hope | Thurrock | Thurrock Council | Development | 722.89 | 326.186 | 396.704 | 39.595 | 246.725 | 2017-2019 | By April 2021 | 85 | 0 | 85 | 0
Tilbury Barrier - Dual Function Lock Gate Installation | East of England | Anglian Eastern | East Anglia | Thurrock | Tilbury, Essex | Thurrock | Environment Agency | Development | 14183.997 | 10105 | 4078.997 | 3098.504 | 6500.167 | 2017-2019 | Beyond 2021 | 2500 | 0 | 2500 | 0
Tilbury Town Surface Water Flood Study | East of England | Anglian Eastern | East Anglia | Thurrock | Tilbury, Essex | Thurrock | Thurrock Council | Pipeline | 47.499 | 22.5 | 24.999 | 2.075 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Leiston Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Suffolk Coastal | Leiston | Uttlesford | Suffolk County Council | Development | 158.001 | 103.002 | 54.999 | 9.511 | 77.395 | 2017-2019 | By April 2021 | 15 | 0 | 15 | 0
Lowestoft Flood Risk Management Project | East of England | Anglian Eastern | East Anglia | Waveney | Lowestoft Lake Lothing and Kirkley Stream | Waveney | Waveney District Council | Development | 22490.803 | 4650.8 | 17840.003 | 563.779 | 3187.021 | 2017-2019 | By April 2021 | 0 | 0 | 415 | 0
Easton Broad Flood Management Project | East of England | Anglian Eastern | East Anglia | Suffolk Coastal | Easton Broad, Suffolk | Waveney | Environment Agency | Pipeline | 1495.503 | 1495.503 | 0 | 33.068 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Blyth Harbour North Pier Fender Replacement Works | East of England | Anglian Eastern | East Anglia | Waveney | Southwold | Waveney | Waveney District Council | Pipeline | 379.997 | 159.997 | 220 | 28.176 | 58.337 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
North Forty Foot drain revetments | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | Boston | Boston | Black Sluice IDB | Construction | 532 | 272 | 260 | 122 | 0 | By April 2017 | By April 2021 | 80 | 0 | 80 | 0
Culverted Watercourse Re-lining | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | Spalding, Lincolnshire - Pennygate Drain | Boston | Welland and Deepings IDB | Construction | 1140 | 660 | 480 | 200 | 100 | By April 2017 | By April 2019 | 250 | 0 | 250 | 0
Culverted Watercourse Lining | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | Town | Boston | Witham Fourth District IDB | Construction | 450 | 450 | 0 | 45 | 135 | By April 2017 | By April 2019 | 150 | 0 | 220 | 0
Boston Barrage/Barrier Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | River Witham, Boston, Lincs | Boston | Environment Agency | Development | 90339.95 | 90339.95 | 0 | 4910 | 74377.876 | 2017-2019 | By April 2021 | 14255 | 0 | 14255 | 0
Boston Haven Banks | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | South Holland and The Deepings | The Tidal Haven Banks, Boston, Lincolnshire | Boston | Environment Agency | Development | 2000 | 1400 | 600 | 1100 | 0 | 2017-2019 | By April 2019 | 310 | 0 | 310 | 0
Five Towns Sluice Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | Fosdyke Bridge | Boston | Welland and Deepings IDB | Development | 792 | 782 | 10 | 47 | 735 | 2017-2019 | By April 2021 | 190 | 0 | 190 | 0
Risegate Eau Sluice Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | Fosdyke Bridge | Boston | Welland and Deepings IDB | Development | 792 | 782 | 10 | 235 | 500 | 2017-2019 | By April 2019 | 130 | 0 | 130 | 0
Lade Bank Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | Inland | Boston | Witham Fourth District IDB | Development | 500 | 500 | 0 | 25 | 450 | 2017-2019 | By April 2019 | 185 | 0 | 185 | 0
Works Arising from Wash Banks Strategy - Wrangle seabanks | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Boston and Skegness | Gib Point to Hunstanton | Boston | Witham Fourth District IDB | Development | 675.33 | 504 | 171.33 | 500 | 0 | 2017-2019 | By April 2019 | 440 | 0 | 440 | 0
East Street, Long Buckby - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Daventry | East Street, Long Buckby | Daventry | Northamptonshire County Council | Pipeline | 565 | 166.165 | 398.835 | 0 | 146.165 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Humber - Donna Nook | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Louth | East Lindsey | Environment Agency | Construction | 8535.15 | 8535.15 | 0 | 50 | 876.65 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Lincshore | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Mablethorpe to Skegness | East Lindsey | Environment Agency | Construction | 65792.126 | 65792.126 | 0 | 2600 | 17730.226 | By April 2017 | Beyond 2021 | 13115 | 0 | 33395 | 0
Works Arising from Witham Opportunity Study - Lower | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | River Witham, Lincs | East Lindsey | Environment Agency | Development | 2190 | 1190 | 1000 | 50 | 600 | 2019-2021 | Beyond 2021 | 0 | 0 | 345 | 0
Horncastle - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Horncastle | East Lindsey | Lincolnshire County Council | Development | 426.607 | 106.25 | 320.357 | 73.75 | 0 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Kirkby on Bain - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Kirkby on Bain | East Lindsey | Lincolnshire County Council | Development | 210 | 105 | 105 | 75 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Toynton St Peter - Surface Water Flood Risk Improvements | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Toynton St Peter | East Lindsey | Lincolnshire County Council | Development | 275 | 100 | 175 | 5 | 85 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Boygrift Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Sandilands | East Lindsey | Lindsey Marsh Drainage Board | Development | 397 | 297 | 100 | 297 | 0 | 2017-2019 | By April 2019 | 345 | 0 | 345 | 0
Saltfleet Pumping Station Replacement | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Saltfleet | East Lindsey | Lindsey Marsh Drainage Board | Development | 2115 | 1015 | 1100 | 0 | 1015 | 2019-2021 | By April 2021 | 175 | 0 | 175 | 0
Theddlethorpe Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Louth and Horncastle | Theddlethorp | East Lindsey | Lindsey Marsh Drainage Board | Development | 537 | 385 | 152 | 0 | 385 | 2017-2019 | By April 2019 | 175 | 0 | 175 | 0
Raunds Hog Dyke Culvert Improvement | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Corby | Raunds, Hog Dyke and Rushden | East Northamptonshire | Environment Agency | Development | 901 | 901 | 0 | 0 | 88 | Beyond 2021 | Beyond 2021 | 0 | 0 | 65 | 0
Duck End & Freeman's Lane, Denford - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Corby | Duck End and Freeman's Lane, Denford | East Northamptonshire | Northamptonshire County Council | Pipeline | 317.4 | 46.859 | 270.541 | 0 | 31.859 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Hundred of Wisbech Channel Conveyance Improvements | East of England | Anglian Northern | Lincolnshire and Northamptonshire | North East Cambridgeshire | Wisbech, Cambs | Fenland | Hundred of Wisbech IDB | Development | 250 | 150 | 100 | 150 | 0 | 2017-2019 | By April 2019 | 150 | 0 | 150 | 0
Pyewipe Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Lincoln | South bank Fossdyke | Lincoln | Upper Witham IDB | Construction | 118.25 | 23.2625 | 94.9875 | 12.8 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Local Communities at Risk - Works Arising | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Lincoln | Lincolnshire | Lincoln | Lincolnshire County Council | Development | 1308 | 428 | 880 | 100 | 300 | 2017-2019 | Beyond 2021 | 0 | 0 | 395 | 0
Port of Immingham sea defence improvements | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | Immingham, North East Lincolnshire | North East Lincolnshire | North East Lincolnshire Council | Construction | 10398 | 4471 | 5927 | 0 | 1921 | By April 2017 | By April 2021 | 0 | 0 | 0 | 0
Humber - Cleethorpes & Humberston | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | Cleethorpes, Humberston and Tetney | North East Lincolnshire | Environment Agency | Development | 4550 | 3500 | 1050 | 50 | 300 | Beyond 2021 | Beyond 2021 | 0 | 0 | 2200 | 0
Humber - Immingham to Freshney sea defence improvements | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | Immingham to Grimsby | North East Lincolnshire | Environment Agency | Development | 5010 | 5010 | 0 | 0 | 210 | Beyond 2021 | Beyond 2021 | 0 | 0 | 4900 | 0
North East Lincolnshire Surface Water - Peaksfield Avenue | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Great Grimsby | Grimsby | North East Lincolnshire | North East Lincolnshire Council | Development | 275 | 115 | 160 | 0 | 115 | 2017-2019 | By April 2019 | 150 | 0 | 150 | 0
North East Lincolnshire Surface Water - North Immingham | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | Immingham, Grimsby, Humberston | North East Lincolnshire | North East Lincolnshire Council | Development | 350 | 290 | 60 | 0 | 290 | 2019-2021 | By April 2021 | 380 | 0 | 380 | 0
North East Lincolnshire Surface Water - Willingham Street | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Great Grimsby | Grimsby | North East Lincolnshire | North East Lincolnshire Council | Development | 250 | 190 | 60 | 190 | 0 | 2017-2019 | By April 2019 | 155 | 0 | 155 | 0
Damford Pumping Station Flood Resilience | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Damford | North Kesteven | Black Sluice IDB | Construction | 65 | 65 | 0 | 35 | 0 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Helpringham Fen Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Helpringham Fen | North Kesteven | Black Sluice IDB | Construction | 84 | 84 | 0 | 54 | 0 | By April 2017 | By April 2019 | 25 | 0 | 25 | 0
Branston Fen Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Bardney | North Kesteven | Witham First District IDB | Construction | 79 | 51 | 28 | 12 | 0 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Works Arising from Upper Witham Strategy Review | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Upper Witham | North Kesteven | Environment Agency | Development | 1730 | 1730 | 0 | 100 | 1500 | 2017-2019 | Beyond 2021 | 0 | 0 | 1260 | 0
Leasingham - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Leasingham | North Kesteven | Lincolnshire County Council | Development | 25 | 25 | 0 | 0 | 25 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Ruskington - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Ruskington | North Kesteven | Lincolnshire County Council | Development | 287.5 | 115 | 172.5 | 55 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Scopwick - Surface Water Flood Risk Improvements | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Scopwick | North Kesteven | Lincolnshire County Council | Development | 175 | 75 | 100 | 50 | 15 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Timberland - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Timberland | North Kesteven | Lincolnshire County Council | Development | 245 | 106 | 139 | 0 | 101 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Aubourn Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | EA Brant Washland Site | North Kesteven | Upper Witham IDB | Development | 146 | 146 | 0 | 9 | 137 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Sand Syke Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Bassingham | North Kesteven | Upper Witham IDB | Development | 138 | 138 | 0 | 0 | 47 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Billinghay Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Tattershall Bridge, Lincolnshire | North Kesteven | Witham First District IDB | Development | 146 | 98 | 48 | 6 | 75 | 2017-2019 | By April 2021 | 30 | 0 | 30 | 0
North Kyme Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | North Kyme, Lincolnshire | North Kesteven | Witham First District IDB | Development | 71 | 71 | 0 | 0 | 9 | 2019-2021 | Beyond 2021 | 0 | 0 | 20 | 0
Swaton Resilience Scheme | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Sleaford and North Hykeham | Swaton Village | North Kesteven | Environment Agency | Pipeline | 1237 | 462 | 775 | 0 | 179 | 2017-2019 | Beyond 2021 | 0 | 0 | 25 | 0
South Ferriby Pointing Doors | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Brigg and Goole | South Ferriby | North Lincolnshire | Environment Agency | Construction | 1184 | 1184 | 0 | 250 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
East Halton flood defence improvements | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | East Halton, North Lincs | North Lincolnshire | North Lincolnshire Council | Development | 13500 | 4100 | 9400 | 3600 | 0 | 2017-2019 | By April 2019 | 1 | 0 | 1 | 0
Ulceby Flood Alleviation Scheme | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | Spruce Lane, Coronation Road, Ulceby, North Lincs | North Lincolnshire | North Lincolnshire Council | Development | 403 | 28 | 375 | 28 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Humber - Barton Haven to New Holland tidal defence improvements | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | Barrow upon Humber, North Lincolnshire | North Lincolnshire | Environment Agency | Pipeline | 23283 | 11912 | 11371 | 77 | 0 | 2019-2021 | Beyond 2021 | 0 | 0 | 1810 | 0
Humber - Halton and Killingholme Marshes | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Cleethorpes | East Halton & North Killingholme | North Lincolnshire | Environment Agency | Pipeline | 8174 | 6124 | 2050 | 0 | 10 | 2017-2019 | Beyond 2021 | 0 | 0 | 4 | 0
Humber - Winteringham Ings & South Ferriby | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Brigg and Goole | Winteringham to South Ferriby | North Lincolnshire | Environment Agency | Pipeline | 14466 | 5566 | 8900 | 147 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 130 | 0
Northern Area Reservoirs Statutory Obligations | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | South Northamptonshire | Northampton and other FSR's | Northampton | Environment Agency | Construction | 2071 | 2071 | 0 | 50 | 100 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Brook Drain Flood Risk Management Peterborough | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Daventry | Nether Heyford | Peterborough | Environment Agency | Development | 329.843 | 179.843 | 150 | 166.843 | 0 | 2017-2019 | By April 2019 | 140 | 0 | 140 | 0
Sutton St James Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | South Holland and The Deepings | PUMPING STATION ON SOUTH SIDE OF SOUTH HOLLAND MAIN DRAIN BETWEEN CLIFTONS BRIDGE AND REDHOUSE BRIDGE NEAR SUTTON ST JAMES | South Holland | South Holland IDB | Construction | 500 | 500 | 0 | 180 | 0 | By April 2017 | By April 2019 | 135 | 0 | 135 | 0
Chalk Lane Sluice - Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | South Holland and The Deepings | Fens | South Holland | Kings Lynn IDB | Development | 140 | 119 | 21 | 0 | 119 | 2019-2021 | By April 2021 | 225 | 0 | 225 | 0
Hundreds Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | South Holland and The Deepings | B1040, Nene Terrace, Peterborough | South Holland | North Level District (2010) IDB | Development | 40 | 18 | 22 | 18 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Fleet Haven Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | South Holland and The Deepings | PUMPING STATION IS WITHIN THE RAF HOLBEACH SITE OFF DURHAMS ROAD, GEDNEY MARSH, SPALDING | South Holland | South Holland IDB | Development | 700 | 700 | 0 | 40 | 660 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Westmere Pumping Station and Sluice Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | South Holland and The Deepings | THE PUMPING STATION AND TIDAL SLUICE ARE ON THE TIDAL BANK OF THE RIVER NENE OFF PETTS LANE, SUTTON BRIDGE, SPALDING | South Holland | South Holland IDB | Development | 535 | 190 | 345 | 155 | 0 | 2017-2019 | By April 2019 | 3 | 0 | 3 | 0
Sempringham Fen Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Grantham and Stamford | Boston | South Kesteven | Black Sluice IDB | Construction | 161 | 161 | 0 | 131 | 0 | By April 2017 | By April 2019 | 30 | 0 | 30 | 0
Greatford Flood Alleviation Scheme | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Grantham and Stamford | Greatford | South Kesteven | Environment Agency | Development | 118 | 86 | 32 | 0 | 86 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Bourne Eau Health and Safety Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Grantham and Stamford | Boune Eau | South Kesteven | Environment Agency | Pipeline | 470.868 | 470.868 | 0 | 250 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Wootton Brook Flood Risk Management | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Daventry | Wootton Brook | South Northamptonshire | Environment Agency | Development | 145 | 90 | 55 | 0 | 90 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
Nether Heyford Flood Alleviation Scheme | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Daventry | Nether Heyford | South Northamptonshire | Environment Agency | Pipeline | 1347.784 | 1000.252 | 347.532 | 207 | 700 | 2017-2019 | By April 2021 | 50 | 0 | 50 | 0
Welland & Nene Property Level Protection | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Wellingborough | Welland & Nene Catchment | Wellingborough | Environment Agency | Pipeline | 954 | 423 | 531 | 100 | 263 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Keelby - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Gainsborough | Keelby | West Lindsey | Lincolnshire County Council | Development | 295 | 112.5 | 182.5 | 80 | 20 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Middle Rasen - Surface Water Flood Risk Improvement Works | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Gainsborough | Middle Rasen | West Lindsey | Lincolnshire County Council | Development | 190 | 45 | 145 | 30 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Broxholme Pumping Station | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Gainsborough | River Till | West Lindsey | Upper Witham IDB | Development | 119.6 | 92 | 27.6 | 0 | 92 | 2017-2019 | By April 2021 | 3 | 0 | 3 | 0
Thorpe in the Fallows Pumping Station Environmental/Efficiency Scheme | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Gainsborough | Saxilby | West Lindsey | Upper Witham IDB | Development | 27 | 27 | 0 | 0 | 27 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Metheringham Pumping Station Refurbishment | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Gainsborough | Sots Hole, Lincolnshire | West Lindsey | Witham First District IDB | Development | 163 | 158 | 5 | 25 | 133 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Upper Hearne Brook Flood Alleviation Scheme (Beeches Road) | South West | English Severn and Wye | West Midlands | Cheltenham | Cheltenham - Hearne Brook | Cheltenham | Cheltenham Borough Council | Development | 180 | 130 | 50 | 0 | 25 | Beyond 2021 | Beyond 2021 | 20 | 0 | 20 | 0
Canley, Canley Brook Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Coventry South | Coventry, Canley Brook | Coventry | Environment Agency | Development | 500 | 180 | 320 | 0 | 27 | Beyond 2021 | Beyond 2021 | 0 | 0 | 50 | 0
Butt Lane, Coventry, River Sherbourne, Property Level Protection Scheme | West Midlands | English Severn and Wye | West Midlands | Coventry North West Broro Const | Allesley, Coventry | Coventry | Environment Agency | Pipeline | 314.903 | 186.403 | 128.5 | 186.403 | 0 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Deans Walk, Property Level Protection, Gloucester | South West | English Severn and Wye | West Midlands | Gloucester | Deans Walk, Gloucester - River Twyver | Gloucester | Gloucestershire County Council | Development | 230 | 220 | 10 | 220 | 0 | 2017-2019 | By April 2019 | 45 | 0 | 45 | 0
Alney Island Flood Alleviation Scheme Improvements, River Severn | South West | English Severn and Wye | West Midlands | Gloucester | Pool Meadow Alney Island Gloucester. East channel river Severn | Gloucester | Environment Agency | Development | 995 | 670 | 325 | 0 | 470 | 2019-2021 | By April 2021 | 0 | 0 | 60 | 0
Podsmead Playing Fields, Sports Complex, Sustainable Drainage System | South West | English Severn and Wye | West Midlands | Gloucester | Podsmead, Gloucester, GL1 5TX | Gloucester | Gloucestershire County Council | Development | 156.7 | 50 | 106.7 | 50 | 0 | Beyond 2021 | Beyond 2021 | 60 | 0 | 60 | 0
Bishops Frome, Herefordshire Property Level Protection, River Frome | West Midlands | English Severn and Wye | West Midlands | North Herefordshire | Bishops Frome Herefordshire | Herefordshire, County of | Environment Agency | Development | 66.1 | 28 | 38.1 | 0 | 28 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Cherry Brook, Hope Under Dinmore, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Hereford and South Herefordshire | Hope Under Dinmore | Herefordshire, County of | Herefordshire Council | Development | 151 | 69 | 82 | 0 | 69 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Gosford Brook, Brimfield, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | North Herefordshire | Brimfield, Herefordshire | Herefordshire, County of | Herefordshire Council | Development | 121.3 | 96.3 | 25 | 0 | 17 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
River Lugg, Leominster Flood Alleviation Scheme Improvements | West Midlands | English Severn and Wye | West Midlands | North Herefordshire | Leominster, Herefordshire | Herefordshire, County of | Environment Agency | Development | 1808 | 1808 | 0 | 926 | 630 | 2017-2019 | By April 2019 | 250 | 0 | 250 | 0
Ewyas Harold Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Hereford and South Herefordshire | Ewyas Harold, Herefordshire on the Dulas book | Herefordshire, County of | Environment Agency | Development | 710 | 655 | 55 | 0 | 35 | 2017-2019 | By April 2021 | 0 | 0 | 30 | 0
Halesend Estate Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Stourbridge | Halesend Estate, Storridge, Cradley | Herefordshire, County of | Herefordshire Council | Development | 20 | 10 | 10 | 10 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Huntsmans Drive, Hereford Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Hereford and South Herefordshire | 42, 43,44,45 Huntsmans Drive, Hereford | Herefordshire, County of | Herefordshire Council | Development | 5 | 5 | 0 | 5 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Severn Stoke Flood Alleviation Scheme , River Severn | West Midlands | English Severn and Wye | West Midlands | West Worcestershire | Severn Stoke, Worcs | Malvern Hills | Environment Agency | Development | 1405 | 190 | 1215 | 0 | 190 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Bilton Road, Rugby, Surface Water Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Warwick and Leamington | Bilton Road, Rugby | Rugby | Warwickshire County Council | Development | 315 | 95 | 220 | 0 | 95 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
Pailton, Rugby, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Rugby | Lillington | Rugby | Warwickshire County Council | Development | 47.6 | 35.6 | 12 | 35.6 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Withybrook, Warwickshire Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Rugby | Withybrook | Rugby | Severn Trent Water | Development | 609.6 | 40 | 569.6 | 30 | 0 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Bagley Brook Outfall replacement | West Midlands | English Severn and Wye | West Midlands | Shrewsbury and Atcham | Shrewsbury, Bagley Brook | Shropshire | Environment Agency | Construction | 150 | 150 | 0 | 0 | 150 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Cleobury Mortimer Pudding Brook Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Ludlow | Cleobury Mortimer | Shropshire | Shropshire Council | Construction | 329 | 179 | 150 | 0 | 179 | By April 2017 | By April 2021 | 30 | 0 | 30 | 0
Slow the Flow - Shropshire Rivers | West Midlands | English Severn and Wye | West Midlands | Ludlow | Shropshire/Herefordshire. | Shropshire | Environment Agency | Construction | 470 | 470 | 0 | 70 | 260 | By April 2017 | By April 2021 | 0 | 0 | 0 | 0
Westbury Brook, Westbury, Shropshire Property Level Resilience | West Midlands | English Severn and Wye | West Midlands | Shrewsbury and Atcham | Westbury, Shropshire | Shropshire | Shropshire Council | Construction | 66 | 50 | 16 | 45 | 0 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
East Church Stretton Surface and Ordinary Watercourse Flood Relief Works | West Midlands | English Severn and Wye | West Midlands | Ludlow | Church Stretton | Shropshire | Shropshire Council | Development | 500 | 425 | 75 | 0 | 50 | 2019-2021 | By April 2021 | 0 | 0 | 110 | 0
Hunters Gate, Surface Water Flood Alleviation Scheme, Much Wenlock | West Midlands | English Severn and Wye | West Midlands | Ludlow | Much Wenlock, Shropshire | Shropshire | Shropshire Council | Development | 168 | 138 | 30 | 128 | 0 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Shrewsbury, River Severn Property Level Protection | West Midlands | English Severn and Wye | West Midlands | Shrewsbury and Atcham | Shrewsbury, River Severn | Shropshire | Environment Agency | Development | 150 | 90 | 60 | 0 | 72.5 | 2017-2019 | By April 2021 | 0 | 0 | 25 | 0
Wesley Brook, Shifnal, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | The Wrekin | Shifnal | Shropshire | Shropshire Council | Development | 532 | 282 | 250 | 0 | 172 | 2017-2019 | By April 2021 | 85 | 0 | 85 | 0
Daniels Brook Flood Alleviation Scheme | South West | English Severn and Wye | West Midlands | Gloucester | Gloucester | South Staffordshire | Environment Agency | Construction | 913.817 | 123.82 | 789.997 | 2.126 | 4 | By April 2017 | By April 2019 | 0 | 0 | 180 | 0
Cherington, Shipston-on-Stour, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Stratford-on-Avon | Cherington | Stratford-on-Avon | Warwickshire County Council | Construction | 271.4 | 135 | 136.4 | 0 | 67.5 | By April 2017 | By April 2019 | 20 | 0 | 20 | 0
Ladbroke, Southam, Lot Brook, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Kenilworth and Southam | Ladbroke | Stratford-on-Avon | Warwickshire County Council | Development | 170 | 60 | 110 | 60 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Stratford-Upon-Avon, Racecourse Brook, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Stratford-on-Avon | North West Stratford-Upon-Avon | Stratford-on-Avon | Environment Agency | Development | 805 | 590 | 215 | 590 | 0 | 2017-2019 | By April 2019 | 130 | 0 | 130 | 0
Lucy's Mill Health and Safety Improvement Works | West Midlands | English Severn and Wye | West Midlands | Stratford-on-Avon | Stratford Upon Avon | Stratford-on-Avon | Environment Agency | Pipeline | 250 | 250 | 0 | 50 | 200 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Coal Brook, Coalbrookdale, Flood Relief Works | West Midlands | English Severn and Wye | West Midlands | Telford | Coalbrookdale, R Severn | Telford and Wrekin | Telford and Wrekin Borough Council | Development | 241 | 201 | 40 | 0 | 201 | 2017-2019 | By April 2021 | 40 | 0 | 40 | 0
Undefended Properties in the Ironbridge Gorge Indvidual Property Protection | West Midlands | English Severn and Wye | West Midlands | Telford | Ironbridge | Telford and Wrekin | Shropshire Council | Development | 292 | 125 | 167 | 0 | 25 | 2019-2021 | Beyond 2021 | 0 | 0 | 40 | 0
River Severn, Minsterworth Flood Alleviation Scheme Erosion Protection | South West | English Severn and Wye | West Midlands | Forest of Dean | Minsterworth | Tewkesbury | Environment Agency | Construction | 252 | 172 | 80 | 18 | 125 | By April 2017 | By April 2019 | 25 | 0 | 25 | 0
Whaddon, Cheltenham Flood Alleviation Scheme | South West | English Severn and Wye | West Midlands | Tewkesbury | Cheltenham | Tewkesbury | Gloucestershire County Council | Construction | 1598 | 1298 | 300 | 10 | 0 | By April 2017 | By April 2019 | 215 | 0 | 215 | 0
Bishops Cleeve, Gloucestershire Flood Alleviation Scheme | South West | English Severn and Wye | West Midlands | Tewkesbury | Bishops Cleeve | Tewkesbury | Gloucestershire County Council | Development | 958.034 | 728.034 | 230 | 0 | 364 | 2019-2021 | Beyond 2021 | 0 | 0 | 90 | 0
Brockworth, Gloucestershire Surface Water Scheme | South West | English Severn and Wye | West Midlands | Tewkesbury | Brockworth, Gloucester | Tewkesbury | Gloucestershire County Council | Development | 197 | 142 | 55 | 127 | 0 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Churchdown Surface Water Scheme | South West | English Severn and Wye | West Midlands | Tewkesbury | Churchdown | Tewkesbury | Gloucestershire County Council | Development | 124 | 71 | 53 | 58 | 0 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Shrops Heref Worcs and Glos Invest to Save | West Midlands | English Severn and Wye | West Midlands | Various | Severn & Wye | Various | Environment Agency | Construction | 982 | 982 | 0 | 0 | 40 | By April 2017 | By April 2021 | 0 | 0 | 0 | 0
Gloucester to Tewkesbury River Severn Property Level Protection | South West | English Severn and Wye | West Midlands | Gloucester | Gloucester to Tewkesbury, River Severn | Various | Environment Agency | Development | 1440 | 513 | 927 | 0 | 111 | 2017-2019 | Beyond 2021 | 20 | 0 | 180 | 0
Shropshire Individual Property Protection Phase 2 | West Midlands | English Severn and Wye | West Midlands | Various | Shropshire | Various | Shropshire Council | Development | 76 | 36 | 40 | 36 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Warwick, St Johns Brook, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Warwick and Leamington | St Johns Brook, Warwick | Warwick | Environment Agency | Development | 1411.685 | 1319.685 | 92 | 460 | 756 | 2017-2019 | Beyond 2021 | 205 | 0 | 205 | 0
Diglis, Worcs Property Level Protection, River Severn | West Midlands | English Severn and Wye | West Midlands | Worcester | Diglis,Worcester, River Severn | Worcester | Environment Agency | Development | 120 | 86 | 34 | 0 | 76 | 2017-2019 | By April 2019 | 15 | 0 | 20 | 0
Worcester Property Level Protection, River Severn | West Midlands | English Severn and Wye | West Midlands | Worcester | Worcester, River Severn | Worcester | Environment Agency | Development | 204 | 146 | 58 | 0 | 130 | 2017-2019 | By April 2019 | 30 | 0 | 35 | 0
Himbleton, Bow Brook, Property Level Protection | West Midlands | English Severn and Wye | West Midlands | Mid Worcestershire | Himbleton | Wychavon | Environment Agency | Construction | 139 | 60 | 79 | 0 | 60 | By April 2017 | By April 2021 | 25 | 0 | 25 | 0
Badsey Brook (Broadway, Childswickham and Murcot) Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Mid Worcestershire | Badsey | Wychavon | Environment Agency | Development | 3821.383 | 2030 | 1791.383 | 100 | 1800 | 2017-2019 | By April 2019 | 250 | 0 | 250 | 0
Hunters Way, Droitwich Property Level Protection, Elmbridge Brook | West Midlands | English Severn and Wye | West Midlands | Mid Worcestershire | Droitwich, Elmbridge Brook | Wychavon | Environment Agency | Development | 176 | 86 | 90 | 0 | 43 | 2017-2019 | By April 2021 | 10 | 0 | 20 | 0
Evesham Property Level Resilience, River Avon | West Midlands | English Severn and Wye | West Midlands | Mid Worcestershire | Evesham | Wychavon | Environment Agency | Development | 852 | 367 | 485 | 0 | 67 | 2019-2021 | Beyond 2021 | 15 | 0 | 95 | 0
Braithwaite Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Copeland | Braithwaite, Cumbria | Allerdale | Environment Agency | Development | 800 | 300 | 500 | 100 | 200 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Flimby Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Workington | Flimby, Cumbria | Allerdale | Environment Agency | Development | 1100 | 400 | 700 | 200 | 200 | 2017-2019 | By April 2021 | 50 | 0 | 50 | 0
Wigton Flood Risk Management Scheme | North West | North West | Cumbria and Lancashire | Penrith and The Border | Wigton, Cumbria | Allerdale | Environment Agency | Development | 2000 | 700 | 1300 | 500 | 0 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Penrith Road, Keswick | North West | North West | Cumbria and Lancashire | Copeland | Keswick, Cumbria | Allerdale | Cumbria County Council | Pipeline | 1910 | 1760 | 150 | 1460 | 0 | 2017-2019 | By April 2019 | 290 | 0 | 290 | 0
Mill Beck, Barrow in Furness | North West | North West | Cumbria and Lancashire | Barrow and Furness | Barrow-in-Furness, Cumbria | Barrow-in-Furness | Environment Agency | Development | 2080 | 1925 | 155 | 0 | 150 | 2017-2019 | By April 2021 | 440 | 0 | 440 | 0
Jacks Key Reservoir Improvements, Darwen | North West | North West | Cumbria and Lancashire | Rossendale and Darwen | Darwen , Lancashire | Blackburn with Darwen | Environment Agency | Construction | 3178 | 3178 | 0 | 400 | 0 | By April 2017 | By April 2019 | 1100 | 0 | 1100 | 0
Birch Hall, Darwen | North West | North West | Cumbria and Lancashire | Rossendale and Darwen | Darwen, Lancashire | Blackburn with Darwen | Blackburn with Darwen Borough Council | Development | 305 | 140 | 165 | 0 | 140 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Darwen Surface Water Management Plan | North West | North West | Cumbria and Lancashire | Rossendale and Darwen | Darwen, Lancashire | Blackburn with Darwen | Blackburn with Darwen Borough Council | Development | 1135 | 1000 | 135 | 200 | 400 | 2017-2019 | By April 2021 | 65 | 0 | 65 | 0
Old Gate Drive, Blackburn | North West | North West | Cumbria and Lancashire | Blackburn | Blackburn, Lancashire | Blackburn with Darwen | Blackburn with Darwen Borough Council | Development | 222 | 192 | 30 | 0 | 192 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
River Darwen, Darwen | North West | North West | Cumbria and Lancashire | Rossendale and Darwen | Darwen, Lancashire | Blackburn with Darwen | Environment Agency | Development | 2050 | 2050 | 0 | 1070 | 0 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Blackpool Local Flood Risk Management Strategy Review | North West | North West | Cumbria and Lancashire | Blackpool South, Blackpool North and Cleveleys | Blackpool | Blackpool | Blackpool Council | Development | 100 | 100 | 0 | 60 | 40 | 2017-2019 | By April 2019 | 0 | 0 | 445 | 0
Bolton Culvert Improvements | North West | North West | Greater Manchester Merseyside and Cheshire | Bolton West, Bolton North East, and Bolton South East | Bolton, Greater Manchester | Bolton | Bolton Borough Council | Construction | 240 | 219 | 21 | 73 | 73 | By April 2017 | By April 2019 | 55 | 0 | 55 | 0
Bolton Upland Storage Project | North West | North West | Greater Manchester Merseyside and Cheshire | Bolton West | Various, Bolton, greater Manchester | Bolton | Bolton Borough Council | Development | 450 | 350 | 100 | 50 | 300 | 2017-2019 | By April 2019 | 100 | 0 | 100 | 0
Bolton Critical Culvert Rehabilitation | North West | North West | Greater Manchester Merseyside and Cheshire | Bolton West, Bolton North East, and Bolton South East | Bolton, Greater Manchester | Bolton | Bolton Borough Council | Development | 1250 | 1100 | 150 | 200 | 789 | 2017-2019 | By April 2019 | 90 | 0 | 90 | 0
Horwich Town Centre Flood Alleviation | North West | North West | Greater Manchester Merseyside and Cheshire | Bolton West | Horwich, Bolton, greater Manchester | Bolton | Bolton Borough Council | Development | 2452 | 2352 | 100 | 428 | 1724 | 2017-2019 | By April 2021 | 190 | 0 | 190 | 0
Bolton, River Croal | North West | North West | Greater Manchester Merseyside and Cheshire | Bolton South East | Bolton, Greater Manchester | Bolton | Environment Agency | Development | 1070 | 1070 | 0 | 0 | 70 | Beyond 2021 | Beyond 2021 | 0 | 0 | 295 | 0
Dean Brook Culvert, Bolton | North West | North West | Greater Manchester Merseyside and Cheshire | Bolton West | Bolton, Greater Manchester | Bolton | Environment Agency | Development | 250 | 250 | 0 | 250 | 0 | 2019-2021 | By April 2021 | 55 | 0 | 55 | 0
Radcliffe & Redvales FRM Scheme | North West | North West | Greater Manchester Merseyside and Cheshire | Bury South | Radcliffe, Greater Manchester | Bury | Environment Agency | Pipeline | 12405 | 10203 | 2202 | 235 | 1910 | 2019-2021 | Beyond 2021 | 0 | 0 | 1560 | 0
Carlisle (Post 15' Works) | North West | North West | Cumbria and Lancashire | Carlisle | Carlisle, Cumbria | Carlisle | Environment Agency | Development | 25000 | 25000 | 0 | 250 | 24650 | 2017-2019 | By April 2021 | 1665 | 0 | 1665 | 0
Gosling Sike, Carlisle | North West | North West | Cumbria and Lancashire | Penrith and The Border / Carlisle | Carlisle, Cumbria | Carlisle | Environment Agency | Development | 715 | 515 | 200 | 0 | 515 | 2017-2019 | By April 2021 | 80 | 0 | 80 | 0
Rickerby Park Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Carlisle | Rickerby Park, Cumbria | Carlisle | Environment Agency | Development | 1200 | 500 | 700 | 300 | 0 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Durranhill Public Realm Safety Improvements | North West | North West | Cumbria and Lancashire | Carlisle | Carlisle | Carlisle | Environment Agency | Pipeline | 26 | 26 | 0 | 26 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Pearl Street, Prestbury | North West | North West | Greater Manchester Merseyside and Cheshire | Macclesfield | Prestbury, Cheshire | Cheshire East | Cheshire East Council | Construction | 70 | 50 | 20 | 0 | 50 | By April 2017 | By April 2019 | 15 | 0 | 15 | 0
Tributaries of Poynton Brook, Poynton | North West | North West | Greater Manchester Merseyside and Cheshire | Macclesfield | Poynton, Cheshire | Cheshire East | Cheshire East Council | Development | 300 | 300 | 0 | 50 | 250 | 2017-2019 | By April 2019 | 100 | 0 | 100 | 0
Mobberley Brook and tributaries, Wilmslow | North West | North West | Greater Manchester Merseyside and Cheshire | Macclesfield | Wilmslow, Cheshire | Cheshire East | Cheshire East Council | Development | 225 | 26 | 199 | 20 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Cheshire Asset Inspection/CCTV Survey | North West | North West | Greater Manchester Merseyside and Cheshire | Crewe and Nantwich | Cheshire East | Cheshire East | Cheshire East Council | Development | 250 | 200 | 50 | 50 | 50 | 2017-2019 | Beyond 2021 | 100 | 0 | 400 | 0
Cheshire East Ordinary Watercourse Capital Maintenance | North West | North West | Greater Manchester Merseyside and Cheshire | TBC | Cheshire East | Cheshire East | Cheshire East Council | Development | 300 | 300 | 0 | 50 | 100 | 2017-2019 | Beyond 2021 | 90 | 0 | 175 | 0
Blakelow Road, Macclesfield | North West | North West | Greater Manchester Merseyside and Cheshire | Macclesfield | Macclesfield, Cheshire | Cheshire East | Cheshire East Council | Development | 120 | 120 | 0 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 50 | 0
A50 Pear Tree Cottages, Brereton | North West | North West | Greater Manchester Merseyside and Cheshire | Congleton | Brereton, Cheshire | Cheshire East | Cheshire East Council | Development | 135 | 15 | 120 | 0 | 15 | 2019-2021 | By April 2021 | 0 | 0 | 4 | 0
A6 Market Street, Danebank | North West | North West | Greater Manchester Merseyside and Cheshire | Macclesfield | Disley, Cheshire | Cheshire East | Cheshire East Council | Development | 100 | 100 | 0 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
River Bollin Tributaries, Macclesfield Town Centre | North West | North West | Greater Manchester Merseyside and Cheshire | Macclesfield | Macclesfield, Cheshire | Cheshire East | Cheshire East Council | Development | 290 | 225 | 65 | 45 | 180 | Beyond 2021 | Beyond 2021 | 80 | 0 | 80 | 0
Chorley District Focussed Studies - Eccleston, Brinscall, Whittle-le-Woods, Coppull | North West | North West | Cumbria and Lancashire | South Ribble / Chorley | Chorley, Lancashire | Chorley | Lancashire County Council | Development | 70 | 70 | 0 | 70 | 0 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Fairways, Seascale Attenuation Scheme | North West | North West | Cumbria and Lancashire | Copeland | Seascale, Cumbria | Copeland | Cumbria County Council | Construction | 255 | 215 | 40 | 125 | 0 | By April 2017 | By April 2019 | 15 | 0 | 15 | 0
Gosforth, West Cumbria | North West | North West | Cumbria and Lancashire | Copeland | Gosforth, West Cumbria | Copeland | Cumbria County Council | Development | 710 | 610 | 100 | 70 | 540 | 2017-2019 | By April 2021 | 190 | 0 | 190 | 0
Moresby Watercourse investigation | North West | North West | Cumbria and Lancashire | Copeland | Moresby parks | Copeland | Cumbria County Council | Development | 100 | 50 | 50 | 0 | 30 | 2019-2021 | Beyond 2021 | 0 | 0 | 5 | 0
Parton fluvial and surface water flooding investigation | North West | North West | Cumbria and Lancashire | Copeland | Parton, Cumbria | Copeland | Cumbria County Council | Development | 320 | 100 | 220 | 20 | 80 | 2017-2019 | By April 2021 | 15 | 0 | 15 | 0
Ravenglass, Cumbria | North West | North West | Cumbria and Lancashire | Copeland | Ravenglass, Cumbria | Copeland | Cumbria County Council | Development | 330 | 165 | 165 | 0 | 165 | 2017-2019 | By April 2021 | 30 | 0 | 30 | 0
Skirting Beck, Egremont | North West | North West | Cumbria and Lancashire | Copeland | Egremont, Cumbria | Copeland | Environment Agency | Development | 6937.913 | 5817.913 | 1120 | 1370.2 | 3766.15 | 2017-2019 | By April 2019 | 295 | 0 | 295 | 0
Whitehaven Coastal Erosion and Flooding Protection | North West | North West | Cumbria and Lancashire | Copeland | Whitehaven, Cumbria | Copeland | Copeland Borough Council | Development | 300 | 300 | 0 | 0 | 250 | 2019-2021 | By April 2021 | 105 | 0 | 105 | 0
Appleby Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Penrith and The Border | Appleby, Cumbria | Eden | Environment Agency | Development | 2500 | 2400 | 100 | 500 | 1700 | 2017-2019 | By April 2021 | 130 | 0 | 130 | 0
Eamont Bridge Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Penrith and The Border | Eamont Bridge, Cumbria | Eden | Environment Agency | Development | 1400 | 1100 | 300 | 500 | 400 | 2017-2019 | By April 2019 | 60 | 0 | 60 | 0
Gamblesby, River Eden | North West | North West | Cumbria and Lancashire | Penrith and The Border | Gamblesby, Cumbria | Eden | Cumbria County Council | Development | 75 | 75 | 0 | 0 | 75 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Pooley Bridge Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Penrith and The Border | Pooley Bridge, Cumbria | Eden | Environment Agency | Development | 400 | 300 | 100 | 100 | 200 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
East Lytham FRM Scheme | North West | North West | Cumbria and Lancashire | Fylde | East Lytham | Fylde | Environment Agency | Construction | 3400 | 3000 | 400 | 2000 | 400 | By April 2017 | By April 2019 | 650 | 0 | 650 | 0
Starr Hill Sand Dunes Environmental Works | North West | North West | Cumbria and Lancashire | Blackpool South, Fylde | Starr Hill Sand Dunes | Fylde | Blackpool Council | Construction | 867.5 | 817.5 | 50 | 100.377 | 165.833 | By April 2017 | By April 2019 | 10 | 495 | 10 | 495
Fairhaven and Church Scar Coast Protection Scheme | North West | North West | Cumbria and Lancashire | Fylde | Lytham St Annes, Lancashire | Fylde | Fylde Borough Council | Development | 21411.95 | 20936.95 | 475 | 13000 | 5825 | 2017-2019 | By April 2021 | 1355 | 990 | 1355 | 990
Staining, Fylde Level 3 SWMP's | North West | North West | Cumbria and Lancashire | Fylde Co | Staining, Fylde | Fylde | Lancashire County Council | Development | 85 | 85 | 0 | 10 | 75 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Keckwick Brook, Wharford Farm, Runcorn | North West | North West | Greater Manchester Merseyside and Cheshire | Weaver Vale | Runcorn, Cheshire | Halton | Environment Agency | Construction | 35 | 35 | 0 | 0 | 35 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Bridgewater and Lockgate, Runcorn | North West | North West | Greater Manchester Merseyside and Cheshire | Weaver Vale | Windmill Hill, Runcorn, Cheshire | Halton | Halton Borough Council | Development | 244 | 135 | 109 | 53 | 74 | 2017-2019 | By April 2019 | 120 | 0 | 120 | 0
Runcorn & Widnes Culvert Study | North West | North West | Greater Manchester Merseyside and Cheshire | Halton | Farnworth, Widnes, Cheshire | Halton | Halton Borough Council | Development | 35 | 10 | 25 | 0 | 10 | 2017-2019 | Beyond 2021 | 15 | 0 | 15 | 0
New Mills, Derbyshire Surface Water Mgmt Scheme | East Midlands | North West | Greater Manchester Merseyside and Cheshire | High Peak | New Mills, Derbyshire | High Peak | Derbyshire County Council | Development | 150 | 140 | 10 | 16 | 24 | 2019-2021 | Beyond 2021 | 20 | 0 | 35 | 0
Birch Vale, Derbyshire Suface Water Mgmt Scheme | East Midlands | North West | Greater Manchester Merseyside and Cheshire | High Peak | Birch Vale, Derbyshire | High Peak | Derbyshire County Council | Development | 217 | 180 | 37 | 0 | 8 | 2019-2021 | By April 2021 | 0 | 0 | 25 | 0
Knowsley Village Land Drainage Investigation | North West | North West | Greater Manchester Merseyside and Cheshire | Knowsley | Knowsley Village, Knowsley, Merseyside | Knowsley | Knowsley Borough Council | Development | 112 | 107 | 5 | 85 | 0 | 2017-2019 | Beyond 2021 | 40 | 0 | 40 | 0
Warrington Road, Knowsley | North West | North West | Greater Manchester Merseyside and Cheshire | Knowsley | Knowsley, Merseyside | Knowsley | Knowsley Borough Council | Development | 120 | 115 | 5 | 0 | 115 | 2019-2021 | By April 2021 | 45 | 0 | 45 | 0
Morecambe Wave Reflection Wall Phases 1 - 3 | North West | North West | Cumbria and Lancashire | Morecambe & Luneside | Morecambe, Lancashire | Lancaster | Lancaster City Council | Construction | 9772.674 | 9772.674 | 0 | 2654.699 | 1775.502 | By April 2017 | By April 2019 | 11415 | 0 | 11415 | 0
Cote Beck, Halton Flow Control | North West | North West | Cumbria and Lancashire | Morecambe & Luneside | Halton, Lancaster | Lancaster | Lancaster City Council | Development | 65 | 26 | 39 | 0 | 26 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Glasson Dock Gate Refurbishment | North West | North West | Cumbria and Lancashire | Lancaster and Fleetwood | Lancaster | Lancaster | Environment Agency | Development | 126 | 126 | 0 | 126 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Slyne Level 3 SWMP | North West | North West | Cumbria and Lancashire | Morecambe & Luneside | Slyne, Lancashire | Lancaster | Lancashire County Council | Development | 75 | 75 | 0 | 75 | 0 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Mab Lane Surface Water Culvert, Liverpool | North West | North West | Greater Manchester Merseyside and Cheshire | Liverpool West Derby | Liverpool, Merseyside | Liverpool | Liverpool City Council | Development | 500 | 375 | 125 | 0 | 375 | 2017-2019 | By April 2019 | 270 | 0 | 270 | 0
Wirral Surface Water Mgmt Scheme | North West | North West | Greater Manchester Merseyside and Cheshire | All Wirral Constituencies | Wirral, Merseyside | Liverpool | Wirral Borough Council | Development | 1410 | 980 | 430 | 160 | 320 | 2017-2019 | Beyond 2021 | 0 | 0 | 2720 | 0
Upper Brook Surface Water Mgmt, Liverpool | North West | North West | Greater Manchester Merseyside and Cheshire | Liverpool Wavertree, Liverpool Riverside | Liverpool, Merseyside | Liverpool | Liverpool City Council | Development | 235 | 160 | 75 | 160 | 0 | 2017-2019 | Beyond 2021 | 105 | 0 | 105 | 0
Lower Tue Brook Culvert, Liverpool | North West | North West | Greater Manchester Merseyside and Cheshire | Liverpool Walton | Liverpool, Merseyside | Liverpool | Liverpool City Council | Development | 500 | 375 | 125 | 375 | 0 | 2017-2019 | By April 2019 | 155 | 0 | 155 | 0
River Mersey Wall | North West | North West | Greater Manchester Merseyside and Cheshire | Liverpool, Riverside | Liverpool, Merseyside | Liverpool | Liverpool City Council | Development | 25 | 20 | 5 | 20 | 0 | Beyond 2021 | Beyond 2021 | 10 | 0 | 10 | 0
Hidden Watercourses Appraisal | North West | North West | Greater Manchester Merseyside and Cheshire | Manchester Central | Manchester | Manchester | Manchester City Council | Construction | 911 | 911 | 0 | 125 | 0 | By April 2017 | By April 2019 | 0 | 0 | 400 | 0
Manchester Trash Screen and Culvert Rehabilitation | North West | North West | Greater Manchester Merseyside and Cheshire | Manchester Central | Manchester | Manchester | Manchester City Council | Development | 300 | 300 | 0 | 100 | 200 | 2017-2019 | By April 2021 | 150 | 0 | 150 | 0
Cringle Bk, Ladybarn | North West | North West | Greater Manchester Merseyside and Cheshire | Manchester, Gorton | Ladybarn, Withington, Greater Manchester | Manchester | Environment Agency | Development | 2025 | 2025 | 0 | 0 | 525 | Beyond 2021 | Beyond 2021 | 0 | 0 | 265 | 0
The Rookery, Kidsgrove | West Midlands | North West | Greater Manchester Merseyside and Cheshire | Newcastle-under-Lyme | Kidsgrove, Cheshire | Newcastle-under-Lyme | Staffordshire County Council | Development | 220 | 145 | 75 | 0 | 125 | 2017-2019 | By April 2019 | 45 | 0 | 45 | 0
Broomes Park, Royton, Oldham | North West | North West | Greater Manchester Merseyside and Cheshire | Oldham West and Royton | Chadderton, Oldham | Oldham | Oldham Borough Council | Development | 362.5 | 265.5 | 97 | 0 | 250.5 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Patridge Way, Chadderton, Oldham | North West | North West | Greater Manchester Merseyside and Cheshire | Oldham West and Royton | Royton, Oldham | Oldham | Oldham Borough Council | Development | 335 | 185 | 150 | 0 | 185 | 2019-2021 | Beyond 2021 | 20 | 0 | 20 | 0
Merton Avenue, Medlock Vale, Oldham | North West | North West | Greater Manchester Merseyside and Cheshire | Oldham West and Royton | Medlock Vale, Oldham | Oldham | Oldham Borough Council | Development | 125 | 105 | 20 | 0 | 105 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Greencroft Meadow, Royton, Oldham | North West | North West | Greater Manchester Merseyside and Cheshire | Oldham West and Royton | Royton, Oldham, Luzley Brook Culvert Improvement Flood Defence | Oldham | Oldham Borough Council | Development | 160 | 100 | 60 | 0 | 10 | 2017-2019 | By April 2021 | 0 | 0 | 5 | 0
Churchfields, Dobcross, Oldham | North West | North West | Greater Manchester Merseyside and Cheshire | Oldham East and Saddleworth | Dobcross, Oldham | Oldham | Oldham Borough Council | Development | 770 | 370 | 400 | 0 | 15 | 2019-2021 | By April 2021 | 0 | 0 | 70 | 0
Mossley Road, Greenfield Oldham | North West | North West | Greater Manchester Merseyside and Cheshire | Oldham East and Saddleworth | Greenfield, Oldham | Oldham | Oldham Borough Council | Development | 890 | 125 | 765 | 0 | 110 | 2019-2021 | Beyond 2021 | 30 | 0 | 55 | 0
Pendle Ordinary Watercourse Study | North West | North West | Cumbria and Lancashire | Pendle | Pendle, Lancashire | Pendle | Lancashire County Council | Development | 55 | 55 | 0 | 0 | 55 | 2019-2021 | By April 2021 | 35 | 0 | 35 | 0
Lancashire Armco culverts | North West | North West | Cumbria and Lancashire | Preston | Various locations across Lancashire | Preston | Environment Agency | Development | 100 | 100 | 0 | 100 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Whalley and Billington Surface Water Improvement Scheme | North West | North West | Cumbria and Lancashire | Ribble Valley Co | Whalley, Lancashire | Ribble Valley | Lancashire County Council | Development | 2528.558 | 2528.558 | 0 | 0 | 528.558 | Beyond 2021 | Beyond 2021 | 0 | 0 | 350 | 0
Shaw, Cringle, Ley and Willow Brook | North West | North West | Greater Manchester Merseyside and Cheshire | Manchester, Withington | Withington, Greater Manchester | Richmondshire | Manchester City Council | Development | 600 | 600 | 0 | 100 | 500 | 2017-2019 | By April 2021 | 115 | 0 | 115 | 0
Rusholme and Moss Side Surface Water Management Scheme | North West | North West | Greater Manchester Merseyside and Cheshire | Manchester Central | Rusholme and Moss Side - Dog Kennel Brook and Rush Brook | Richmondshire | Manchester City Council | Development | 600 | 600 | 0 | 0 | 600 | 2019-2021 | By April 2021 | 110 | 0 | 110 | 0
River Roch, Rochdale & Littleborough | North West | North West | Greater Manchester Merseyside and Cheshire | Rochdale | Rochdale, River Roch, Greater Manchester | Rochdale | Environment Agency | Pipeline | 27064.5 | 17864.5 | 9200 | 355 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 1065 | 0
Boundary Edge Brook, Rossendale | North West | North West | Cumbria and Lancashire | Rossendale and Darwen | Edenfield, Rossendale | Rossendale | Lancashire County Council | Development | 60 | 60 | 0 | 0 | 60 | 2019-2021 | By April 2021 | 4 | 0 | 4 | 0
Rossendale District Level 2's - Waterfoot, Rawtenstall, Bacup, Shawforth | North West | North West | Cumbria and Lancashire | Rossendale and Darwen | Rossendale, Lancashire | Rossendale | Lancashire County Council | Development | 90 | 90 | 0 | 10 | 80 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Limy Water Culvert, Rawtenstall | North West | North West | Greater Manchester Merseyside and Cheshire | Rossendale and Darwen | Rawtenstall, Rossendale | Rossendale | Environment Agency | Development | 500 | 500 | 0 | 250 | 250 | Beyond 2021 | Beyond 2021 | 75 | 0 | 75 | 0
Greave Clough Brook Culvert, Bacup | North West | North West | Greater Manchester Merseyside and Cheshire | Rossendale and Darwen | Bacup, Rossendale | Rossendale | Environment Agency | Development | 250 | 250 | 0 | 250 | 0 | Beyond 2021 | Beyond 2021 | 80 | 0 | 80 | 0
River Spodden, North Street Culvert, Whitworth | North West | North West | Greater Manchester Merseyside and Cheshire | Rossendale and Darwen | Whitworth, Rossendale | Rossendale | Environment Agency | Development | 250 | 250 | 0 | 250 | 0 | Beyond 2021 | Beyond 2021 | 70 | 0 | 70 | 0
Gore Avenue Groundwater, Salford | North West | North West | Greater Manchester Merseyside and Cheshire | Salford and Eccles | Weaste, Salford | Salford | Salford City Council | Construction | 130 | 130 | 0 | 75 | 0 | By April 2017 | By April 2019 | 40 | 0 | 40 | 0
Groundwater Study - Castlewood Road, Kersal | North West | North West | Greater Manchester Merseyside and Cheshire | Salford and Eccles | Castlewood Road, Kersal | Salford | Salford City Council | Development | 100 | 100 | 0 | 25 | 75 | 2017-2019 | By April 2019 | 45 | 0 | 45 | 0
Four Acres, Maghull Asset Management Plan | North West | North West | Greater Manchester Merseyside and Cheshire | Sefton Central | Maghull, Merseyside | Sefton | Sefton Borough Council | Construction | 205 | 205 | 0 | 0 | 70 | By April 2017 | By April 2019 | 40 | 0 | 40 | 0
The Nile, Southport | North West | North West | Greater Manchester Merseyside and Cheshire | Southport | Southport | Sefton | Sefton Borough Council | Development | 90 | 90 | 0 | 0 | 30 | 2017-2019 | Beyond 2021 | 0 | 0 | 0 | 0
The Pool, Southport | North West | North West | Greater Manchester Merseyside and Cheshire | Southport | Southport | Sefton | Sefton Borough Council | Development | 90 | 90 | 0 | 0 | 30 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Merseyside Natural Flood Management Study | North West | North West | Greater Manchester Merseyside and Cheshire | Bootle | Merseyside | Sefton | Sefton Borough Council | Development | 170 | 170 | 0 | 0 | 40 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
River Alt Training Bank | North West | North West | Greater Manchester Merseyside and Cheshire | Sefton Central | Hightown-Blundelsands - River Alt | Sefton | Sefton Borough Council | Development | 430 | 425 | 5 | 10 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 25
Seaforth and Litherland Strategic Flood Risk Management Programme | North West | North West | Greater Manchester Merseyside and Cheshire | Bootle | Seaforth, Merseyside | Shropshire | Sefton Borough Council | Development | 90 | 90 | 0 | 15 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Ulverston FRM Scheme | North West | North West | Cumbria and Lancashire | Barrow and Furness | Ulverston, Cumbria. | South Lakeland | Environment Agency | Construction | 10034.439 | 9954.439 | 80 | 4625.428 | 0 | By April 2017 | By April 2019 | 505 | 0 | 505 | 0
Carrus Green, Kendal | North West | North West | Cumbria and Lancashire | Westmorland and Lonsdale | Carrus Green , Kendal | South Lakeland | Cumbria County Council | Development | 65 | 65 | 0 | 0 | 20 | 2019-2021 | Beyond 2021 | 0 | 0 | 10 | 0
Grange-Over-Sands, Windermere Road | North West | North West | Cumbria and Lancashire | Westmorland and Lonsdale | Grange-over-Sands | South Lakeland | Environment Agency | Development | 1355 | 190 | 1165 | 0 | 190 | 2017-2019 | By April 2021 | 40 | 0 | 40 | 0
Kendal, River Kent | North West | North West | Cumbria and Lancashire | Westmorland and Lonsdale | Kendal, Cumbria. | South Lakeland | Environment Agency | Development | 24000 | 20600 | 3400 | 300 | 20000 | 2017-2019 | By April 2021 | 1555 | 0 | 1555 | 0
Low Beckside, Kirkby in Furness | North West | North West | Cumbria and Lancashire | Barrow and Furness | Low Beckside, Kirkby in Furness | South Lakeland | Cumbria County Council | Development | 154 | 77 | 77 | 0 | 77 | 2017-2019 | By April 2021 | 20 | 0 | 20 | 0
Ulverston Urban Drainage | North West | North West | Cumbria and Lancashire | Barrow and Furness | Ulverston, Cumbria | South Lakeland | Cumbria County Council | Development | 1115 | 615 | 500 | 100 | 515 | 2017-2019 | By April 2019 | 205 | 0 | 205 | 0
Ulverston, Dragley Beck Rydal Road | North West | North West | Cumbria and Lancashire | Barrow and Furness | Ulverston,Cumbria | South Lakeland | Environment Agency | Development | 500 | 500 | 0 | 0 | 500 | 2019-2021 | By April 2021 | 80 | 0 | 80 | 0
Grasmere, River Rothay | North West | North West | Cumbria and Lancashire | Westmorland and Lonsdale | Grasmere, Cumbria | South Lakeland | Environment Agency | Pipeline | 200 | 150 | 50 | 0 | 50 | 2019-2021 | Beyond 2021 | 0 | 0 | 50 | 0
Preston / South Ribble | North West | North West | Cumbria and Lancashire | Preston / Ribble Valley / South Ribble | Preston, Lancashire | South Ribble | Environment Agency | Development | 19830 | 13547 | 6283 | 0 | 3800 | 2019-2021 | Beyond 2021 | 0 | 0 | 2900 | 0
King William IV Fishing Lake Outfall and Overflow Replacement | North West | North West | Greater Manchester Merseyside and Cheshire | Blackley and Broughton | Higher Blackley King William IV Fishing Lake discharging to the River Irk | South Staffordshire | Manchester City Council | Development | 110 | 100 | 10 | 0 | 100 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Cheadle Flood Risk Area | North West | North West | Greater Manchester Merseyside and Cheshire | Cheadle | Chorlton Brook, Cheadle | Stockport | Stockport Borough Council | Construction | 690 | 690 | 0 | 250 | 300 | By April 2017 | By April 2021 | 320 | 0 | 320 | 0
River Mersey Warrington FRM Scheme | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington South | Warrington, Cheshire | Warrington | Environment Agency | Construction | 34496 | 29237 | 5259 | 2052 | 70 | By April 2017 | By April 2019 | 655 | 0 | 2155 | 0
Orford, Warrington | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington North | Warrington, Cheshire | Warrington | Warrington Borough Council | Development | 425 | 350 | 75 | 0 | 350 | 2019-2021 | By April 2021 | 75 | 0 | 75 | 0
Heath Lane, Croft, Warrington | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington North | Warrington, Cheshire | Warrington | Warrington Borough Council | Development | 0.09 | 0.09 | 0 | 0 | 0.09 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Sankey Bridges, Warrington | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington South | Sankey Bridges & Dallam areas of Warrington | Warrington | Environment Agency | Development | 3645 | 3286 | 359 | 0 | 3260 | 2017-2019 | Beyond 2021 | 475 | 0 | 475 | 0
Thelwall, Warrington | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington South | Thelwall, Warrington | Warrington | Environment Agency | Development | 50 | 50 | 0 | 0 | 50 | 2017-2019 | By April 2019 | 190 | 0 | 190 | 0
Eastford Road, Warrington | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington South | Lower Walton, Warrington | Warrington | Environment Agency | Development | 75 | 75 | 0 | 0 | 75 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Warrington Road, Walton | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington South | Warrington, Cheshire | Warrington | Warrington Borough Council | Development | 15 | 10 | 5 | 0 | 10 | 2019-2021 | By April 2021 | 2 | 0 | 2 | 0
Jennets Lane PS, Leigh | North West | North West | Greater Manchester Merseyside and Cheshire | Warrington North | Leigh, Greater Manchester | Warrington | Environment Agency | Development | 197 | 197 | 0 | 197 | 0 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Hesketh Outmarsh East Managed Realignment | North West | North West | Cumbria and Lancashire | South Ribble | Hesketh Bank, Nr Preston | West Lancashire | Environment Agency | Construction | 3383.638 | 3383.638 | 0 | 618.92 | 11 | By April 2017 | By April 2019 | 140 | 0 | 140 | 0
Abbey Brook (The Pines Estate), Ormskirk | North West | North West | Cumbria and Lancashire | West Lancashire | Abbey Brook, Ormskirk | West Lancashire | West Lancashire District Council | Development | 640 | 640 | 0 | 0 | 567 | 2019-2021 | By April 2021 | 25 | 0 | 25 | 0
Downholland Brook berm removal | North West | North West | Cumbria and Lancashire | Sefton Central | Formby | West Lancashire | Environment Agency | Development | 746 | 746 | 0 | 0 | 373 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Hurlston Brook, Ormskirk West Study | North West | North West | Cumbria and Lancashire | West Lancashire | Ormskirk, Lancashire | West Lancashire | Lancashire County Council | Development | 2111 | 2051 | 60 | 0 | 112 | Beyond 2021 | Beyond 2021 | 0 | 0 | 215 | 0
Clarington Brook Culvert, Wigan | North West | North West | Cumbria and Lancashire | Wigan | Wigan, Greater Manchester | Wigan | Environment Agency | Development | 500 | 500 | 0 | 0 | 500 | 2017-2019 | Beyond 2021 | 40 | 0 | 40 | 0
Bag Lane Culvert, Atherton | North West | North West | Greater Manchester Merseyside and Cheshire | Bolton West | Atherton, Greater Manchester | Wigan | Environment Agency | Development | 405 | 405 | 0 | 405 | 0 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Common Lane Bk, Leigh | North West | North West | Greater Manchester Merseyside and Cheshire | Leigh | Common Lane Bk, Leigh Greater Manchester | Wigan | Environment Agency | Development | 300 | 213 | 87 | 0 | 213 | 2019-2021 | By April 2021 | 45 | 0 | 45 | 0
West Kirby Flood Alleviation Scheme | North West | North West | Greater Manchester Merseyside and Cheshire | Wirral West | West Kirby, Wirral, Merseyside | Wirral | Wirral Borough Council | Construction | 3100 | 1750 | 1350 | 1250 | 0 | By April 2017 | By April 2019 | 285 | 0 | 285 | 0
Rossall Coastal Defence Improvement Scheme | North West | North West | Cumbria and Lancashire | Lancaster & Fleetwood CC | Fylde coast Lancashire, Rossall Hospital to Fleetwood Golf Course | Wyre | Wyre Borough Council | Construction | 94202 | 94077 | 125 | 11869 | 0 | By April 2017 | By April 2019 | 7495 | 0 | 7495 | 0
Churchtown Defence Improvements | North West | North West | Cumbria and Lancashire | Wyre and Preston North | Churchtown near St Michaels on Wyre, Lancs | Wyre | Environment Agency | Development | 100 | 100 | 0 | 100 | 0 | 2017-2019 | By April 2019 | 45 | 0 | 45 | 0
Hillylaid Pool, Thornton | North West | North West | Cumbria and Lancashire | Wyre and Preston North | Thornton, Wyre | Wyre | Environment Agency | Development | 1852 | 1852 | 0 | 780 | 750 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Upper & Middle Wyre FRM Asset Mgmt Review | North West | North West | Cumbria and Lancashire | Wyre and Preston North | St Michaels on Wyre, Lancashire | Wyre | Environment Agency | Development | 941 | 891 | 50 | 0 | 870 | 2017-2019 | By April 2021 | 310 | 0 | 310 | 0
Wyre Dune and Beach Management Scheme | North West | North West | Cumbria and Lancashire | Blackpool North , Lancaster & Fleetwood CC | Fylde Coast Lancashire, Cleveleys to Fleetwood Ferry Dock | Wyre | Wyre Borough Council | Development | 40448 | 40448 | 0 | 375 | 9298 | 2017-2019 | By April 2021 | 1915 | 0 | 1915 | 0
Crosby Marine Lake to Formby Point Strategy Delivery Programme | North West | North West | Greater Manchester Merseyside and Cheshire | Sefton Central, Bootle | Waterloo, Crosby, Blundellsands,Hightown, Sefton Coast SSSI, SPA, RAMSAR,SAC | Wyre | Sefton Borough Council | Development | 2724 | 1724 | 1000 | 30 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 200 | 0
Sefton Strategic Surface Water Management Plan Delivery Programme | North West | North West | Greater Manchester Merseyside and Cheshire | Southport, Sefton Central, Bootle | Sefton, Southport, Ainsdale, Formby, Crosby, Hightown, Bootle | Wyre | Sefton Borough Council | Development | 2040 | 2040 | 0 | 0 | 540 | 2019-2021 | Beyond 2021 | 75 | 0 | 340 | 0
Tindale Beck Flood Alleviation Scheme update | North East | Northumbria | Northumberland Durham and Tees | Bishop Auckland | West Auckland, Tindale Beck | County Durham | Environment Agency | Construction | 275 | 230 | 45 | 75 | 0 | By April 2017 | By April 2019 | 60 | 0 | 60 | 0
Castlefields, Bournmoor, Surface Water Flood Alleviation Works | North East | Northumbria | Northumberland Durham and Tees | North Durham | Side of Castlefields, Bournmoor | County Durham | Durham County Council | Construction | 36.3 | 10.3 | 26 | 0 | 10.3 | By April 2017 | By April 2019 | 2 | 0 | 2 | 0
Lanchester Surface Water Scheme | North East | Northumbria | Northumberland Durham and Tees | North West Durham | Lanchester | County Durham | Durham County Council | Construction | 1265.9 | 263.327 | 1002.573 | 170.9 | 0 | By April 2017 | By April 2019 | 45 | 0 | 45 | 0
Staindrop Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Bishop Auckland | Staindrop, Langley Beck/Sudburn Beck/Moor Beck | County Durham | Environment Agency | Development | 485 | 172 | 313 | 172 | 0 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Sherburn Park Estate, Rowlands Gill Surface water management scheme | North East | Northumbria | Northumberland Durham and Tees | Blaydon | Rowlands Gill, Gateshead | County Durham | Gateshead Borough Council | Development | 106.4 | 81.4 | 25 | 5.2 | 76.2 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Dipton Surface Water Flood Management Works | North East | Northumbria | Northumberland Durham and Tees | North West Durham | Dipton | County Durham | Durham County Council | Development | 42.5 | 37.5 | 5 | 0 | 37.5 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Shotley Bridge Surface Water Flood Management Works | North East | Northumbria | Northumberland Durham and Tees | North West Durham | Shotley Bridge | County Durham | Durham County Council | Development | 90.9 | 45.9 | 45 | 0 | 45.9 | 2017-2019 | By April 2021 | 5 | 0 | 5 | 0
Spennymoor Integrated Drainage Study | North East | Northumbria | Northumberland Durham and Tees | Bishop Auckland | Northumbrian Waters Drainage Area of Spennymoor, County Durham | County Durham | Durham County Council | Development | 126.296 | 126.296 | 0 | 0 | 126.296 | Beyond 2021 | Beyond 2021 | 85 | 0 | 85 | 0
Crook Integrated Drainage Study | North East | Northumbria | Northumberland Durham and Tees | North West Durham | Northumbrian Water's Drainage Area of Crook, County Durham | County Durham | Durham County Council | Development | 126.296 | 126.296 | 0 | 0 | 126.296 | Beyond 2021 | Beyond 2021 | 40 | 0 | 40 | 0
Cherry Banks, Chester le Street, Surface Water | North East | Northumbria | Northumberland Durham and Tees | North Durham | 5 Cherry Banks, Chester le Street | County Durham | Durham County Council | Development | 5.4 | 4.8 | 0.6 | 0 | 4.8 | 2019-2021 | By April 2021 | 1 | 0 | 1 | 0
Dunelm Walk, Leadgate, Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | North West Durham | 83 - 91 Dunelm Walk, Leadgate | County Durham | Durham County Council | Development | 65 | 26.5 | 38.5 | 0 | 26.5 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Hardwick Road, Sedgefield, Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Sedgefield | 14 - 22 hardwick Road, Sedgefield | County Durham | Durham County Council | Development | 160.7 | 55.7 | 105 | 0 | 55.7 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Kingfisher Close, Esh Winning, Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | North West Durham | Esh Winning - Hedleyhope Burn | County Durham | Durham County Council | Development | 155.2 | 67.2 | 88 | 0 | 67.2 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Darlington Town Centre Fringe Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Darlington | Darlington Town Centre Fringe | Darlington | Environment Agency | Development | 8408.8 | 1670 | 6738.8 | 0 | 124.5 | 2019-2021 | Beyond 2021 | 0 | 0 | 175 | 0
Hurworth Asset Recovery (formerly Hurworth Place) | North East | Northumbria | Northumberland Durham and Tees | Darlington | Hurworth Place, River Tees | Darlington | Environment Agency | Development | 305.85 | 75.85 | 230 | 0 | 75.85 | 2019-2021 | By April 2021 | 15 | 0 | 15 | 0
Oxney Flatts Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Darlington | Oxney Flatts, River Tees | Darlington | Environment Agency | Development | 170 | 170 | 0 | 0 | 170 | 2019-2021 | By April 2021 | 70 | 0 | 70 | 0
Cockerton Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Darlington | Darlington, West Beck and Cocker Beck | Darlington | Environment Agency | Pipeline | 1487.506 | 822.506 | 665 | 0 | 100 | Beyond 2021 | Beyond 2021 | 0 | 0 | 120 | 0
Heworth | North East | Northumbria | Northumberland Durham and Tees | Gateshead | Heworth, East Gateshead | Gateshead | Gateshead Borough Council | Construction | 216.3 | 161.3 | 55 | 80.3 | 70.7 | By April 2017 | By April 2021 | 20 | 0 | 20 | 0
Team Valley Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Gateshead & Blaydon | Team Valley, Gateshead | Gateshead | Environment Agency | Development | 1674.35 | 631.2 | 1043.15 | 283.5 | 70.2 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Blackhall Mill Flood Defence Renewal | North East | Northumbria | Northumberland Durham and Tees | Blaydon | Blackhall Mill, River Derwent, Gateshead, Tyne & Wear | Gateshead | Environment Agency | Development | 546.3 | 546.3 | 0 | 0 | 546.3 | 2019-2021 | By April 2021 | 75 | 0 | 75 | 0
Field Lane / Laburnum Avenue Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Gateshead | Field Lane, Heworth | Gateshead | Gateshead Borough Council | Development | 166 | 145 | 21 | 0 | 145 | 2017-2019 | By April 2021 | 25 | 0 | 25 | 0
Green Lane Gardens Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Gateshead | Green Lane Gardens, East Gateshead | Gateshead | Gateshead Borough Council | Development | 497.1 | 369.6 | 127.5 | 200 | 116 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
St Omer's Haugh Flood Alleviation Study, Gateshead | North East | Northumbria | Northumberland Durham and Tees | Gateshead | St Omer's Haugh, Gateshead | Gateshead | Environment Agency | Development | 146.774 | 24.274 | 122.5 | 0 | 15.974 | 2019-2021 | By April 2021 | 3 | 0 | 3 | 0
Great Ayton Flood Alleviation Scheme | Yorkshire & the Humber | Northumbria | Northumberland Durham and Tees | Richmond (Yorks) | Great Ayton | Hambleton | Environment Agency | Development | 1032.5 | 232.5 | 800 | 60 | 167.5 | 2017-2019 | By April 2019 | 95 | 0 | 95 | 0
Stokesley Flood Alleviation Scheme | Yorkshire & the Humber | Northumbria | Northumberland Durham and Tees | Richmond (Yorks) | Stokesley, River leven | Hambleton | Environment Agency | Pipeline | 988 | 648 | 340 | 0 | 531 | 2017-2019 | By April 2021 | 260 | 0 | 260 | 0
Hutton Rudby Flood Alleviation Study | Yorkshire & the Humber | Northumbria | Northumberland Durham and Tees | Richmond (Yorks) | Hutton Rudby, River Leven | Hambleton | Environment Agency | Pipeline | 60.753 | 32.753 | 28 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Greatham North Tidal Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Hartlepool | Hartlepool | Hartlepool | Environment Agency | Construction | 5779.918 | 5779.918 | 0 | 20 | 20 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Headland Walls and Blocksands, Hartlepool, Coastal Protection Scheme | North East | Northumbria | Northumberland Durham and Tees | Hartlepool | Hartlepool Headland | Hartlepool | Hartlepool Borough Council | Construction | 10387.6558 | 7188.4 | 3199.2558 | 0 | 633.4 | By April 2017 | By April 2021 | 0 | 195 | 0 | 195
Jesmond Gardens Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Hartlepool | Hartlepool | Hartlepool | Hartlepool Borough Council | Construction | 560 | 560 | 0 | 30 | 510 | By April 2017 | By April 2019 | 80 | 0 | 80 | 0
Riverston Close Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Hartlepool | Hartlepool | Hartlepool | Hartlepool Borough Council | Construction | 196 | 196 | 0 | 100 | 76 | By April 2017 | By April 2019 | 25 | 0 | 25 | 0 | 0
Tynebrook Avenue Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Hartlepool | Hartlepool | Hartlepool | Hartlepool Borough Council | Construction | 233 | 233 | 0 | 110 | 103 | By April 2017 | By April 2019 | 25 | 0 | 25 | 0
Hartlepool Marina Study and Construction (North Pier) | North East | Northumbria | Northumberland Durham and Tees | Hartlepool | Hartlepool Marina | Hartlepool | Hartlepool Borough Council | Development | 3698 | 3618 | 80 | 0 | 1194 | 2019-2021 | Beyond 2021 | 0 | 0 | 0 | 360
Saltersgill Fields Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough | Middlesbrough | Middlesbrough | Middlesbrough Borough Council | Construction | 207.8 | 207.8 | 0 | 187.8 | 0 | By April 2017 | By April 2019 | 70 | 0 | 70 | 0
Marton West Beck, Middlesbrough, Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough | Middlesbrough, Marton West Beck, d/s of Albert Park | Middlesbrough | Environment Agency | Pipeline | 5005 | 3405 | 1600 | 50 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 555 | 0
Scrogg Road Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Newcastle upon Tyne East | Newcastle - Byker/Walkergate - Scrogg Rd and surrounding area, inc Moorland Crescent, Ennerdale Rd, Ashbourne Avenue | Newcastle upon Tyne | Newcastle Upon Tyne City Council | Construction | 551.05 | 277.8 | 273.25 | 141.3 | 0 | By April 2017 | By April 2019 | 90 | 0 | 90 | 0
Coast Road Drainage Scheme | North East | Northumbria | Northumberland Durham and Tees | Newcastle upon Tyne East | A1058 Junction with Chillingham Road, Newcastle | Newcastle upon Tyne | Newcastle Upon Tyne City Council | Development | 195.5 | 56.5 | 139 | 35.1 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Newcastle Local Flood Alleviation Schemes - Citywide | North East | Northumbria | Northumberland Durham and Tees | Newcastle upon Tyne North | Newcastle Upon Tyne | Newcastle upon Tyne | Newcastle Upon Tyne City Council | Development | 905.53 | 625.53 | 280 | 20 | 424 | By April 2017 | By April 2021 | 95 | 0 | 95 | 0
Newcastle Local Flood Alleviation Schemes - Kingston Park | North East | Northumbria | Northumberland Durham and Tees | Newcastle upon Tyne North | Newcastle Upon Tyne | Newcastle upon Tyne | Newcastle Upon Tyne City Council | Development | 199.6 | 84.6 | 115 | 84.6 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Tyneside Sustainable Sewerage Study - Broad Chare/Central Motorway Feasibility | North East | Northumbria | Northumberland Durham and Tees | Newcastle upon Tyne East | Central Motorway, Newcastle | Newcastle upon Tyne | Northumbrian Water | Pipeline | 2994.26 | 573.46 | 2420.8 | 0 | 50 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Killingworth, Longbenton, and Forest Hall Surface Water Separation and SuDS Phase 1, Appraisal, Design and Construction. | North East | Northumbria | Northumberland Durham and Tees | North Tyneside | Killingworth, Longbenton and Forest Hall, North Tyneside | North Tyneside | North Tyneside Borough Council | Construction | 5142.4 | 2257.7 | 2884.7 | 680 | 757.7 | By April 2017 | By April 2021 | 285 | 0 | 285 | 0
Southern Promenade Sea Wall Repair - Appraisal, Design and Construction, Whitely Bay | North East | Northumbria | Northumberland Durham and Tees | Tynemouth | Whitely Bay, Tyne & Wear | North Tyneside | North Tyneside Borough Council | Construction | 531.2 | 381.2 | 150 | 281.2 | 0 | By April 2017 | By April 2019 | 0 | 80 | 0 | 80
Central Promenade Appraisal, Design And Construction, North Tyneside | North East | Northumbria | Northumberland Durham and Tees | Tynemouth | Whitely Bay, Tyne & Wear | North Tyneside | North Tyneside Borough Council | Construction | 3386.2 | 1192.2 | 2194 | 489.2 | 0 | By April 2017 | By April 2019 | 0 | 60 | 0 | 60
Shiremoor, Appraisal, Design and Construction | North East | Northumbria | Northumberland Durham and Tees | North Tyneside | Shiremoor | North Tyneside | North Tyneside Borough Council | Development | 1807 | 656 | 1151 | 103 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Long Sands and Bear's Back Sea Wall Appraisal, Design and Construction, Tynemouth | North East | Northumbria | Northumberland Durham and Tees | Tynemouth | Tynemouth, Tyne & Wear | North Tyneside | North Tyneside Borough Council | Development | 452.3 | 105.3 | 347 | 0 | 32.1 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Sea Banks Sea Wall - Appraisal Design and Construction, Tynemouth | North East | Northumbria | Northumberland Durham and Tees | Tynemouth | Tynemouth, Tyne & Wear | North Tyneside | North Tyneside Borough Council | Development | 450.7 | 105.7 | 345 | 0 | 32.1 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Briar Vale Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | North Tyneside | Briar Vale | North Tyneside | North Tyneside Borough Council | Development | 692.3534 | 594.695 | 97.6584 | 223 | 0 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Fairfield Green Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | North Tyneside | Fairfield Green, West Monkseaton | North Tyneside | North Tyneside Borough Council | Development | 1798.222 | 835.222 | 963 | 207 | 0 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Haltwhistle Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Hexham | Haltwhistle, Northumberland | Northumberland | Northumberland County Council | Construction | 1405.023 | 1104.523 | 300.5 | 262.927 | 0 | By April 2017 | By April 2019 | 45 | 0 | 45 | 0
Morpeth Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Wansbeck | Morpeth, Northumberland | Northumberland | Northumberland County Council | Construction | 1606.601 | 1056.601 | 550 | 232.601 | 0 | By April 2017 | By April 2019 | 165 | 0 | 165 | 0
Morpeth Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Wansbeck | Morpeth | Northumberland | Environment Agency | Construction | 28954.6245 | 16427.642 | 12526.9825 | 25 | 5 | By April 2017 | By April 2019 | 815 | 0 | 815 | 0
Little Shore Improvement Works | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Amble | Northumberland | Northumberland County Council | Development | 117.85 | 97.85 | 20 | 15 | 82.85 | 2017-2019 | By April 2019 | 0 | 55 | 0 | 55
Alnwick East Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Alnwick, Northumberland | Northumberland | Northumberland County Council | Development | 211.1 | 106.1 | 105 | 0 | 106.1 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Shilbottle Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Shilbottle, Northumberland | Northumberland | Northumberland County Council | Development | 285 | 115 | 170 | 0 | 115 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Acomb (Red Burn) Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Hexham | Acomb, Red Burn, | Northumberland | Environment Agency | Development | 629.959 | 297.3 | 332.659 | 133.65 | 133.65 | 2017-2019 | By April 2021 | 45 | 0 | 45 | 0
Rothbury Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Rothbury, Northumberland | Northumberland | Northumberland County Council | Development | 225 | 200 | 25 | 0 | 200 | 2019-2021 | By April 2021 | 35 | 0 | 35 | 0
Wooler Water Defence Replacement and Reallignment | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Wooler, Northumberland. River : Wooler Water | Northumberland | Environment Agency | Development | 1261 | 1141 | 120 | 0 | 25 | Beyond 2021 | Beyond 2021 | 0 | 0 | 15 | 0
Cramlington Surface Water Scheme | North East | Northumbria | Northumberland Durham and Tees | Blyth Valley | Cramlington | Northumberland | Northumberland County Council | Development | 1820 | 1725 | 95 | 0 | 75 | Beyond 2021 | Beyond 2021 | 0 | 0 | 200 | 0
Warkworth Harbour North Pier Geophysical and Ground Investigations | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Warkworth Harbour, Amble, Northumberland | Northumberland | Northumberland County Council | Development | 645.4 | 645.4 | 0 | 0 | 645.4 | Beyond 2021 | Beyond 2021 | 0 | 80 | 0 | 80
Craster Coast Protection Scheme | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Craster Harbour | Northumberland | Northumberland County Council | Development | 2560 | 700 | 1860 | 0 | 700 | 2017-2019 | By April 2019 | 0 | 50 | 0 | 50
Lowick Flood Mitigation Works | North East | Northumbria | Northumberland Durham and Tees | Berwick-upon-Tweed | Lowick | Northumberland | Northumberland County Council | Development | 15.5 | 12.5 | 3 | 0 | 12.5 | 2019-2021 | By April 2021 | 2 | 0 | 2 | 0
Newbiggin Point Coast Protection Scheme | North East | Northumbria | Northumberland Durham and Tees | Wansbeck | Newbiggin Point, Northumberland | Northumberland | Northumberland County Council | Development | 177.8 | 92.3 | 85.5 | 0 | 92.3 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Bellingham Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Hexham | Bellingham, Hareshaw Burn & River Tyne | Northumberland | Environment Agency | Pipeline | 450 | 38 | 412 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Hardhaugh, Warden Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Hexham | Bridge End, Hexham | Northumberland | Environment Agency | Pipeline | 400 | 38 | 362 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 20 | 0
Ponteland Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | TBC | Ponteland | Northumberland | Environment Agency | Pipeline | 3500 | 2380 | 1120 | 100 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 460 | 0
Prudhoe Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Hexham | Prudhoe | Northumberland | Environment Agency | Pipeline | 565.632 | 238.704 | 326.928 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Stocksfield Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Hexham | Stocksfield, Stocksfield Burn | Northumberland | Environment Agency | Pipeline | 49.362 | 27.362 | 22 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Well Bank Corbridge Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Hexham | Corbridge, River Tyne | Northumberland | Environment Agency | Pipeline | 21.407 | 10.907 | 10.5 | 0 | 10.907 | Beyond 2021 | Beyond 2021 | 0 | 0 | 4 | 0
North Skelton Inland Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough South and East Cleveland | North Skelton | Redcar and Cleveland | Redcar and Cleveland Borough Council | Development | 165 | 150 | 15 | 55 | 55 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Cross Beck Inland Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough South and East Cleveland | Eston | Redcar and Cleveland | Redcar and Cleveland Borough Council | Development | 1519 | 614 | 905 | 0 | 257 | 2019-2021 | Beyond 2021 | 0 | 0 | 30 | 0
Hutton Lane Inland Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough South and East Cleveland | Guisborough | Redcar and Cleveland | Redcar and Cleveland Borough Council | Development | 952.288 | 388.288 | 564 | 188.288 | 200 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Ormesby High Street Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough | Ormesby | Redcar and Cleveland | Middlesbrough Borough Council | Development | 125.7 | 20.7 | 105 | 0 | 20.7 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Whale Hill Ironstone Culvert Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough South and East Cleveland | Eston | Redcar and Cleveland | Redcar and Cleveland Borough Council | Development | 2780 | 2180 | 600 | 0 | 285 | Beyond 2021 | Beyond 2021 | 0 | 0 | 75 | 0
Guisborough Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough South and East Cleveland | Guisborough, Skelton Beck/Chapel Beck | Redcar and Cleveland | Environment Agency | Pipeline | 2299.304 | 1249.304 | 1050 | 170 | 869.304 | 2017-2019 | By April 2019 | 100 | 0 | 100 | 0
Charltons Inland Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Middlesbrough South and East Cleveland | Charltons | Redcar and Cleveland | Redcar and Cleveland Borough Council | Pipeline | 431.59 | 172.59 | 259 | 0 | 156.59 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Upper Tees Flood Risk Management Plan | Yorkshire & the Humber | Northumbria | Northumberland Durham and Tees | Richmond (Yorks) | Upper Tees | Richmondshire | North Yorkshire County Council | Development | 932.16 | 812.16 | 120 | 0 | 568.512 | 2017-2019 | By April 2019 | 95 | 0 | 95 | 0
Cleasby Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Richmond (Yorks) | Cleasby, River Tees | Richmondshire | Environment Agency | Pipeline | 460 | 43 | 417 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 40 | 0
Monkton Village Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Jarrow | Hebburn, South Tyneside | South Tyneside | South Tyneside Borough Council | Construction | 3450 | 2100 | 1350 | 440.545 | 1059.455 | By April 2017 | By April 2019 | 135 | 0 | 135 | 0
Property Level Protection - Don View (West Boldon) and Newcastle Road (South Shields) | North East | Northumbria | Northumberland Durham and Tees | South Shields | South Shields | South Tyneside | South Tyneside Borough Council | Construction | 42.6 | 42.6 | 0 | 34.3 | 0 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Property Level Protection - Elberfeld Court, Jarrow | North East | Northumbria | Northumberland Durham and Tees | South Shields | South Shields | South Tyneside | South Tyneside Borough Council | Construction | 126.8 | 126.8 | 0 | 102.8 | 0 | By April 2017 | By April 2019 | 25 | 0 | 25 | 0
Cleadon Village and Boldon Flats - Appraisal, Design and Construction | North East | Northumbria | Northumberland Durham and Tees | South Shields | Cleadon, South Tyneside | South Tyneside | South Tyneside Borough Council | Development | 1964.3 | 577.646 | 1386.654 | 50 | 299.246 | 2017-2019 | By April 2021 | 55 | 0 | 55 | 0
Newmarket Walk South Shields Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | South Shields | South Shields, South Tyneside | South Tyneside | South Tyneside Borough Council | Development | 1325.3 | 550.3 | 775 | 0 | 50 | 2019-2021 | Beyond 2021 | 0 | 0 | 85 | 0
Marsden Bay Cliff Erosion Study | North East | Northumbria | Northumberland Durham and Tees | South Shields | Marsden Bay, Whitburn | South Tyneside | South Tyneside Borough Council | Development | 923.1 | 556.1 | 367 | 0 | 310.5 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Cut Throat Dene Watercourse Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Sunderland Central | Sunderland | South Tyneside | Sunderland City Council | Development | 175 | 45 | 130 | 0 | 45 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Port Clarence and Greatham South Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Stockton North | Middlesborough | Stockton-on-Tees | Environment Agency | Construction | 17142.223 | 8842.223 | 8300 | 1650 | 1250 | By April 2017 | By April 2021 | 360 | 0 | 360 | 0
Ings lane Surface Water Property Level Protection | North East | Northumbria | Northumberland Durham and Tees | Stockton South | Ings Lane, Yarm | Stockton-on-Tees | Stockton-on-Tees Borough Council | Construction | 6.2 | 0.8 | 5.4 | 0 | 0.8 | By April 2017 | By April 2019 | 1 | 0 | 1 | 0
Lustrum Beck Flood Alleviation Scheme including Browns Bridge | North East | Northumbria | Northumberland Durham and Tees | Stockton South | Stockton on Tees: Hartburn, Oxbridge, Newton | Stockton-on-Tees | Environment Agency | Construction | 3402.947 | 1869.972 | 1532.975 | 176 | 25.5 | By April 2017 | By April 2021 | 220 | 0 | 220 | 0
Springwell Village - surface water flooding | North East | Northumbria | Northumberland Durham and Tees | Washington and Sunderland West | Sunderland | Sunderland | Sunderland City Council | Construction | 259.9 | 209.9 | 50 | 101.2 | 0 | By April 2017 | By April 2019 | 40 | 0 | 40 | 0
Dene Street Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Houghton and Sunderland South | Sunderland | Sunderland | Sunderland City Council | Construction | 115.456 | 55.456 | 60 | 55.456 | 0 | By April 2017 | By April 2019 | 5 | 0 | 5 | 0
Hendon Burn Culvert Capital Maintenance Design & Construction (i.e. strengthening deformed section of culvert) | North East | Northumbria | Northumberland Durham and Tees | Sunderland Central | Sunderland | Sunderland | Sunderland City Council | Development | 170 | 75 | 95 | 75 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Strategy Frontage 3 (Hendon Foreshore Barrier / Stonehill Wall / SW Breakwater) | North East | Northumbria | Northumberland Durham and Tees | Sunderland Central | Sunderland | Sunderland | Sunderland City Council | Development | 10141 | 3691 | 6450 | 0 | 690.39 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Citywide Culvert Repairs | North East | Northumbria | Northumberland Durham and Tees | Washington and Sunderland West | Sunderland City | Sunderland | Sunderland City Council | Development | 2537.2 | 1197.2 | 1340 | 0 | 53.6 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Blackberry Cottages, Springwell Village, Surface Water Flood Alleviation | North East | Northumbria | Northumberland Durham and Tees | Washington and Sunderland West | Blackberry Cottages, Springwell Village | Sunderland | Sunderland City Council | Development | 55 | 40 | 15 | 40 | 0 | Beyond 2021 | Beyond 2021 | 5 | 0 | 5 | 0
Hendon Burn Watercourse, Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Houghton and Sunderland South | Sunderland | Sunderland | Sunderland City Council | Development | 77 | 7 | 70 | 7 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Holley Park, Surface Water Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Washington and Sunderland West | Lambton, Washington | Sunderland | Sunderland City Council | Development | 120 | 20 | 100 | 20 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Fatfield Flood Alleviation Study | North East | Northumbria | Northumberland Durham and Tees | Washington and Sunderland West | Fatfield | Sunderland | Environment Agency | Pipeline | 590 | 100 | 490 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 45 | 0
Croft (downstream of bridge) Flood Alleviation Scheme | Yorkshire & the Humber | Northumbria | Northumberland Durham and Tees | Richmond (Yorks) | Croft-on-Tees, River Tees | Various | Environment Agency | Development | 367.6 | 332.6 | 35 | 0 | 324.1 | 2019-2021 | By April 2021 | 35 | 0 | 35 | 0
North West Durham propertly level protection | North East | Northumbria | Northumberland Durham and Tees | North Durham | North West Durham Co Const (Consett, Stanley, Burnhope, Langley Park) | Various | Durham County Council | Development | 33 | 26 | 7 | 0 | 26 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Helston Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Helston | Cornwall | Environment Agency | Construction | 2911.703 | 2591.703 | 320 | 1355.5 | 10 | By April 2017 | By April 2019 | 105 | 0 | 105 | 0
CCTV Installation of Devon and Cornwall Flood Risk Management Assets | South West | South West | Devon Cornwall and the Isles of Scilly | various | various | Cornwall | Environment Agency | Construction | 400 | 400 | 0 | 40 | 120 | By April 2017 | By April 2021 | 0 | 0 | 0 | 0
Falmouth Tidal Flood Defence Scheme Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Truro and Falmouth | Falmouth | Cornwall | Environment Agency | Construction | 95 | 95 | 0 | 85 | 0 | By April 2017 | By April 2019 | 5 | 0 | 5 | 0
Par Moor Diversion Culvert | South West | South West | Devon Cornwall and the Isles of Scilly | St Austell and Newquay | Par | Cornwall | Environment Agency | Construction | 820 | 180 | 640 | 50 | 0 | By April 2017 | By April 2021 | 15 | 0 | 15 | 0
Perranporth (Bolingey River) Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Truro & Falmouth | Perranporth | Cornwall | Environment Agency | Construction | 1221.556 | 1014.556 | 207 | 25 | 0 | By April 2017 | By April 2019 | 105 | 0 | 105 | 0
Wooda Screen Inlet Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Wooda screen inlet screen, Wooda Lane, Launceston | Cornwall | Environment Agency | Construction | 40 | 40 | 0 | 25 | 0 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Bude Breakwater Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | North Cornwall | Bude | Cornwall | Cornwall Council | Development | 180 | 180 | 0 | 45 | 135 | 2017-2019 | By April 2021 | 20 | 0 | 20 | 0
Chapel Square, Mevagissey Culvert Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | St Austell & Newquay | Mevagissey | Cornwall | Cornwall Council | Development | 330 | 190 | 140 | 0 | 190 | 2019-2021 | By April 2021 | 45 | 0 | 45 | 0
Cockington Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Torquay | Cornwall | Torbay Council | Development | 255 | 150 | 105 | 125 | 25 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Downderry Coast Protection Works Phase 2 | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Downderry | Cornwall | Cornwall Council | Development | 826 | 495 | 331 | 0 | 445 | 2019-2021 | Beyond 2021 | 0 | 25 | 0 | 25
Fowey Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Fowey | Cornwall | Environment Agency | Development | 1080 | 380 | 700 | 50 | 180 | 2019-2021 | Beyond 2021 | 0 | 0 | 30 | 0
Halzephron Coastal Adaptation Works | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Gunwalloe | Cornwall | Cornwall Council | Development | 250 | 62.5 | 187.5 | 0 | 62.5 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Hannafore Sea Defence Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Hannafore | Cornwall | Cornwall Council | Development | 100 | 80 | 20 | 80 | 0 | 2017-2019 | By April 2019 | 0 | 15 | 0 | 15
Hollicombe Rock Armour | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Paignton | Cornwall | Torbay Council | Development | 1543.8 | 1279.8 | 264 | 384.8 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Keveral Gardens, Seaton Culvert Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Seaton | Cornwall | Cornwall Council | Development | 250 | 165 | 85 | 0 | 165 | 2019-2021 | By April 2021 | 25 | 0 | 25 | 0
Kingsand Coast Protection Works | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Kingsand | Cornwall | Cornwall Council | Development | 125 | 125 | 0 | 0 | 125 | 2017-2019 | By April 2019 | 0 | 5 | 0 | 5
Long Rock Revetment Extension East | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Long Rock, Penzance | Cornwall | Cornwall Council | Development | 250 | 125 | 125 | 0 | 125 | 2017-2019 | By April 2019 | 0 | 15 | 0 | 15
Mevagissey Harbour Victoria Pier Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | St Austell and Newquay | Mevagissey | Cornwall | Cornwall Council | Development | 980 | 780 | 200 | 60 | 720 | 2019-2021 | By April 2021 | 100 | 0 | 100 | 0
Monksbridge Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Totnes | Brixham | Cornwall | Torbay Council | Development | 260 | 210 | 50 | 210 | 0 | 2019-2021 | By April 2021 | 35 | 0 | 35 | 0
Porthleven Harbour Walls Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Porthleven | Cornwall | Cornwall Council | Development | 300 | 300 | 0 | 0 | 300 | 2017-2019 | By April 2021 | 0 | 50 | 0 | 50
Portreath Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Camborne and Redruth | Portreath | Cornwall | Environment Agency | Development | 987 | 557 | 430 | 50 | 382 | 2019-2021 | Beyond 2021 | 135 | 0 | 135 | 0
River Fleet Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Torquay | Cornwall | Torbay Council | Development | 5359 | 2109 | 3250 | 675 | 1359 | 2017-2019 | By April 2021 | 500 | 0 | 500 | 0
Tumble Tyn and Paul Stream Culvert Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Mousehole | Cornwall | Cornwall Council | Development | 260 | 135 | 125 | 0 | 135 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
A390 Tregrehan Stream Culvert Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | St. Austell and Newquay | Tregehan Stream, Par | Cornwall | Cornwall Council | Development | 350 | 200 | 150 | 200 | 0 | 2017-2019 | By April 2019 | 3 | 0 | 3 | 0
Bude Flood Defence and River Restoration Project | South West | South West | Devon Cornwall and the Isles of Scilly | North Cornwall | Bude | Cornwall | Environment Agency | Development | 1073 | 713 | 360 | 41 | 562 | 2017-2019 | By April 2021 | 30 | 0 | 30 | 0
Calstock Flood Defence Improvements and Habitat Creation | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Calstock | Cornwall | Environment Agency | Development | 850.159 | 576.909 | 273.25 | 60 | 328 | 2017-2019 | By April 2021 | 15 | 0 | 15 | 0
Coverack Sea Walls Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Coverack | Cornwall | Cornwall Council | Development | 310 | 155 | 155 | 155 | 0 | 2017-2019 | By April 2019 | 0 | 10 | 0 | 10
Drakewalls Stream Culvert Inlet Screen Refurbishments | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Body's Court, Gunnislake | Cornwall | Environment Agency | Development | 60 | 37 | 23 | 0 | 37 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Hayle River Flood Bank Re-Alignment and Habitat Creation | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Hayle | Cornwall | Environment Agency | Development | 2300 | 220 | 2080 | 50 | 120 | 2019-2021 | By April 2021 | 25 | 0 | 25 | 0
Latchbrook Impoundment Dam Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Latchbrook, Saltash | Cornwall | Environment Agency | Development | 120 | 97 | 23 | 0 | 97 | 2019-2021 | By April 2021 | 25 | 0 | 25 | 0
Looe Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Looe | Cornwall | Environment Agency | Development | 10695 | 1295 | 9400 | 100 | 980 | 2017-2019 | By April 2021 | 115 | 0 | 115 | 0
Mevagissey - Fluvial Culvert Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | St Austell and Newquay | Mevagissey | Cornwall | Environment Agency | Development | 482 | 247 | 235 | 50 | 197 | 2019-2021 | By April 2021 | 45 | 0 | 45 | 0
Newlyn - Tidal Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Newlyn | Cornwall | Environment Agency | Development | 410 | 55 | 355 | 15 | 0 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Padstow Town Stream Harbour Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | St. Austell and Newquay | Padstow Harbour | Cornwall | Environment Agency | Development | 380 | 376.57 | 3.43 | 10 | 206.57 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Par/St. Blazey Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | North Cornwall | Par/St. Blazey | Cornwall | Environment Agency | Development | 15420 | 6763 | 8657 | 220 | 4288 | 2017-2019 | Beyond 2021 | 200 | 0 | 450 | 0
Paul Stream Channel/Culvert Refurbishments | South West | South West | Devon Cornwall and the Isles of Scilly | St. Ives | Mousehole | Cornwall | Environment Agency | Development | 150 | 83 | 67 | 0 | 83 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Penryn Tidal Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Truro and Falmouth | Penryn | Cornwall | Environment Agency | Development | 540 | 185 | 355 | 10 | 145 | Beyond 2021 | Beyond 2021 | 0 | 0 | 20 | 0
Penzance Wherrytown and Harbour Tidal Flood Defence Scheme Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Penzance | Cornwall | Environment Agency | Development | 1345 | 440 | 905 | 75 | 255 | 2019-2021 | By April 2021 | 60 | 0 | 60 | 0
Polperro Trash Screen Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | South East Cornwall | Polperro | Cornwall | Environment Agency | Development | 200 | 177 | 23 | 102 | 0 | 2017-2019 | By April 2019 | 60 | 0 | 60 | 0
Portreath Tunnel Patch Repairs | South West | South West | Devon Cornwall and the Isles of Scilly | Camborne and Redruth | Portreath | Cornwall | Environment Agency | Development | 100 | 100 | 0 | 100 | 0 | 2017-2019 | By April 2019 | 85 | 0 | 85 | 0
Property Protection East Cornwall Catchment Flood Management Plan Phase 2 | South West | South West | Devon Cornwall and the Isles of Scilly | TBC | East Cornwall | Cornwall | Cornwall Council | Development | 99 | 47 | 52 | 47 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Property Protection East Cornwall Catchment Flood Management Plan Phase 3 | South West | South West | Devon Cornwall and the Isles of Scilly | TBC | East Cornwall | Cornwall | Cornwall Council | Development | 99 | 47 | 52 | 0 | 47 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Property Protection Tamar Catchment Flood Management Plan Phase 3 | South West | South West | Devon Cornwall and the Isles of Scilly | TBC | Tamar | Cornwall | Cornwall Council | Development | 99 | 47 | 52 | 0 | 47 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Property Protection West Cornwall Catchment Flood Management Plan Phase 2 | South West | South West | Devon Cornwall and the Isles of Scilly | TBC | West Conrwall | Cornwall | Cornwall Council | Development | 99 | 47 | 52 | 47 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Property Protection West Cornwall Catchment Flood Management Plan Phase 3 | South West | South West | Devon Cornwall and the Isles of Scilly | TBC | West Conrwall | Cornwall | Cornwall Council | Development | 99 | 47 | 52 | 0 | 47 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Sandy River Improvements Project | South West | South West | Devon Cornwall and the Isles of Scilly | St Austell and Newquay | St Austell | Cornwall | Environment Agency | Development | 723 | 379.41 | 343.59 | 90 | 179.41 | 2017-2019 | By April 2019 | 90 | 0 | 90 | 0
Tywardreath Stream Culvert Repairs | South West | South West | Devon Cornwall and the Isles of Scilly | St. Austell and Newquay | Par | Cornwall | Environment Agency | Development | 100 | 100 | 0 | 0 | 100 | 2019-2021 | By April 2021 | 105 | 0 | 105 | 0
Wadebridge Sheet Pile Wall | South West | South West | Devon Cornwall and the Isles of Scilly | North Cornwall | Wadebridge | Cornwall | Environment Agency | Development | 423 | 423 | 0 | 240 | 5 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
White River Flood Defence Re-Alignment and Habitat Creation | South West | South West | Devon Cornwall and the Isles of Scilly | St Austell and Newquay | St Austell | Cornwall | Environment Agency | Development | 2685 | 289 | 2396 | 100 | 0 | 2017-2019 | Beyond 2021 | 45 | 0 | 45 | 0
Long Rock Coastal Improvements Project | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Long Rock, Penzance | Cornwall | Cornwall Council | Development | 3724 | 2724 | 1000 | 0 | 2724 | 2017-2019 | By April 2021 | 265 | 0 | 265 | 0
Exmouth Tidal Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Exmouth | East Devon | Environment Agency | Construction | 15422.413 | 13765.137 | 1657.276 | 505 | 12750 | By April 2017 | By April 2021 | 1415 | 0 | 1415 | 0
Lympstone Strand Trash Screen Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Wotton Brook, Lympstone | East Devon | Environment Agency | Construction | 95 | 95 | 0 | 4 | 0 | By April 2017 | By April 2019 | 165 | 0 | 165 | 0
New Feniton Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Feniton, Devon | East Devon | East Devon District Council | Construction | 1788 | 480 | 1308 | 137 | 0 | By April 2017 | Beyond 2021 | 65 | 0 | 65 | 0
Bampton Scheme Upstream Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Tiverton and Honiton | Bampton, Devon | East Devon | Environment Agency | Development | 628 | 503 | 125 | 75 | 353 | 2017-2019 | By April 2021 | 45 | 0 | 45 | 0
Clyst St Mary Flood Defence Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Tiverton and Honiton | Clyst St Mary | East Devon | Environment Agency | Development | 1400 | 975 | 425 | 0 | 850 | 2017-2019 | By April 2021 | 40 | 0 | 40 | 0
Colaton Raleigh Flood Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Colaton Raleigh | East Devon | Devon County Council | Development | 220 | 150 | 70 | 0 | 150 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Sidmouth Main Beach and Eastern Beach - Beach Management Plan | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Sidmouth | East Devon | East Devon District Council | Development | 370.5 | 300 | 70.5 | 60 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Sidmouth Flood Improvement Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Sidmouth | East Devon | Devon County Council | Development | 330 | 200 | 130 | 0 | 200 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Seaton Beach and Axmouth Harbour - Beach Management Plan | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Seaton | East Devon | East Devon District Council | Development | 375 | 375 | 0 | 150 | 125 | 2019-2021 | By April 2021 | 330 | 0 | 330 | 0
Exe Estuary Habitat Delivery | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Exe Estuary | East Devon | Environment Agency | Pipeline | 8137.394 | 5137.394 | 3000 | 370 | 4140 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Withycombe and Bapton Wall Refurfishments | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Withycombe and Bapton Brook, Exmouth, Devon | East Devon | Environment Agency | Pipeline | 230 | 230 | 0 | 30 | 0 | 2019-2021 | Beyond 2021 | 0 | 0 | 0 | 0
Exeter Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Exeter | Exeter | Exeter | Environment Agency | Construction | 32797.306 | 19327.306 | 13470 | 4132.065 | 2815 | By April 2017 | By April 2019 | 3270 | 0 | 3270 | 0
Exeter Flood Surface Water Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Exeter | Exeter | Exeter | Devon County Council | Development | 585 | 300 | 285 | 150 | 150 | 2017-2019 | By April 2019 | 60 | 0 | 60 | 0
Mincinglake /Northbrook Watercourse Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Exeter | EXETER | Exeter | Exeter City Council | Development | 1368 | 1165 | 203 | 0 | 1005 | 2019-2021 | By April 2021 | 140 | 0 | 140 | 0
Church Sea Wall Repairs, Old Town, St Mary's | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | St Mary's | Isles of Scilly | Council of the Isles of Scilly | Development | 75 | 75 | 0 | 0 | 75 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Dune Management Plan and Works, Isles of Scilly | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | St Mary's | Isles of Scilly | Council of the Isles of Scilly | Development | 200 | 200 | 0 | 200 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Great Pool Sea Defence Repairs, St Agnes | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | St Agnes | Isles of Scilly | Council of the Isles of Scilly | Development | 100 | 100 | 0 | 50 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Hell Bay Sea Defence Repairs, Bryher | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | Bryher | Isles of Scilly | Council of the Isles of Scilly | Development | 100 | 100 | 0 | 100 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Lower Moors Catchment Management, St Mary's | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | St Mary's | Isles of Scilly | Council of the Isles of Scilly | Development | 200.01 | 200 | 0.01 | 0 | 100 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Mermaid Sea Wall Repairs, St Mary's | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | St Mary's | Isles of Scilly | Council of the Isles of Scilly | Development | 100 | 100 | 0 | 0 | 100 | 2019-2021 | By April 2021 | 2 | 2 | 2 | 2
Porthminick Revetment Repairs, St Mary's | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | St Mary's | Isles of Scilly | Council of the Isles of Scilly | Development | 100 | 100 | 0 | 0 | 100 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Town Beach Flood Defence, St Mary's | South West | South West | Devon Cornwall and the Isles of Scilly | St Ives | St Mary's | Isles of Scilly | Council of the Isles of Scilly | Development | 400.02 | 400.02 | 0 | 0 | 311 | 2019-2021 | By April 2021 | 20 | 20 | 20 | 20
Devon County Council Property Level Protection | South West | South West | Devon Cornwall and the Isles of Scilly | Devon Wide | Devon | Mid Devon | Devon County Council | Construction | 730 | 250 | 480 | 50 | 150 | By April 2017 | Beyond 2021 | 250 | 0 | 250 | 0
Tiverton Flood Defence Improvements Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Tiverton and Honiton | Tiverton, Devon | Mid Devon | Environment Agency | Development | 1335 | 1335 | 0 | 50 | 1100 | 2017-2019 | By April 2021 | 880 | 0 | 880 | 0
Wrafton Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | North Devon | Wrafton Braunton North Devon River Knowle and Chivenor | North Devon | Environment Agency | Development | 335.495 | 200 | 135.495 | 80 | 105 | 2017-2019 | By April 2021 | 95 | 0 | 95 | 0
Rolle Quay Flood Defence Repair | South West | South West | Devon Cornwall and the Isles of Scilly | North Devon | Barnstaple | North Devon | Environment Agency | Development | 1201.619 | 1201.619 | 0 | 350 | 450 | 2017-2019 | By April 2021 | 330 | 0 | 330 | 0
Dean Cross IUDM Flood Alleviation Scheme, Plymstock | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plymouth | Plymouth | Plymouth City Council | Development | 616 | 416 | 200 | 416 | 0 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Norossisick Way Culvert Trash Screen | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Moor View | Plymouth | Plymouth | Plymouth City Council | Development | 50 | 50 | 0 | 0 | 50 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Alexandra Close, Plymstock, Surface Water Flood Protection | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plymouth | Plymouth | Plymouth City Council | Development | 49 | 49 | 0 | 0 | 49 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Bernice Terrace, Lipson Vale, Surface Water Capacity Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Sutton, Devonport | Plymouth | Plymouth | Plymouth City Council | Development | 60 | 60 | 0 | 0 | 60 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Chaddlewood Screen Upgrade | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plympton | Plymouth | Environment Agency | Development | 130 | 63 | 67 | 28 | 0 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Chaddlewood Stream, Plympton, Plymouth, Capacity Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plymouth | Plymouth | Plymouth City Council | Development | 100 | 100 | 0 | 0 | 100 | 2017-2019 | By April 2021 | 20 | 0 | 20 | 0
Drunken Bridge Hill, Plympton, Addional Highway Drainage | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plymouth | Plymouth | Plymouth City Council | Development | 20 | 20 | 0 | 0 | 20 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Longbrook Culvert Desilts/Repairs | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plympton | Plymouth | Environment Agency | Development | 33 | 33 | 0 | 0 | 33 | 2017-2019 | By April 2019 | 65 | 0 | 65 | 0
Longbrook Street Drainage Management Scheme, Plympton, Plymouth, Watercourse Capacity Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plymouth | Plymouth | Plymouth City Council | Development | 202 | 202 | 0 | 182 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Plymouth, Stonehouse and Durnford Street, Tidal Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Sutton, Devonport | Plymouth | Plymouth | Plymouth City Council | Development | 1126 | 1126 | 0 | 0 | 876 | 2019-2021 | Beyond 2021 | 0 | 0 | 140 | 0
Plymouth, Sutton Harbour, Coxside, Lock Gate Climate Change Assessment Stage 1 & Stage 2 Works | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Sutton | Plymouth | Plymouth | Plymouth City Council | Development | 310 | 310 | 0 | 40 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 35 | 0
Plymouth, The Cattewater, Teats Hill Slipway Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Sutton, Devonport | Plymouth | Plymouth | Plymouth City Council | Development | 8 | 8 | 0 | 0 | 8 | 2019-2021 | By April 2021 | 3 | 0 | 3 | 0
Saltash Road, Keyham, Surface Water Capacity Improvments | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Moor View | Plymouth | Plymouth | Plymouth City Council | Development | 11 | 11 | 0 | 0 | 11 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Shearwood Close, Plympton, Additional Highway Drainage | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plymouth | Plymouth | Plymouth City Council | Development | 10 | 10 | 0 | 0 | 10 | 2017-2019 | By April 2019 | 2 | 0 | 2 | 0
Stenlake Terrace, Plymouth, Surface Water Capacity Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Sutton, Devonport | Plymouth | Plymouth | Plymouth City Council | Development | 60 | 60 | 0 | 0 | 60 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Tamerton Foliot Stream Screen Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth, Moor View | Tamerton Foliot | Plymouth | Environment Agency | Development | 65 | 42 | 23 | 22 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Tory Brook Desilt | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Plympton | Plymouth | Environment Agency | Development | 33 | 33 | 0 | 0 | 33 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Wadebridge Flood Defence Improvements and Habitat Creation | South West | South West | Devon Cornwall and the Isles of Scilly | North Cornwall | Wadebridge | Plymouth | Environment Agency | Development | 3144 | 329 | 2815 | 50 | 79 | 2019-2021 | Beyond 2021 | 170 | 0 | 170 | 0
Wolseley Road, Camels Head, Carriageway Reprofiling | South West | South West | Devon Cornwall and the Isles of Scilly | Plymouth-Moor View | Plymouth | Plymouth | Plymouth City Council | Development | 11 | 11 | 0 | 0 | 11 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Totnes Flood Defence Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Totnes | Totnes | South Hams | Environment Agency | Construction | 3966.6 | 3397.482 | 569.118 | 1095 | 10 | By April 2017 | By April 2019 | 285 | 0 | 285 | 0
Modbury Flood Defence Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Modbury | South Hams | Devon County Council | Construction | 460 | 300 | 160 | 150 | 0 | By April 2017 | By April 2019 | 60 | 0 | 60 | 0
Stibbs Lane, Ivybridge Drainage Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Stibbs Lane Ivybridge | South Hams | Devon County Council | Construction | 185 | 90 | 95 | 50 | 0 | By April 2017 | By April 2019 | 25 | 0 | 25 | 0
Kingsbridge Flood Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | South West Devon | Kingsbridge | South Hams | Environment Agency | Development | 570 | 400 | 170 | 0 | 400 | 2017-2019 | By April 2021 | 100 | 0 | 100 | 0
Totnes Steamer Quay Wall Repairs | South West | South West | Devon Cornwall and the Isles of Scilly | Totnes | Totnes, Steamer Quay, River Dart | South Hams | Environment Agency | Development | 385 | 385 | 0 | 105 | 0 | 2017-2019 | By April 2019 | 110 | 0 | 110 | 0
Dawlish Warren and Exmouth Beach Management Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Newton Abbot | Dawlish Warren & Exmouth | Teignbridge | Environment Agency | Construction | 14803.236 | 14636.236 | 167 | 10500 | 886 | By April 2017 | By April 2021 | 2880 | 0 | 2880 | 0
Stokeinteignhead Flood 2012 - Remedial Works | South West | South West | Devon Cornwall and the Isles of Scilly | Newton Abbot | Stokeinteignhead | Teignbridge | Devon County Council | Construction | 240 | 200 | 40 | 50 | 0 | By April 2017 | By April 2019 | 70 | 0 | 70 | 0
Newton Abbot and Kingsteignton Flood Defence Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Newton Abbot | Newton Abbot and Kingsteignton | Teignbridge | Environment Agency | Development | 2652 | 1385 | 1267 | 60 | 925 | 2019-2021 | Beyond 2021 | 0 | 0 | 530 | 0
Starcross and Cockwood Tidal Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Newton Abbot | Starcross and Cockwood | Teignbridge | Environment Agency | Development | 3390 | 3365 | 25 | 1755 | 1265 | 2017-2019 | By April 2019 | 660 | 0 | 660 | 0
Combeinteignhead, Shaldon Floods 2012 Remedial Works - Culvert Replacement | South West | South West | Devon Cornwall and the Isles of Scilly | Newton Abbot | Combeinteignhead | Teignbridge | Teignbridge District Council | Development | 326.001 | 266 | 60.001 | 100 | 166 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Coombe Valley Dam - Flood Storage Improvements. | South West | South West | Devon Cornwall and the Isles of Scilly | Newton Abbot | Coombe Valley Dam, Teignmouth | Teignbridge | Teignbridge District Council | Development | 309 | 289 | 20 | 0 | 289 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Dawlish Water, Dawlish Floods 2012 - Flood Defence Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Newton Abbot | Dawlish Water | Teignbridge | Environment Agency | Development | 1000 | 980 | 20 | 0 | 730 | 2019-2021 | Beyond 2021 | 0 | 0 | 40 | 0
Paignton Green Culvert and Pump Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Victoria Stream, Paignton, Devon | Torbay | Environment Agency | Construction | 1140 | 1140 | 0 | 358.342 | 0 | By April 2017 | By April 2019 | 120 | 0 | 120 | 0
Brixham Flood Alleviatioon Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Totnes | Brixham | Torbay | Torbay Council | Development | 1280 | 1220 | 60 | 0 | 790 | 2019-2021 | Beyond 2021 | 10 | 0 | 225 | 0
Collaton St Mary Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Paignton | Torbay | Torbay Council | Development | 191 | 91 | 100 | 0 | 91 | 2019-2021 | By April 2021 | 10 | 0 | 10 | 0
Occombe Valley Watercourse Flood Alleviation Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Paignton | Torbay | Torbay Council | Development | 265 | 235 | 30 | 0 | 235 | 2017-2019 | By April 2021 | 65 | 0 | 65 | 0
Paignton Seafront Defence Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Paignton Seafront | Torbay | Torbay Council | Development | 1850 | 1283 | 567 | 0 | 1083 | 2019-2021 | Beyond 2021 | 605 | 0 | 605 | 0
Haldon & Princess Piers Structural Repairs | South West | South West | Devon Cornwall and the Isles of Scilly | Torbay | Torquay | Torbay | Torbay Council | Pipeline | 5765.21 | 1191.5 | 4573.71 | 0 | 30 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Kenwith Operational Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Torridge and West Devon | River Kenwith, Bideford, Devon. | Torridge | Environment Agency | Development | 575 | 575 | 0 | 75 | 0 | 2017-2019 | By April 2019 | 220 | 0 | 220 | 0
Seaton Estuary Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | East Devon | Seaton | Torridge | Environment Agency | Development | 1650 | 1245 | 405 | 100 | 1000 | 2017-2019 | By April 2021 | 480 | 0 | 480 | 0
East The Water, Bideford Flood Wall Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | North Devon | Bideford | Torridge | Environment Agency | Development | 1245 | 220 | 1025 | 75 | 20 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
Ilfracombe Sea Defence Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | North Devon | Ilfracombe | Torridge | Environment Agency | Development | 350 | 327 | 23 | 50 | 277 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Kenwith, Bideford Flood Defence Scheme Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | North Devon | Bideford | Torridge | Environment Agency | Development | 1300 | 1275 | 25 | 0 | 1000 | 2019-2021 | Beyond 2021 | 700 | 0 | 700 | 0
Property Protection Tamar Catchment Flood Management Plan Phase 2 | South West | South West | Devon Cornwall and the Isles of Scilly | TBC | Tamar | West Devon | Cornwall Council | Development | 99 | 47 | 52 | 47 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Tinhay Scheme Refurbishment | South West | South West | Devon Cornwall and the Isles of Scilly | Torridge and West Devon | Tinhay, Lifton | West Devon | Environment Agency | Development | 85 | 62 | 23 | 0 | 62 | 2019-2021 | By April 2021 | 15 | 0 | 15 | 0
Willow Road, Tavistock Flood Defence Scheme Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Torridge and West Devon | Tavistock, Devon | West Devon | West Devon Borough Council | Development | 105 | 45 | 60 | 5 | 40 | 2017-2019 | By April 2019 | 105 | 0 | 105 | 0
Shoreham and Lancing Coastal Defences Beach Management Plan | South East | Southern | Solent and South Downs | East Worthing and Shoreham | Shoreham, West Sussex | Adur | Environment Agency | Construction | 599 | 599 | 0 | 190 | 280 | By April 2017 | By April 2021 | 900 | 0 | 900 | 0
Lancing Surface Water Management Plan and Actions | South East | Southern | Solent and South Downs | East Worthing and Shoreham | Lancing, West Sussex | Adur | West Sussex County Council | Construction | 270 | 270 | 0 | 90 | 0 | By April 2017 | By April 2019 | 90 | 0 | 90 | 0
Shoreham Adur Tidal Walls Scheme | South East | Southern | Solent and South Downs | East Worthing and Shoreham | Shoreham | Adur | Environment Agency | Construction | 29748.3192 | 21707.0802 | 8041.239 | 10838 | 2731 | By April 2017 | By April 2019 | 2330 | 0 | 2330 | 0
Works from Brighton Marina to River Adur Flood and Coastal Erosion Risk Management Strategy | South East | Southern | Solent and South Downs | Brighton, Pavilion | Shoreham to Brighton Marina | Adur | Brighton and Hove City Council | Development | 158939.0487 | 81640.0487 | 77299 | 0 | 321 | 2019-2021 | Beyond 2021 | 0 | 0 | 20 | 250
Capital Recycling West of R. Arun | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Aldwick, West Sussex | Arun | Arun District Council | Construction | 124 | 124 | 0 | 34 | 90 | By April 2017 | By April 2019 | 0 | 60 | 0 | 60
Pagham Beach Erosion Management Option | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Pagham, West Sussex | Arun | Arun District Council | Construction | 124.6 | 124.6 | 0 | 29.6 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Littlehampton Arun Tidal Defences East Bank | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Littlehampton, coast to 500m north of A259 | Arun | Environment Agency | Construction | 20186.1066 | 17886.1066 | 2300 | 24 | 0 | By April 2017 | By April 2019 | 0 | 0 | 750 | 0
Arun to Pagham Beach Management Plan | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Felpham, West Sussex | Arun | Arun District Council | Development | 223 | 183 | 40 | 46 | 117 | 2017-2019 | By April 2021 | 0 | 100 | 0 | 100
Arun Partnership Watercourse Management (East of District) | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Rustington, West Sussex | Arun | Arun District Council | Development | 90 | 70 | 20 | 26 | 25 | 2017-2019 | Beyond 2021 | 75 | 0 | 75 | 0
Ferring Rife Embankment Improvements | South East | Southern | Solent and South Downs | Worthing West | Ferring, Worthing | Arun | Environment Agency | Development | 600 | 350 | 250 | 0 | 320 | 2019-2021 | By April 2021 | 170 | 0 | 170 | 0
Aldingbourne Rife Integrated Flood Risk Management Plan and Works | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Aldingbourne, Bognor | Arun | Environment Agency | Development | 883.5167 | 671.5167 | 212 | 110 | 100 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Elmer Beach Management Works | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Elmer, West Sussex | Arun | Environment Agency | Development | 502.199 | 437.199 | 65 | 200 | 127.136 | 2017-2019 | By April 2019 | 105 | 20 | 105 | 20
Arundel Tidal Defence Improvements Phase 1 | South East | Southern | Solent and South Downs | Arundel and South Downs | Arundel | Arun | Environment Agency | Development | 750 | 271 | 479 | 0 | 220 | 2017-2019 | By April 2019 | 140 | 0 | 140 | 0
Land Drainage Outfall Improvement Provision (Rustington and East Preston) | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Rustington, West Sussex | Arun | Arun District Council | Development | 168 | 168 | 0 | 148 | 0 | 2017-2019 | By April 2019 | 60 | 0 | 60 | 0
Aldwick Groyne Replacement Scheme Ph 10 | South East | Southern | Solent and South Downs | Bognor Regis and Littlehampton | Aldwick, West Sussex | Arun | Arun District Council | Development | 380 | 227 | 153 | 0 | 227 | 2019-2021 | By April 2021 | 0 | 30 | 0 | 30
Angmering Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Arundel and South Downs | Angmering | Arun | Environment Agency | Pipeline | 1286.812 | 560 | 726.812 | 65 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 20 | 0
South Ashford Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Ashford | Ashford, Kent | Ashford | Environment Agency | Pipeline | 2229 | 602 | 1627 | 100 | 100 | Beyond 2021 | Beyond 2021 | 0 | 0 | 280 | 0
Thames Estuary Phase 1 Programme (So) | South East | Southern | Kent, South London and East Sussex | Dartford | Thames Estuary | Bexley | Environment Agency | Construction | 817114.7916 | 788349.6086 | 28765.183 | 1984.9 | 15632.361 | By April 2017 | Beyond 2021 | 310 | 0 | 13785 | 0
Crayford Integrated Drainage Study Output Scheme | London | Southern | Kent, South London and East Sussex | Bexleyheath and Crayford | Crayford, River Cray | Bexley | London Borough of Bexley | Development | 310 | 310 | 0 | 160 | 0 | 2017-2019 | By April 2019 | 165 | 0 | 165 | 0
Crayford Town Centre | London | Southern | Kent, South London and East Sussex | Bexleyheath and Crayford | Crayford Town Centre | Bexley | Environment Agency | Development | 1000 | 823 | 177 | 0 | 50 | 2019-2021 | By April 2021 | 0 | 0 | 300 | 0
Hall Place Flood Storage Reservoir Improvement works | London | Southern | Kent, South London and East Sussex | Bexleyheath and Crayford | Hall Place, Bourne Rd, Bexley | Bexley | Environment Agency | Development | 500 | 301.384 | 198.616 | 0 | 301.384 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Lamorbey Park Flood Storage Reservoir Improvement works | London | Southern | Kent, South London and East Sussex | Old Bexley and Sidcup | Burnt Oak Lane, Sidcup | Bexley | Environment Agency | Development | 200 | 200 | 0 | 0 | 200 | 2019-2021 | By April 2021 | 220 | 0 | 220 | 0
Old Bexley Defences Refurbishment/Replacement | London | Southern | Kent, South London and East Sussex | Old Bexley and Sidcup | Old Bexley | Bexley | Environment Agency | Development | 300 | 300 | 0 | 220 | 0 | 2019-2021 | By April 2021 | 95 | 0 | 95 | 0
Wyncham Stream Catchment | London | Southern | Kent, South London and East Sussex | Bexleyheath and Crayford | Sidcup, Wyncham Stream | Bexley | London Borough of Bexley | Development | 710 | 710 | 0 | 300 | 50 | 2017-2019 | By April 2019 | 490 | 0 | 490 | 0
Bevendean Surface water scheme | South East | Southern | Solent and South Downs | Brighton, Kemptown | Bevendean, Brighton | Brighton and Hove | Brighton and Hove City Council | Construction | 212.3187 | 20.847 | 191.4717 | 0 | 20.847 | By April 2017 | By April 2019 | 1 | 0 | 1 | 0
Carden Avenue (Brighton) Surface Water Scheme | South East | Southern | Solent and South Downs | Brighton, Pavilion | Warmdene Road, Brighton | Brighton and Hove | Brighton and Hove City Council | Construction | 78.7228 | 16.6239 | 62.0989 | 16.6239 | 0 | By April 2017 | By April 2019 | 5 | 0 | 5 | 0
Ruxley Gravel Pits Storage Scheme Improvement works | London | Southern | Kent, South London and East Sussex | Old Bexley and Sidcup | Ruxley Gravel Pits, Edgington Way, Foot's Cray | Bromley | Environment Agency | Development | 100 | 100 | 0 | 100 | 0 | 2019-2021 | By April 2021 | 100 | 0 | 100 | 0
Hampton to Bishopstone Coast Protection Works | South East | Southern | Kent, South London and East Sussex | North Thanet | Beltinge nr Herne Bay | Canterbury | Canterbury City Council | Construction | 5020 | 4231 | 789 | 2100 | 0 | By April 2017 | By April 2019 | 0 | 55 | 0 | 55
Herne Bay Sea Defence Works | South East | Southern | Kent, South London and East Sussex | North Thanet | Herne Bay, Kent | Canterbury | Canterbury City Council | Construction | 5458 | 5378 | 80 | 0 | 182.8 | By April 2017 | By April 2019 | 0 | 0 | 190 | 450
Studd Hill & Hampton Coastal Defence Works | South East | Southern | Kent, South London and East Sussex | North Thanet, Canterbury | Hampton nr Herne Bay | Canterbury | Canterbury City Council | Construction | 5655 | 4905 | 750 | 0 | 2397 | By April 2017 | Beyond 2021 | 0 | 245 | 0 | 245
Tankerton Coast Protection Works | South East | Southern | Kent, South London and East Sussex | Canterbury | Tankerton near Whitstable | Canterbury | Canterbury City Council | Development | 1420 | 1320 | 100 | 0 | 1320 | 2019-2021 | By April 2021 | 0 | 465 | 0 | 465
Great Stour Flood Alleviation Schemes | South East | Southern | Kent, South London and East Sussex | Canterbury | Great Stour between Wye (TR04824650) and Fordwich (TR18666014) | Canterbury | Environment Agency | Pipeline | 12236 | 9040.4368 | 3195.5632 | 1010 | 6014.4368 | 2017-2019 | By April 2021 | 0 | 0 | 300 | 0
Implementation of the Selsey, Bracklesham and East Wittering Beach Management (5yrs 2016/17 to 2020/21) | South East | Southern | Solent and South Downs | Chichester | Selsey, Bracklesham & East Wittering | Chichester | Chichester District Council | Construction | 1250 | 1250 | 0 | 250 | 750 | By April 2017 | By April 2021 | 430 | 80 | 430 | 80
Manhood Peninsula Surface Water Management Plan and Actions | South East | Southern | Solent and South Downs | Chichester | Manhood Peninsula, West Sussex | Chichester | West Sussex County Council | Construction | 270 | 270 | 0 | 90 | 0 | By April 2017 | By April 2019 | 215 | 0 | 215 | 0
Medmerry monitoring | South East | Southern | Solent and South Downs | Chichester | Medmerry Nr Selsey | Chichester | Environment Agency | Construction | 560 | 560 | 0 | 80 | 160 | By April 2017 | By April 2021 | 0 | 0 | 0 | 0
Medmerry Managed Realignment | South East | Southern | Solent and South Downs | Chichester | Medmerry Nr Selsey | Chichester | Environment Agency | Construction | 22218.6185 | 22218.6185 | 0 | 36.498 | 20 | By April 2017 | By April 2019 | 0 | 0 | 350 | 0
Sidlesham - Pagham harbour inland banks improvements | South East | Southern | Solent and South Downs | Chichester | Sidlesham, West Sussex | Chichester | Environment Agency | Pipeline | 3077.672 | 1227 | 1850.672 | 218 | 252 | 2017-2019 | By April 2021 | 0 | 0 | 35 | 0
Swanscombe Peninsula Defence Improvements and Land raising | South East | Southern | Kent, South London and East Sussex | Dartford | Swanscombe penninsula at Dartford - DA119BB | Dartford | Environment Agency | Development | 350 | 350 | 0 | 0 | 350 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Dartford Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Dartford | Dartford Town Centre, Dartford | Dartford | Environment Agency | Pipeline | 790 | 490 | 300 | 200 | 245 | 2017-2019 | By April 2019 | 0 | 0 | 80 | 0
Church Street, Deal Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Dover | Deal, Kent | Dover | Kent County Council | Construction | 270 | 169 | 101 | 0 | 169 | By April 2017 | By April 2019 | 40 | 0 | 40 | 0
Deal Beach management 2015-2020 | South East | Southern | Kent, South London and East Sussex | Dover | Deal Castle to Sandown Castle | Dover | Dover District Council | Construction | 1800 | 1800 | 0 | 350 | 1050 | By April 2017 | By April 2021 | 4700 | 0 | 4700 | 0
Kingsdown Beach Management 2015/16-20/21 | South East | Southern | Kent, South London and East Sussex | Dover | Kingsdown, Kent | Dover | Dover District Council | Construction | 750 | 750 | 0 | 0 | 450 | By April 2017 | By April 2021 | 535 | 0 | 890 | 0
Sandwich Town Tidal Defences | South East | Southern | Kent, South London and East Sussex | South Thanet | Sandwich, Kent | Dover | Environment Agency | Construction | 21958.76 | 12036.69 | 9922.07 | 640 | 43 | By April 2017 | By April 2019 | 0 | 0 | 485 | 0
St Margaret's Bay Coastal Protection Works | South East | Southern | Kent, South London and East Sussex | Dover | St Margaret's Bay | Dover | Dover District Council | Construction | 0.15 | 0.15 | 0 | 0.15 | 0 | By April 2017 | By April 2019 | 5 | 10 | 5 | 10
Brewery Sluice Reinstatement | South East | Southern | Kent, South London and East Sussex | South Thanet | Sandwich | Dover | Environment Agency | Development | 350 | 9.65 | 340.35 | 9.65 | 0 | 2017-2019 | By April 2019 | 100 | 0 | 100 | 0
Lydden Valley Wetlands | South East | Southern | Kent, South London and East Sussex | Dover | Lydden Valley, East Kent | Dover | Environment Agency | Development | 3037.974 | 847.875 | 2190.099 | 275.965 | 0 | By April 2017 | Beyond 2021 | 10 | 0 | 10 | 0
River Dour Desilting at Bridge Street | South East | Southern | Kent, South London and East Sussex | TBC | Bridge Street, Dover | Dover | Environment Agency | Development | 100 | 100 | 0 | 0 | 100 | 2019-2021 | By April 2021 | 45 | 0 | 45 | 0
Eastbourne Beach Management - 6 yr Plan (2015/16 - 2020/21) (Yrs 1 to 6) | South East | Southern | Solent and South Downs | Eastbourne | Eastbourne Sea Front | Eastbourne | Eastbourne Borough Council | Construction | 2100 | 1500 | 600 | 300 | 900 | By April 2017 | By April 2021 | 7465 | 270 | 7465 | 270
Lottbridge pump replacement | South East | Southern | Solent and South Downs | Eastbourne | Eastbourne | Eastbourne | Environment Agency | Pipeline | 280 | 280 | 0 | 280 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Hill Head to Portsmouth Harbour Entrance Beach Management Plan | South East | Southern | Solent and South Downs | Gosport | Gosport and Fareham Open Coast | Fareham | Gosport Borough Council | Development | 275 | 275 | 0 | 0 | 55 | 2017-2019 | By April 2019 | 10 | 10 | 10 | 10
Tidal Flood Defence Improvements, Wallington Shore Road, Fareham | South East | Southern | Solent and South Downs | Fareham | Old Wallington Village, Shore Road | Fareham | Environment Agency | Development | 1458.082 | 1458.082 | 0 | 868 | 3.6 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Alverstoke Coastal Flood & Erosion Risk Management Scheme | South East | Southern | Solent and South Downs | Gosport | Stoke Lake, Gosport | Gosport | Gosport Borough Council | Development | 539.5 | 539.5 | 0 | 23.1 | 434.5 | 2017-2019 | By April 2019 | 105 | 1 | 105 | 1
Forton Lake (Gosport) Coastal Flood and Erosion Risk Management Scheme | South East | Southern | Solent and South Downs | Gosport | Forton Lake. Gosport | Gosport | Gosport Borough Council | Development | 364.5 | 364.5 | 0 | 22 | 264.5 | 2017-2019 | By April 2019 | 70 | 5 | 70 | 5
Ebbsfleet Culvert Refurbishment/Replacement | South East | Southern | Kent, South London and East Sussex | Gravesham | Ebbsfleet and Gravesham | Gravesham | Environment Agency | Development | 520 | 520 | 0 | 20 | 500 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Hastings Coastal Defence Works - Stage 2 (Pier to Harbour Arm) | South East | Southern | Solent and South Downs | Hastings and Rye | Hastings, Pier to Harbour Arm | Hastings | Hastings Borough Council | Construction | 5586 | 5076 | 510 | 3249 | 52 | By April 2017 | By April 2019 | 30 | 270 | 30 | 270
Bulverhythe Capital Maintenance 2018/19-2022/23 | South East | Southern | Solent and South Downs | Hastings and Rye | Bulverhythe, East Sussex | Hastings | Environment Agency | Construction | 1230 | 1230 | 0 | 0 | 630 | By April 2017 | Beyond 2021 | 465 | 0 | 775 | 0
Bulverhythe Capital Maintenance 2013/14-2017/18 | South East | Southern | Solent and South Downs | Hastings and Rye | Between Bexhill and Hastings | Hastings | Environment Agency | Construction | 930 | 930 | 0 | 30 | 0 | By April 2017 | By April 2019 | 465 | 0 | 620 | 0
Hastings Coastal Defence Works - Stage 3 (SW Outfall to Pier) | South East | Southern | Solent and South Downs | Hastings and Rye | Hastings, Pier to SW Outfall | Hastings | Hastings Borough Council | Development | 260 | 260 | 0 | 70 | 80 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
South Hayling Island Beach Management Activities | South East | Southern | Solent and South Downs | Havant | Hayling Island Southern Frontage | Havant | Havant Borough Council | Development | 7253.9709 | 7253.9709 | 0 | 300 | 900 | 2017-2019 | By April 2019 | 240 | 2700 | 240 | 3000
West Brook South Flood Alleviation Scheme Emsworth | South East | Southern | Solent and South Downs | East Hampshire | Emsworth West Brook | Havant | Environment Agency | Development | 685.2 | 635.2 | 50 | 0 | 200 | 2017-2019 | By April 2019 | 0 | 0 | 125 | 0
West Brook North Flood Alleviation Scheme, Emsworth | South East | Southern | Solent and South Downs | Havant | Emswoth The West Brook | Havant | Environment Agency | Development | 950 | 280 | 670 | 280 | 0 | 2017-2019 | By April 2019 | 55 | 0 | 55 | 0
Lower Tidal River Arun Strategy Implementation Phase 1 | South East | Southern | Solent and South Downs | Arundel and South Downs | Arundel | Horsham | Environment Agency | Construction | 150 | 120 | 30 | 60 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Billingshurst Surface Water Management Plan and Actions | South East | Southern | Solent and South Downs | Horsham | Billinshurst, West Sussex | Horsham | West Sussex County Council | Development | 250 | 250 | 0 | 85 | 90 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Sustainable Drainage Systems in RBKC | London | Southern | Hertfordshire and North London | Kensington | The Royal Borough of Kensington and Chelsea (North Kensington and Holland Park Critical Drainage Areas) | Horsham | London Borough of Kensington and Chelsea | Development | 1825 | 1345 | 480 | 220 | 660 | 2017-2019 | Beyond 2021 | 100 | 0 | 520 | 0
Horsham Assets (Warnham Mill Reservoir Sluice Replacement and Provender Mill) | South East | Southern | Solent and South Downs | Horsham | Horsham, West Sussex | Horsham | Environment Agency | Pipeline | 759 | 649 | 110 | 0 | 101 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Monktonmead Brook pumping station and outfall improvements, Ryde, Isle of Wight | South East | Southern | Solent and South Downs | Isle of Wight | Ryde, Isle of Wight | Isle of Wight | Environment Agency | Development | 6004.1693 | 5379.1693 | 625 | 5000 | 0 | 2017-2019 | By April 2019 | 200 | 0 | 200 | 0
Schemes arising from South Wight Coastal Strategy | South East | Southern | Solent and South Downs | Isle of Wight | Anticipated to be in Sandown Bay (and the Ventnor Undercliff, to follow) | Isle of Wight | Isle of Wight Council | Development | 7482 | 7482 | 0 | 0 | 600 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 405
Cowes, East Cowes and Yarmouth Temporary Tidal Flood Barriers | South East | Southern | Solent and South Downs | Isle of Wight | Cowes, East Cowes and Yarmouth | Isle of Wight | Environment Agency | Development | 773.763 | 622.95 | 150.813 | 0 | 622.95 | 2019-2021 | By April 2021 | 75 | 0 | 75 | 0
Cowes and East Cowes PLP | South East | Southern | Solent and South Downs | Isle of Wight | Cowes and East Cowes | Isle of Wight | Environment Agency | Development | 267.23 | 131.437 | 135.793 | 0 | 131.437 | 2017-2019 | By April 2021 | 35 | 0 | 35 | 0
Tidal Cuckmere River Restoration | South East | Southern | Solent and South Downs | Lewes | Tidal Cuckmere, South of Alfriston | Lewes | Environment Agency | Construction | 550 | 150 | 400 | 0 | 150 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Southease Parish and Southease to A27 Tidal Embankment Rebuilds | South East | Southern | Solent and South Downs | Lewes | East Sussex | Lewes | Environment Agency | Construction | 2271.986 | 2271.986 | 0 | 166 | 769 | By April 2017 | Beyond 2021 | 25 | 0 | 40 | 0
Seaford Beach Shingle Recycling 2013/14 - 2017/18 | South East | Southern | Solent and South Downs | Lewes | Seaford | Lewes | Environment Agency | Construction | 1719 | 1719 | 0 | 350 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Middle Ouse WFD Mitigation and Wetland Habitat Creation | South East | Southern | Solent and South Downs | Lewes | Barcombe, East Sussex | Lewes | Environment Agency | Development | 155 | 125 | 30 | 15 | 100 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Winterbourne Stream (Lewes) Outfall Tidal Doors Replacement | South East | Southern | Solent and South Downs | Lewes | Ouse Catchment | Lewes | Environment Agency | Development | 250 | 194.475 | 55.525 | 0 | 194.475 | 2017-2019 | By April 2019 | 105 | 0 | 105 | 0
Hassocks Surface Water Management Plan and Actions | South East | Southern | Solent and South Downs | Arundel and South Downs | Hassocks, West Sussex | Mid Sussex | West Sussex County Council | Development | 425 | 425 | 0 | 150 | 200 | 2017-2019 | By April 2019 | 110 | 0 | 110 | 0
Hythe Coastal Flood Allevation Scheme | South East | Southern | Solent and South Downs | New Forest East | Hythe, Hampshire | New Forest | Environment Agency | Construction | 415 | 415 | 0 | 0 | 25 | By April 2017 | By April 2019 | 0 | 0 | 30 | 0
Hurst Spit Beach Management Plan 2013/14 to 2016/17 | South East | Southern | Solent and South Downs | New Forest West | Southeast England | New Forest | New Forest District Council | Construction | 100 | 87 | 13 | 20.88 | 0 | By April 2017 | By April 2019 | 450 | 0 | 450 | 0
Eastoke Drainage Improvements CFERM Scheme | South East | Southern | Solent and South Downs | Havant | Hayling Island | New Forest | Havant Borough Council | Development | 3500 | 3500 | 0 | 100 | 3400 | 2017-2019 | By April 2019 | 240 | 0 | 240 | 0
Hurst Spit Beach Management Plan 2016/17 to 2021/22 | South East | Southern | Solent and South Downs | New Forest West | Southeast England | New Forest | New Forest District Council | Development | 4150 | 4150 | 0 | 150 | 4000 | 2019-2021 | By April 2021 | 450 | 0 | 450 | 0
Bartley (New Forest) Fluvial Flood Alleviation Scheme | South East | Southern | Solent and South Downs | New Forest East | nr The New Forest SSSI, Bartley Water, Bartley Village, New Forest | New Forest | Environment Agency | Development | 170 | 85 | 85 | 0 | 85 | Beyond 2021 | Beyond 2021 | 15 | 0 | 15 | 0
Portsea Island - Flood Cell 4: North Portsea Island Coastal Flood and Erosion Risk Management Scheme | South East | Southern | Solent and South Downs | Portsmouth North | Portsea Island, Portsmouth | Portsmouth | Portsmouth City Council | Construction | 44774 | 44492 | 282 | 5300 | 16292 | By April 2017 | Beyond 2021 | 1315 | 0 | 1905 | 0
Portchester Castle to Paulsgrove Tidal Defence | South East | Southern | Solent and South Downs | Portsmouth North | Portchester, North shore Portsmouth Harbour | Portsmouth | Fareham Borough Council | Development | 9367.344 | 2490.344 | 6877 | 400 | 1749.9 | 2017-2019 | By April 2021 | 390 | 0 | 390 | 0
Old Portsmouth Tidal FCRM Scheme | South East | Southern | Solent and South Downs | Portsmouth South | Old Portsmouth, Portsmouth | Portsmouth | Portsmouth City Council | Development | 151.8 | 151.8 | 0 | 0 | 151.8 | 2019-2021 | By April 2021 | 125 | 0 | 125 | 0
Farlington Marsh FCERM Scheme | South East | Southern | Solent and South Downs | Portsmouth North | Farlington Marsh, South of M27 | Portsmouth | Environment Agency | Development | 4948.846 | 4948.846 | 0 | 0 | 525 | 2019-2021 | Beyond 2021 | 0 | 0 | 260 | 0
Portsea Island - Flood Cell 3: Eastney Lake Coastal Flood and Erosion Risk Management Scheme | South East | Southern | Solent and South Downs | Portsmouth South | Eastney & Milton, Portsmouth | Portsmouth | Portsmouth City Council | Development | 5786.6 | 4283.92 | 1502.68 | 0 | 380 | Beyond 2021 | Beyond 2021 | 105 | 0 | 490 | 0
Portsea Island - Flood Cell 1: Southsea Coastal Flood and Erosion Risk Management Scheme | South East | Southern | Solent and South Downs | Portsmouth South | Southsea, Portsmouth | Portsmouth | Portsmouth City Council | Development | 86281.91 | 80281.91 | 6000 | 3880 | 22801 | 2017-2019 | Beyond 2021 | 2300 | 0 | 4115 | 15
Jury's Gap Refurbishment | South East | Southern | Kent, South London and East Sussex | Hastings & Rye | Jury's Gap (Camber) | Rother | Environment Agency | Construction | 2336.386 | 2327.5 | 8.886 | 251 | 0 | By April 2017 | By April 2019 | 405 | 0 | 405 | 0
Pett Shingle Renourishment Phases 2-6 | South East | Southern | Kent, South London and East Sussex | Hastings & Rye | Pett Levels | Rother | Environment Agency | Construction | 3876 | 3876 | 0 | 554 | 554 | By April 2017 | By April 2021 | 1825 | 0 | 3190 | 0
Pett Shingle Renourishment Phases 7-11 | South East | Southern | Kent, South London and East Sussex | Hastings and Rye | Pett Level, Winchelsea Beach | Rother | Environment Agency | Construction | 2400 | 2400 | 0 | 0 | 1700 | By April 2017 | Beyond 2021 | 325 | 0 | 545 | 0
Crowhurst Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Bexhill and Battle | Crowhurst, Powdermill Stream | Rother | Environment Agency | Development | 266 | 106 | 160 | 106 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Lydd Ranges Schemes | South East | Southern | Kent, South London and East Sussex | Hastings & Rye, Folkestone & Hythe | Kent | Rother | Environment Agency | Development | 21759.662 | 15689.49 | 6070.172 | 524.25 | 14554.328 | 2019-2021 | Beyond 2021 | 0 | 0 | 3995 | 0
Rother Tidal Walls East | South East | Southern | Kent, South London and East Sussex | Hastings & Rye | Rother District, Kent | Rother | Environment Agency | Development | 13829.07 | 13661.57 | 167.5 | 388.5 | 12796 | 2017-2019 | By April 2021 | 210 | 0 | 210 | 0
Tillingham Sluice Replacement | South East | Southern | Kent, South London and East Sussex | Hastings and Rye | Rye | Rother | Environment Agency | Development | 575 | 575 | 0 | 75 | 450 | 2017-2019 | By April 2019 | 600 | 0 | 600 | 0
Upper Westerham Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Sevenoaks | River Darent from Squerry's Court to Long Pond, Westerham | Sevenoaks | Environment Agency | Construction | 137 | 137 | 0 | 9 | 128 | By April 2017 | By April 2019 | 40 | 0 | 40 | 0
Leigh Expansion and Hildenborough Embankments | South East | Southern | Kent, South London and East Sussex | Tonbridge and Malling | Tonbridge and Yalding, River Medway | Sevenoaks | Environment Agency | Development | 23625 | 11787.5 | 11837.5 | 0 | 4420 | 2017-2019 | Beyond 2021 | 0 | 0 | 1955 | 0
Leigh FSA Improvements | South East | Southern | Kent, South London and East Sussex | Tonbridge and Malling | Leigh FSA Leigh Kent | Sevenoaks | Environment Agency | Pipeline | 2788 | 2788 | 0 | 135 | 0 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Hythe to Folkestone Beach Management 2015 - 2020 | South East | Southern | Kent, South London and East Sussex | Folkestone & Hythe | East of Hythe Ranges to Sandgate. The Folkestone to Cliff End Flood & Erosion Risk Strategy refers to this frontage as Hythe to Folkestone Harbour Frontage A which is the most easten frontage in Coastal Cell 2. | Shepway | Shepway District Council | Construction | 1520 | 1520 | 0 | 250 | 550 | By April 2017 | By April 2021 | 0 | 2190 | 0 | 2190
Denge (Lydd Ranges) Beach Management 2016-2020 | South East | Southern | Kent, South London and East Sussex | Folkestone and Hythe | Lydd Ranges | Shepway | Environment Agency | Construction | 1960 | 1960 | 0 | 490 | 980 | By April 2017 | By April 2021 | 2140 | 0 | 2140 | 0
Hythe Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Folkestone and Hythe | Hythe | Shepway | Kent County Council | Development | 560 | 500 | 60 | 50 | 450 | 2017-2019 | By April 2021 | 65 | 0 | 65 | 0
Hythe to Folkestone Beach Management 2020 - 2025 | South East | Southern | Kent, South London and East Sussex | Folkestone & Hythe | East of Hythe Ranges to Sandgate. The Folkestone to Cliff End Flood & Erosion Risk Strategy refers to this frontage as Hythe to Folkestone Harbour Frontage A which is the most easten frontage in Coastal Cell 2. | Shepway | Shepway District Council | Development | 1333 | 1333 | 0 | 0 | 277 | 2019-2021 | Beyond 2021 | 0 | 0 | 0 | 1750
Hythe to Folkestone Beach Recharge | South East | Southern | Kent, South London and East Sussex | Folkestone and Hythe | Hythe to Folkestone | Shepway | Shepway District Council | Development | 5035 | 5035 | 0 | 0 | 5035 | 2019-2021 | By April 2021 | 0 | 2190 | 0 | 2190
Littlestone Beach Recharge 2020-21 | South East | Southern | Kent, South London and East Sussex | Folkestone and Hythe | Littlestone-on-Sea, Kent | Shepway | Environment Agency | Development | 1200 | 1200 | 0 | 0 | 1200 | 2019-2021 | By April 2021 | 1220 | 0 | 1220 | 0
Romney Sands Coastal Defences | South East | Southern | Kent, South London and East Sussex | Hastings & Rye, Folkestone & Hythe | Shepway District, Kent | Shepway | Environment Agency | Development | 717.607 | 532.859 | 184.748 | 287.5 | 0 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Hythe Ranges Scheme | South East | Southern | Kent, South London and East Sussex | Folkestone and Hythe | Hythe, Kent | Shepway | Environment Agency | Development | 20923.236 | 7599.317 | 13323.919 | 367.5 | 6389.96 | 2017-2019 | By April 2021 | 670 | 0 | 670 | 0
Seafield Coastal Flood & Erosion Risk Management Scheme | South East | Southern | Solent and South Downs | Gosport | Haslar Lake and Workhouse Lake, Gosport | South Oxfordshire | Gosport Borough Council | Development | 1171.4 | 1171.4 | 0 | 25.3 | 1056.4 | 2017-2019 | By April 2019 | 80 | 50 | 80 | 50
River Itchen (West Bank) Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Southampton, Test | West bank of River Itchen, Southampton | Southampton | Southampton City Council | Development | 34220.3 | 15580.3 | 18640 | 1000 | 8533 | 2017-2019 | By April 2021 | 430 | 0 | 430 | 0
Elmley Managed Realignment and Habitat Creation | South East | Southern | Kent, South London and East Sussex | Sittingbourne and Sheppey | Isle of Sheppey | Swale | Environment Agency | Construction | 1930 | 1930 | 0 | 1000 | 450 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Mocketts and Bells Pumping Station | South East | Southern | Kent, South London and East Sussex | Sittingbourne and Sheppey | Isle of Sheppey | Swale | Environment Agency | Construction | 600 | 600 | 0 | 100 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Warden Bay Outfall Refurbishment | South East | Southern | Kent, South London and East Sussex | Sittingbourne and Sheppey | Warden Bay | Swale | Environment Agency | Construction | 872 | 872 | 0 | 350 | 472 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Great Bells Farm | South East | Southern | Kent, South London and East Sussex | Sittingbourne and Sheppey | Isle of Sheppey | Swale | Environment Agency | Construction | 419.667 | 419.667 | 0 | 28 | 67.6 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Barton's Point Shingle Recycling | South East | Southern | Kent, South London and East Sussex | Sittingbourne and Sheppey | Sheerness | Swale | Environment Agency | Development | 150 | 150 | 0 | 150 | 0 | 2017-2019 | By April 2019 | 2340 | 0 | 2340 | 0
Oare Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Sittingbourne and Sheppey | Oare, Kent | Swale | Environment Agency | Development | 820 | 820 | 0 | 25 | 795 | 2017-2019 | Beyond 2021 | 10 | 0 | 10 | 0
Manor Farm, River Test - Regional Habitat Creation Programme | South East | Southern | Solent and South Downs | Southampton, Test | River Test | Test Valley | Environment Agency | Construction | 175 | 175 | 0 | 75 | 25 | By April 2017 | Beyond 2021 | 0 | 0 | 0 | 0
Romsey (R. Test) Fluvial Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Romsey and Southampton North | Romsey - River Test | Test Valley | Environment Agency | Development | 1739.287 | 1000.04 | 739.247 | 806.52 | 0 | 2017-2019 | By April 2019 | 100 | 0 | 100 | 0
East of Epple to Westgate Bay - Sea Wall Refacing Works | South East | Southern | Kent, South London and East Sussex | North Thanet | Westgate on Sea, Kent | Thanet | Thanet District Council | Construction | 297 | 244 | 53 | 244 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 50
Margate Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | North Thanet | Margate, Kent | Thanet | Kent County Council | Construction | 1190 | 1100 | 90 | 0 | 600 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Northern Sea Wall | South East | Southern | Kent, South London and East Sussex | North Thanet | Reculver/Birchington | Thanet | Environment Agency | Construction | 600 | 540 | 60 | 90 | 270 | By April 2017 | By April 2019 | 295 | 0 | 295 | 0
Ramsgate Marina Esplanade Sea Wall | South East | Southern | Kent, South London and East Sussex | South Thanet | Ramsgate Marina Esplanade | Thanet | Thanet District Council | Development | 530 | 530 | 0 | 30 | 500 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Thanet Groyne Reconstruction/Refurbishment | South East | Southern | Kent, South London and East Sussex | North and South Thanet | Thanet District | Thanet | Thanet District Council | Development | 562.6 | 468.1 | 94.5 | 293.5 | 174.6 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Westbrook Berm Resurfacing. | South East | Southern | Kent, South London and East Sussex | North Thanet | WestBrook Bay | Thanet | Thanet District Council | Development | 150 | 150 | 0 | 0 | 150 | 2017-2019 | By April 2021 | 0 | 70 | 0 | 70
Westbrook to St Mildreds Coping replacement | South East | Southern | Kent, South London and East Sussex | North Thanet | WestBrook to St Mildreds bay (Barns Car Park) Coast | Thanet | Thanet District Council | Development | 630 | 630 | 0 | 30 | 600 | 2017-2019 | By April 2019 | 0 | 70 | 0 | 70
Hildenborough Flood Alleviation | South East | Southern | Kent, South London and East Sussex | Tonbridge and Malling | Hildenborough, Kent | Tonbridge and Malling | Environment Agency | Development | 3200 | 2900 | 300 | 0 | 1400 | 2019-2021 | Beyond 2021 | 0 | 0 | 155 | 0
East Peckham Walls | South East | Southern | Kent, South London and East Sussex | Tonbridge and Malling | East Peckham | Tonbridge and Malling | Environment Agency | Development | 7554.59 | 3054.59 | 4500 | 350 | 2580 | 2017-2019 | By April 2019 | 410 | 0 | 410 | 0
Five Oak Green Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Tunbridge Wells | Five Oak Green | Tunbridge Wells | Environment Agency | Development | 1534 | 534 | 1000 | 250 | 244 | 2017-2019 | By April 2019 | 265 | 0 | 265 | 0
Paddock Wood Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Tunbridge Wells | Paddock Wood, Kent | Tunbridge Wells | Kent County Council | Development | 750 | 550 | 200 | 50 | 500 | 2017-2019 | By April 2021 | 170 | 0 | 170 | 0
Tunbridge Wells trash screen | South East | Southern | Kent, South London and East Sussex | Tunbridge Wells | Tunbridge Wells, Kent | Tunbridge Wells | Kent County Council | Development | 17 | 17 | 0 | 2 | 15 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Pevensey Levels Desilting | South East | Southern | Solent and South Downs | Bexhill and Battle | Pevensey Levels | Wealden | Environment Agency | Construction | 80 | 80 | 0 | 40 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Newhaven Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Lewes | Newhaven and Seaford | Wealden | Environment Agency | Construction | 13148.6125 | 9898.6125 | 3250 | 5750 | 3602 | By April 2017 | By April 2021 | 1060 | 215 | 1060 | 215
PEVENSEY BAY SEA DEFENCES PPP | South East | Southern | Solent and South Downs | Bexhill and Battle | Pevensey, East Sussex | Wealden | Environment Agency | Construction | 45271.6621 | 39935.6621 | 5336 | 1312.062 | 4062.981 | By April 2017 | Beyond 2021 | 18605 | 0 | 34110 | 0
Buleys Weir | South East | Southern | Kent, South London and East Sussex | Tonbridge and Malling | Tonbridge, Gasworks Stream | Wealden | Environment Agency | Construction | 425.012 | 197.639 | 227.373 | 2 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Newbridge Pumping station pump replacement | South East | Southern | Solent and South Downs | Bexhill and Battle | Pevensey levels | Wealden | Environment Agency | Development | 400 | 200 | 200 | 200 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Hailsham (Knockhatch Stream Extension) Flood Alleviation and River Restoration Scheme | South East | Southern | Solent and South Downs | Wealden | Knockhatch Stream Extension, Hailsham | Wealden | Environment Agency | Development | 175 | 175 | 0 | 0 | 175 | 2019-2021 | By April 2021 | 95 | 0 | 95 | 0
Drockmill Pumping Station Capital Maintenance | South East | Southern | Solent and South Downs | Bexhill and Battle | Glynleigh Sewer, Pevensey Levels | Wealden | Pevensey IDB | Development | 230 | 115 | 115 | 55 | 60 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Polegate Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Eastbourne | Wannock Mill Stream, Polegate | Wealden | Environment Agency | Development | 285 | 154 | 131 | 0 | 24 | 2019-2021 | By April 2021 | 0 | 0 | 40 | 0
Winchester Flood Mitigation Study | South East | Southern | Solent and South Downs | Winchester | Winchester, River Itchen Catchments | Winchester | Hampshire County Council | Development | 790 | 516 | 274 | 135 | 381 | 2017-2019 | By April 2021 | 70 | 0 | 70 | 0
Worthing - Goring Development, delivery and construction of replacement groynes | South East | Southern | Solent and South Downs | Worthing West | Worthing | Worthing | Worthing Borough Council | Development | 4045 | 3950 | 95 | 400 | 2300 | 2017-2019 | Beyond 2021 | 470 | 365 | 710 | 545
Oval Road Pumping Station, Dagenham - Refurbishment | East of England | Thames | Hertfordshire and North London | Dagenham and Rainham | Oval Road North, Dagenham, Essex, RM10 9EP | Barking and Dagenham | Environment Agency | Development | 116.899 | 116.899 | 0 | 25.875 | 60.524 | 2017-2019 | By April 2019 | 220 | 0 | 220 | 0
Decoy Brook Catchment (CDA 018) Flood Alleviation Scheme. | London | Thames | Hertfordshire and North London | Finchley and Golders Green | Decoy Brook - London Borough of Barnet | Barnet | London Borough of Barnet | Construction | 395 | 266.3 | 128.7 | 91.3 | 150 | By April 2017 | By April 2019 | 190 | 0 | 190 | 0
Northfield Avenue Surface Water Study | London | Thames | Hertfordshire and North London | Ealing Central and Acton | Area Around Northfield Avenue, Northfields | Basildon | London Borough of Ealing | Development | 380 | 350 | 30 | 20 | 320 | 2017-2019 | By April 2021 | 65 | 0 | 65 | 0
Basingstoke Flood Reduction Scheme | South East | Thames | Thames | Basingstoke | Basingstoke, Hampshire | Basingstoke and Deane | Environment Agency | Development | 1119.9997 | 582.4586 | 537.5411 | 50 | 532.4586 | Beyond 2021 | Beyond 2021 | 135 | 0 | 135 | 0
Tadley Flood Reduction Study | South East | Thames | Thames | TBC | Tadley, Hampshire on the Bishops Wood Stream | Basingstoke and Deane | Environment Agency | Development | 780 | 364.8157 | 415.1843 | 0 | 9.3542 | 2019-2021 | Beyond 2021 | 0 | 0 | 85 | 0
Buckskin Lane Flood Aleviation Scheme, Basingstoke | South East | Thames | Thames | Basingstoke | Buckskin, Basingstoke | Basingstoke and Deane | Hampshire County Council | Development | 2290 | 2090 | 200 | 410 | 1650 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Darent Industrial Estate Fluvial Flood Alleviation Scheme Works | London | Thames | Kent, South London and East Sussex | Bexleyheath and Crayford | Crayford Marshes, Near Erith, Kent DA8 2LD | Bexley | Environment Agency | Construction | 540 | 500 | 40 | 0 | 500 | By April 2017 | By April 2021 | 135 | 0 | 135 | 0
TBAG2 PLA Thames Barrier Act Navigation Reimbursements | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Thames Estuary | Bexley | Environment Agency | Construction | 5721 | 5721 | 0 | 480 | 1649 | By April 2017 | Beyond 2021 | 0 | 0 | 0 | 0
Thames Estuary Phase 1 Programme (TTD) | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Thames Estuary | Bexley | Environment Agency | Construction | 917358.6844 | 917358.6844 | 0 | 17303.667 | 32246.801 | By April 2017 | Beyond 2021 | 7200 | 0 | 167575 | 0
Great Breach Dyke culvert clearance (Alsike Road) | London | Thames | Kent, South London and East Sussex | Erith and Thamesmead | Thamesmead | Bexley | Environment Agency | Development | 750 | 750 | 0 | 750 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Crayford Marshes Flood Embankment Study & Works | London | Thames | Kent, South London and East Sussex | Dartford | Darent Industrail Park and Crayford Marshes, Slade Green, Kent - DA8 2AF | Bexley | Environment Agency | Development | 5055 | 3675 | 1380 | 0 | 55 | 2017-2019 | By April 2021 | 0 | 0 | 1200 | 0
Tokyngton & Stonebridge Flood Alleviation Scheme (LB Brent Tokyngton) | London | Thames | Hertfordshire and North London | Brent North | D/S of Welsh Harp/Tokyngton Park & Stonebridge Park Tube/Willesden Junction Station | Brent | Environment Agency | Development | 4150 | 2965 | 1185 | 0 | 1965 | 2017-2019 | Beyond 2021 | 0 | 0 | 495 | 0
North Brent and Harrow Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Harrow East | Wealdstone Brook | Brent | Environment Agency | Development | 2800 | 230 | 2570 | 0 | 50 | 2019-2021 | Beyond 2021 | 0 | 0 | 690 | 0
Shonks Mill - River Roding FRM Strategy - Works From | East of England | Thames | Hertfordshire and North London | Brentwood and Ongar | In the field north to Shonks Mill Road, Romford, RM4 1ET | Brentwood | Epping Forest District Council | Development | 5244.267 | 2695.318 | 2548.949 | 0 | 2411.746 | 2019-2021 | By April 2021 | 900 | 0 | 900 | 0
Kyd Brook Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Bromley and Chislehurst | Bromley - BR1 2BJ | Bromley | Environment Agency | Development | 1408 | 840.926 | 567.074 | 0 | 583.673 | 2019-2021 | By April 2021 | 145 | 0 | 145 | 0
South London culvert, trash screen and bridges blockage study | London | Thames | Kent, South London and East Sussex | Various | South London / Multiple Watercourses | Bromley | Environment Agency | Development | 700 | 700 | 0 | 50 | 600 | 2019-2021 | Beyond 2021 | 480 | 0 | 480 | 0
St James Stream at Upper Elmers End | London | Thames | Kent, South London and East Sussex | Beckenham | Upper Elmers End, Beckenham - St James Stream (Ravensbourne Catchment) | Bromley | Environment Agency | Development | 1250 | 750.2 | 499.8 | 84.8 | 665.4 | 2017-2019 | By April 2019 | 150 | 0 | 150 | 0
The Beck (East Branch) at Langley Park flood alleviation study | London | Thames | Kent, South London and East Sussex | Bromley and Chislehurst | Park Langley, Bromley | Bromley | Environment Agency | Development | 539 | 87.2 | 451.8 | 0 | 87.2 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
Ravensbourne West branch Integrated flood risk study and culvert improvement works | London | Thames | Kent, South London and East Sussex | Bromley and Chislehurst | London Borough of Bromley, | Bromley | London Borough of Bromley | Development | 115 | 115 | 0 | 0 | 115 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Ravensbourne (East Branch) at Southborough flood alleviation study | London | Thames | Kent, South London and East Sussex | Beckenham | Magpie Hall Lane, Southborough, Bromley | Bromley | Environment Agency | Pipeline | 497 | 87 | 410 | 0 | 47 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Bicester Town Centre Trash Screen Investigation | South East | Thames | Thames | Banbury | Bicester Town Centre, Oxfordshire | Cherwell | Environment Agency | Development | 35 | 35 | 0 | 5 | 30 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Bloxham Flood Alleviation Scheme | South East | Thames | Thames | Banbury | Brookside Way, Bloxham near Banbury | Cherwell | Environment Agency | Development | 340.8 | 164.55 | 176.25 | 42.55 | 69 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Wendlebury | South East | Thames | Thames | Banbury | Wendlebury, Nr Bicester | Cherwell | Environment Agency | Development | 345 | 165.586 | 179.414 | 100 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Bloxham (Tadmarton Road) Flood Risk Management Scheme | South East | Thames | Thames | Banbury | Tadmarton Road, Bloxham, Cherwell District, Oxfordshire | Cherwell | Oxfordshire County Council | Development | 79 | 56 | 23 | 56 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Chesham Flood Alleviation Scheme Vale Brook Culvert | South East | Thames | Hertfordshire and North London | Chesham and Amersham | Chesham | Chiltern | Environment Agency | Development | 3029 | 2214.387 | 814.613 | 0 | 2139.387 | 2017-2019 | By April 2021 | 580 | 0 | 580 | 0
Misbourne Flood alleviation and water management level strategy | South East | Thames | Hertfordshire and North London | Chesham and Amersham | Old Amersham - Chalfont St Giles High - Chalfont St Peter High Street - Missenden | Chiltern | Environment Agency | Development | 350 | 226.7 | 123.3 | 0 | 176.7 | 2017-2019 | By April 2019 | 140 | 0 | 140 | 0
River Churn Strategy Phase two | South West | Thames | Thames | The Cotswolds | River Churn Cirencester | Cotswold | Environment Agency | Construction | 877 | 877 | 0 | 60 | 817 | By April 2017 | Beyond 2021 | 60 | 0 | 60 | 0
Bourton on the Water Flood Alleviation Scheme Remediation | South West | Thames | Thames | The Cotswolds | Bourton on the Water, Gloucestershire | Cotswold | Environment Agency | Development | 343.5 | 143.7 | 199.8 | 0 | 73.7 | 2019-2021 | By April 2021 | 50 | 0 | 50 | 0
Cirencester Flood Storage Area | South West | Thames | Thames | The Cotswolds | Cirencester, Gloucestershire | Cotswold | Environment Agency | Development | 5150 | 1287.5 | 3862.5 | 0 | 1228.5 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Upper Mole Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Crawley | Crawley & Horley, Gatwick Airport | Crawley | Environment Agency | Construction | 21510.784 | 17689.181 | 3821.603 | 713.293 | 133.75 | By April 2017 | By April 2019 | 280 | 0 | 1465 | 0
SuDS in Sutton's Schools | London | Thames | Kent, South London and East Sussex | Carshalton and Wallington | Carshalton and Wallington. River Wandle. | Crawley | London Borough of Sutton | Development | 951.75 | 200.564 | 751.186 | 0 | 145.564 | 2017-2019 | By April 2019 | 110 | 0 | 110 | 0
Welcomes Road and Kenley Station surface water Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Croydon South | Kenley, Croydon | Croydon | London Borough of Croydon | Development | 327 | 327 | 0 | 117 | 0 | 2017-2019 | By April 2019 | 125 | 0 | 125 | 0
CDA003 - Carr Road, Northolt - Flood Risk Study | London | Thames | Hertfordshire and North London | Ealing North | Northolt, Ealing | Ealing | London Borough of Ealing | Development | 610 | 610 | 0 | 50 | 310 | 2019-2021 | Beyond 2021 | 0 | 0 | 40 | 0
CDA041 - Beech Avenue, East Acton - Property level protection, community engagement and SuDS | London | Thames | Hertfordshire and North London | Ealing Central and Acton | East Acton, LB Ealing | Ealing | London Borough of Ealing | Development | 610 | 610 | 0 | 50 | 560 | 2019-2021 | By April 2021 | 85 | 0 | 85 | 0
Critical Drainage Area 007 - High Street Acton Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Ealing Central and Acton | High Street, Acton | Ealing | London Borough of Ealing | Development | 377 | 340 | 37 | 20 | 300 | 2017-2019 | By April 2021 | 10 | 0 | 10 | 0
Islip Manor Estate Redevelopment - Disconnection of surface water drainage and implementation of SuDS | London | Thames | Hertfordshire and North London | Ealing North | Northolt, LB Ealing | Ealing | London Borough of Ealing | Development | 280 | 280 | 0 | 80 | 200 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Greenford Flood Management Scheme | London | Thames | Hertfordshire and North London | Ealing North | Greenford | Ealing | Environment Agency | Development | 1655.5564 | 1655.5564 | 0 | 32.085 | 1573.4714 | 2019-2021 | By April 2021 | 95 | 0 | 95 | 0
Alton Attenuation And Flood Study | South East | Thames | Thames | East Hampshire | Alton | East Hampshire | Environment Agency | Development | 445 | 428.136 | 16.864 | 78.136 | 300 | 2017-2019 | By April 2021 | 125 | 0 | 125 | 0
Chawton Flood Alleviation Scheme | South East | Thames | Thames | TBC | Chawton, Hampshire on the Lavant Stream | East Hampshire | Environment Agency | Development | 155 | 79.5305 | 75.4695 | 2.5655 | 76.965 | 2019-2021 | Beyond 2021 | 10 | 0 | 10 | 0
Local Groundwater Flood Aleviation - A32 Corridor | South East | Thames | Thames | East Hampshire | A32 inc. Farringdon, Four Marks and West Tisted, East Hampshire | East Hampshire | Hampshire County Council | Pipeline | 870 | 442.2548 | 427.7452 | 35 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 30 | 0
Little Hadham A120 Bypass flood storage area | West Midlands | Thames | Hertfordshire and North London | North East Hertfordshire | Rivers Ash, Albury Tributary and Lloyd Taylor Drain at Little Hadham, Hertfordshire | East Hertfordshire | Environment Agency | Development | 4355.892 | 842.11 | 3513.782 | 171.22 | 420.648 | 2017-2019 | By April 2021 | 65 | 0 | 65 | 0
Stanstead Radial Gate replacement River Lee | West Midlands | Thames | Hertfordshire and North London | Hertford and Stortford | Lee Navigation, Stanstead Lock, Great Amwell, Ware, Herts. | East Hertfordshire | Environment Agency | Development | 1099.064 | 304.584 | 794.48 | 103.5 | 201.084 | 2019-2021 | By April 2021 | 85 | 0 | 85 | 0
Stanstead Abbotts Flood Alleviation Scheme | West Midlands | Thames | Hertfordshire and North London | Hertford and Stortford | Stanstead Abbots, Herts. / Stanstead Drain | East Hertfordshire | East Hertfordshire District Council | Development | 745.9998 | 252.2318 | 493.768 | 34.0568 | 138.175 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Violets Lane – Furneux Pelham Flood Alleviation Scheme | West Midlands | Thames | Hertfordshire and North London | North East Hertfordshire | Furneux Pelham, Hertfordshire | East Hertfordshire | Environment Agency | Development | 175.313 | 54.332 | 120.981 | 15.068 | 16.082 | 2017-2019 | By April 2021 | 5 | 0 | 5 | 0
Amwell Bailey Bridge, Ware - Refurbishment | West Midlands | Thames | Hertfordshire and North London | Hertford and Stortford | Amwell Nature Reserve, Hollycross Road, Stanstead Abbotts, Ware, Herts | East Hertfordshire | Environment Agency | Pipeline | 1472.4102 | 417.457 | 1054.9532 | 103.5 | 117.835 | 2019-2021 | By April 2021 | 0 | 0 | 115 | 0
Papermill Stream Penstock, Channel and Bridge, Standon - M&E Upgrade & stuctural repairs | West Midlands | Thames | Hertfordshire and North London | North East Hertfordshire | Papermill House, Papermill Lane, Standon, Herts | East Hertfordshire | Environment Agency | Pipeline | 380.137 | 318.648 | 61.489 | 20 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 65 | 0
Lower Mole Safety Booms | South East | Thames | Kent, South London and East Sussex | Esher and Walton | Molesey, Elmbridge | Elmbridge | Environment Agency | Construction | 544 | 544 | 0 | 7 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
River Rythe: Flood Relief Culvert intake screen modification/replacement | South East | Thames | Kent, South London and East Sussex | Esher and Walton | River Rythe: U/S of Haven Court, Hinchley Wood | Elmbridge | Environment Agency | Construction | 100 | 100 | 0 | 20 | 80 | By April 2017 | By April 2019 | 100 | 0 | 100 | 0
Lower Mole Flood Alleviation Scheme Asset Plan | South East | Thames | Kent, South London and East Sussex | Esher and Walton | Lower River Mole. Hersham, Esher and Molesey in the Surrey Borough of Elmbridge | Elmbridge | Environment Agency | Construction | 750 | 750 | 0 | 0 | 570 | By April 2017 | By April 2019 | 3065 | 0 | 3065 | 0
Wey Meadows Flood Alleviation Scheme | South East | Thames | Thames | Runnymede and Weybridge | Wey Meadows, Surrey | Elmbridge | Environment Agency | Development | 305 | 297.086 | 7.914 | 0 | 37.086 | Beyond 2021 | Beyond 2021 | 0 | 0 | 25 | 0
Byfleet and Webridge Flood Alleviation Scheme | South East | Thames | Thames | Runnymede and Weybridge | Weybridge, Surrey on the River Wey | Elmbridge | Environment Agency | Development | 667.05 | 547.05 | 120 | 0 | 27.05 | 2017-2019 | By April 2019 | 0 | 0 | 680 | 0
Dead River | South East | Thames | Kent, South London and East Sussex | Esher and Walton | Elmbridge, Walton-on-Thames, Dead River | Elmbridge | Environment Agency | Pipeline | 913 | 913 | 0 | 74 | 467 | 2019-2021 | By April 2021 | 0 | 0 | 160 | 0
River Rythe Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Esher and Walton | River Rythe, Oxshott/Esher, Surrey | Elmbridge | Environment Agency | Pipeline | 3250 | 449.75 | 2800.25 | 25 | 175 | Beyond 2021 | Beyond 2021 | 0 | 0 | 220 | 0
Bullsmoor Lane Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Enfield North | Bullsmoor Lane, Bullsmoor, Enfield | Enfield | London Borough of Enfield | Development | 92.956 | 55.635 | 37.321 | 55.635 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Enfield Town Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Enfield, Southgate | Enfield Town (flood storage areas proposed at Town Park and Enfield Grammar School) | Enfield | London Borough of Enfield | Development | 412.728 | 312.728 | 100 | 292.728 | 0 | 2017-2019 | By April 2019 | 135 | 0 | 135 | 0
Rammey Sluice, Waltham Abbey - Replacement of Flood Control Structure | East of England | Thames | Hertfordshire and North London | Epping Forest | Rammey Sluice, Flood Relief Channel, Meridian Way, Waltham Abbey, Essex. | Epping Forest | Environment Agency | Development | 2434.7471 | 1456.4266 | 978.3205 | 0 | 1444.5496 | 2019-2021 | By April 2021 | 205 | 0 | 205 | 0
LFRC Control Structures, Ware to Enfield Island - Gantry Hoist Replacement Package | East of England | Thames | Hertfordshire and North London | Harlow | Hardmead Radial Gates, Stanstead Radial Gates, Feildes Weir, Meadgate Sluices, David Stoker Radial Gates, Rammey Marsh Sluices and Newmans Sluices | Epping Forest | Environment Agency | Pipeline | 229.381 | 94.485 | 134.896 | 41.4 | 23.085 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Clothworkers Wood - Wet Woodland Flood Storage Scheme | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Plumstead, Wickham Valley Watercourse | Greenwich | London Borough of Greenwich | Development | 175 | 141.35 | 33.65 | 0 | 16.35 | 2019-2021 | By April 2021 | 0 | 0 | 30 | 0
Little Quaggy Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Royal Borough of Greenwich | Greenwich | London Borough of Greenwich | Development | 475 | 475 | 0 | 25 | 450 | 2019-2021 | By April 2021 | 105 | 0 | 105 | 0
RBG Ordinary Watercourses | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Royal Borough of Greenwich | Greenwich | London Borough of Greenwich | Development | 85 | 85 | 0 | 40 | 0 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Wickham Valley Water Course Flood Storage Scheme | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | East Wickham, Wickham Valley Watercourse | Greenwich | London Borough of Greenwich | Development | 225 | 200.35 | 24.65 | 30 | 150 | 2017-2019 | By April 2019 | 60 | 0 | 60 | 0
Culvert and Trash Screen Effectiveness Quaggy River | London | Thames | Kent, South London and East Sussex | Eltham | Westhorne Avenue, Eltham, Greenwich, London | Greenwich | Environment Agency | Development | 150 | 150 | 0 | 0 | 75 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
RBG Groundwater preparation | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Royal Borough of Greenwich | Greenwich | London Borough of Greenwich | Development | 505 | 505 | 0 | 0 | 400 | 2017-2019 | By April 2019 | 200 | 0 | 200 | 0
Oxleas Wood NFM | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Royal Borough of Greenwich | Greenwich | London Borough of Greenwich | Pipeline | 35 | 24.02 | 10.98 | 24.02 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Guildford Flood Alleviation Scheme | South East | Thames | Thames | Guildford | Guildford | Guildford | Environment Agency | Development | 3486 | 1097 | 2389 | 0 | 937 | 2017-2019 | By April 2021 | 205 | 0 | 205 | 0
Ashenden Road Surface water scheme | South East | Thames | Thames | Guildford | Guildford | Guildford | Guildford Borough Council | Development | 210 | 150 | 60 | 0 | 150 | 2019-2021 | By April 2021 | 75 | 0 | 75 | 0
Norcott Road Surface Water Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Hackney South and Shoreditch | Hackney | Hackney | London Borough of Hackney | Development | 1236.7 | 1236.7 | 0 | 60 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 730 | 0
Green Lanes Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Enfield, Southgate | Green Lanes, Southgate | Haringey | London Borough of Enfield | Development | 75.07 | 55.18 | 19.89 | 42.18 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Larkspur Close Tottenham Sufrace Water Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Tottenham | Tottenham | Haringey | London Borough of Haringey | Development | 500 | 107.205 | 392.795 | 0 | 10 | Beyond 2021 | Beyond 2021 | 0 | 0 | 50 | 0
Moselle Brook Culvert Refurbishment | London | Thames | Hertfordshire and North London | Tottenham | Tottenham, Gtr. London / Moselle Brook | Haringey | Environment Agency | Development | 3829.5003 | 2059.4973 | 1770.003 | 91.4862 | 1888.0111 | 2017-2019 | By April 2021 | 740 | 0 | 740 | 0
Surface Water - Roundway (A10)_Warkworth Road_063 (Moselle Catchment) | London | Thames | Hertfordshire and North London | Tottenham | London Borough of Haringey | Haringey | London Borough of Haringey | Development | 179.592 | 174.395 | 5.197 | 1.014 | 168.381 | 2019-2021 | By April 2021 | 70 | 0 | 70 | 0
Kingsway, Blackwater Flood Alleviation Scheme | South East | Thames | Thames | Aldershot | Kingsway and Christchurch Drive | Hart | Environment Agency | Construction | 145 | 127.107 | 17.893 | 39.657 | 87.45 | By April 2017 | By April 2019 | 35 | 0 | 35 | 0
Sycamore Road Flood Alleviation Scheme | South East | Thames | Thames | North East Hampshire | Farnborough | Hart | Hampshire County Council | Construction | 304 | 195 | 109 | 185 | 0 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Fleet Flood Alleviation Scheme | South East | Thames | Thames | TBC | Fleet, Hampshire | Hart | Environment Agency | Development | 662.9998 | 536.6361 | 126.3637 | 4.047 | 497.5891 | 2019-2021 | Beyond 2021 | 75 | 0 | 75 | 0
North Yateley Flood Impact Reduction Project | South East | Thames | Thames | North East Hampshire | Yateley Green, Yateley | Hart | Environment Agency | Development | 492 | 477.124 | 14.876 | 50 | 379 | 2017-2019 | By April 2021 | 55 | 0 | 55 | 0
Tudor and Cricket Hill Stream Flood Reduction Project | South East | Thames | Thames | North East Hampshire | Yateley | Hart | Environment Agency | Development | 140 | 76.065 | 63.935 | 19.239 | 24.826 | 2017-2019 | By April 2021 | 25 | 0 | 25 | 0
Frog Island Tidal Sluices Penstock Automation | East of England | Thames | Hertfordshire and North London | Dagenham and Rainham | Creek Way, Rainham, Essex | Havering | Environment Agency | Development | 100.829 | 100.829 | 0 | 20.7 | 49.629 | 2017-2019 | By April 2019 | 155 | 0 | 155 | 0
Rainham Tidal Sluice, Rainham - Power Supply | East of England | Thames | Hertfordshire and North London | Dagenham and Rainham | Rainham , Essex | Havering | Environment Agency | Development | 224.497 | 224.497 | 0 | 41.4 | 152.597 | 2017-2019 | By April 2019 | 655 | 0 | 655 | 0
Upminster Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Uxbridge and South Ruislip | Upstream of Upminster | Havering | London Borough of Havering | Development | 690 | 499.109 | 190.891 | 0 | 21.109 | Beyond 2021 | Beyond 2021 | 0 | 0 | 15 | 0
CDA005 - Yeading Lane, Southall - Flood Risk Study | London | Thames | Hertfordshire and North London | Hayes and Harlington | Southall, Ealing. Proximity to Yeading Brook | Hillingdon | London Borough of Ealing | Development | 860 | 860 | 0 | 50 | 435 | 2019-2021 | Beyond 2021 | 0 | 0 | 60 | 0
Hydraulic Ram Replacement at Huntsmoor Weir | London | Thames | Hertfordshire and North London | Uxbridge and South Ruislip | Huntsmoor Weir is located on the River Colne off Old Mill Lane, Cowley near Uxbridge (TQ0486881576) | Hillingdon | Environment Agency | Pipeline | 830.253 | 405.459 | 424.794 | 20.7 | 0 | 2019-2021 | By April 2021 | 0 | 0 | 70 | 0
Cannon Brook and Mad Bess Brook Flood Management Scheme | London | Thames | Hertfordshire and North London | Uxbridge and South Ruislip | Cannon Brook, Mad Bess Brook & Ruislip Lido | Hillingdon | Environment Agency | Pipeline | 1933 | 183 | 1750 | 115 | 0 | 2017-2019 | Beyond 2021 | 0 | 0 | 95 | 0
Sustainable Drainage Systems in RBKC | London | Thames | Hertfordshire and North London | Kensington | The Royal Borough of Kensington and Chelsea (North Kensington and Holland Park Critical Drainage Areas) | Horsham | London Borough of Kensington and Chelsea | Development | 1825 | 1345 | 480 | 220 | 660 | 2017-2019 | Beyond 2021 | 100 | 0 | 520 | 0
Brentford Flood Risk Management Scheme | London | Thames | Hertfordshire and North London | Brentford and Isleworth | The river Brent from Brentford railway line down to the confluence with the River Thames. | Hounslow | Environment Agency | Pipeline | 2191 | 584.817 | 1606.183 | 80 | 0 | 2017-2019 | Beyond 2021 | 0 | 0 | 130 | 0
Islington Central Flood Risk Management Scheme | London | Thames | Hertfordshire and North London | Islington South and Finsbury | Islington | Islington | London Borough of Islington | Construction | 761.091 | 741.091 | 20 | 0 | 721.091 | By April 2017 | By April 2019 | 100 | 0 | 100 | 0
Islington North Flood Risk Management Scheme | London | Thames | Hertfordshire and North London | Islington North | Islington | Islington | London Borough of Islington | Construction | 481.037 | 481.037 | 0 | 0 | 461.037 | By April 2017 | By April 2019 | 60 | 0 | 60 | 0
Islington South Flood Risk Management Scheme | London | Thames | Hertfordshire and North London | Islington South and Finsbury | Islington | Islington | London Borough of Islington | Construction | 387.686 | 387.686 | 0 | 0 | 367.686 | By April 2017 | By April 2019 | 75 | 0 | 75 | 0
Kingston Town Centre Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Kingston and Surbiton | Kingston Town Centre | Kingston upon Thames | Environment Agency | Development | 4700 | 2597 | 2103 | 100 | 1247 | Beyond 2021 | Beyond 2021 | 0 | 0 | 500 | 0
London to Woking Rail link | London | Thames | Kent, South London and East Sussex | Kingston and Surbiton | Surbiton, Kingston upon Thames | Kingston upon Thames | London Borough of Kingston upon Thames | Development | 2130 | 716.362 | 1413.638 | 0 | 716.362 | 2017-2019 | By April 2019 | 165 | 0 | 165 | 0
Old Malden Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Kingston and Surbiton | Old Malden, Kingston upon Thames | Kingston upon Thames | London Borough of Kingston upon Thames | Development | 1295 | 346.354 | 948.646 | 0 | 346.354 | 2017-2019 | By April 2021 | 115 | 0 | 115 | 0
Surbiton Stream Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Kingston and Surbiton | Surbiton Stream (Surbiton, Kingston upon Thames) | Kingston upon Thames | Environment Agency | Development | 1557.206 | 557.206 | 1000 | 457.206 | 0 | 2017-2019 | By April 2019 | 235 | 0 | 235 | 0
Worcester Park Surface Water Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Sutton and Cheam | Critical Drainage Area 22 - Worcester Park | Kingston upon Thames | London Borough of Sutton | Development | 2420 | 919.229 | 1500.771 | 0 | 919.229 | 2019-2021 | By April 2021 | 210 | 0 | 210 | 0
Brockwell Park Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Dulwich and West Norwood | Brockwell Park, Herne Hill, Lambeth | Lambeth | London Borough of Lambeth | Construction | 233 | 233 | 0 | 133 | 0 | By April 2017 | By April 2019 | 25 | 0 | 25 | 0
Graveney Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Streatham | Streatham Vale and Norbury Park - SW165EQ | Lambeth | Environment Agency | Development | 5222.68 | 3345.68 | 1877 | 229.6 | 1557 | 2019-2021 | Beyond 2021 | 0 | 0 | 780 | 0
Lewisham and Catford Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Lewisham | Lewisham and Catford on the River Ravensbourne | Lewisham | Environment Agency | Development | 16997.28 | 10464.056 | 6533.224 | 2111.24 | 7366.547 | 2017-2019 | By April 2019 | 195 | 0 | 195 | 0
Quaggy at Hither Green flood alleviation study | London | Thames | Kent, South London and East Sussex | Lewisham East | Hither Green, Lewisham | Lewisham | Environment Agency | Development | 500 | 500 | 0 | 0 | 30 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Houghton Regis Flood Storage Area | East of England | Thames | Hertfordshire and North London | South West Bedfordshire | Houghton Regis to Luton Hoo Lakes | Luton | Environment Agency | Construction | 2576.858 | 2352.414 | 224.444 | 1825 | 97 | By April 2017 | By April 2019 | 245 | 0 | 245 | 0
Barton Road, Great Bramingham Flood Alleviation Scheme | East of England | Thames | Hertfordshire and North London | Luton North | Luton/ Bramingham | Luton | Luton Borough Council | Development | 3065 | 2848 | 217 | 0 | 348 | Beyond 2021 | Beyond 2021 | 0 | 0 | 640 | 0
Marsh Dykes sluice repairs and permenant access works | London | Thames | Kent, South London and East Sussex | Erith and Thamesmead | Marsh Dykes between Woolwich and Erith | Maldon | Environment Agency | Development | 1000 | 1000 | 0 | 1000 | 0 | 2017-2019 | By April 2019 | 450 | 0 | 450 | 0
Cottenham Park Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Wimbledon | Cottenham Park, Merton | Merton | London Borough of Merton | Development | 370 | 320 | 50 | 280 | 0 | 2017-2019 | By April 2019 | 90 | 0 | 90 | 0
East Merton Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Mitcham & Morden | East Merton, Merton | Merton | London Borough of Merton | Development | 276.2068 | 276.2068 | 0 | 0 | 34.674 | 2019-2021 | Beyond 2021 | 0 | 0 | 30 | 0
Seely Road Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Mitcham and Morden | Tooting | Merton | London Borough of Merton | Development | 507.5 | 395 | 112.5 | 225 | 150 | 2017-2019 | By April 2019 | 195 | 0 | 195 | 0
Copthorne Stream Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Mole Valley | Copthorn, Crawley | Mid Sussex | Environment Agency | Development | 450 | 402.032 | 47.968 | 380 | 0 | 2019-2021 | Beyond 2021 | 0 | 0 | 170 | 0
Bookham Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Mole Valley | Great Bookham and Little Bookham | Mole Valley | Surrey County Council | Development | 1290 | 1070.675 | 219.325 | 75 | 995.675 | 2017-2019 | By April 2019 | 265 | 0 | 265 | 0
Wallington Station and South Beddington | London | Thames | Kent, South London and East Sussex | Carshalton and Wallington | CDA 30 (Wallington Station) and CDA 31 (South Beddington) | Mole Valley | London Borough of Sutton | Development | 1820 | 585.293 | 1234.707 | 0 | 585.293 | 2017-2019 | By April 2019 | 75 | 0 | 75 | 0
Leatherhead and Fetcham Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Mole Valley | Fetcham and Leatherhead | Mole Valley | Environment Agency | Development | 1365 | 415 | 950 | 0 | 415 | 2017-2019 | By April 2021 | 115 | 0 | 115 | 0
Dorking Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Mole Valley | Dorking | Mole Valley | Environment Agency | Pipeline | 2735 | 615.708 | 2119.292 | 0 | 215.708 | 2017-2019 | By April 2021 | 0 | 0 | 45 | 0
Withy Brook at Hookwood Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Reigate | Horley, Surrey | Mole Valley | Environment Agency | Pipeline | 980 | 596.366 | 383.634 | 150 | 116.366 | 2019-2021 | By April 2021 | 0 | 0 | 95 | 0
TBAG Drive Equipment - Pilot Trials | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Thames Barrier, Woolwich | Newham | Environment Agency | Construction | 3318.407 | 3318.407 | 0 | 1398.501 | 586.021 | By April 2017 | By April 2019 | 685 | 0 | 685 | 0
TBAG Drive Equipment - FRG Roll out | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Thames Barrier, Woolwich | Newham | Environment Agency | Development | 10422.316 | 10422.316 | 0 | 0 | 4171.749 | 2019-2021 | Beyond 2021 | 860 | 0 | 2150 | 0
TBAG Drive Equipment - RSG pilot | London | Thames | Kent, South London and East Sussex | Greenwich and Woolwich | Thames Barrier, Woolwich | Newham | Environment Agency | Development | 5336.662 | 5336.662 | 0 | 0 | 1716.679 | 2019-2021 | Beyond 2021 | 355 | 0 | 1100 | 0
Kimpton Groundwater Flood Risk Management Options Study Herts CC | East of England | Thames | Hertfordshire and North London | North East Hertfordshire | Kimpton | North Hertfordshire | Hertfordshire County Council | Development | 675.006 | 325.413 | 349.593 | 240.413 | 0 | 2017-2019 | By April 2019 | 150 | 0 | 150 | 0
Boundary Brook Catchment (Florence Park) Flood Alleviation | South East | Thames | Thames | Oxford East | Florence Park, Iffley, Oxford | Oxford | Environment Agency | Development | 459 | 246.65 | 212.35 | 200 | 0 | 2017-2019 | By April 2019 | 75 | 0 | 75 | 0
Oxford Flood Alleviation Scheme | South East | Thames | Thames | Oxford West and Abingdon | Oxford | Oxford | Environment Agency | Development | 144260 | 71930 | 72330 | 5030 | 43960 | 2017-2019 | By April 2021 | 0 | 0 | 1200 | 0
Assessment of Surface Water Flood Risk at Wanstead Flats | London | Thames | Hertfordshire and North London | Leyton and Wanstead | Wanstead Flats (South West part of Redbridge bordering Waltham Forest and Newham) | Redbridge | London Borough of Redbridge | Development | 575 | 74.001 | 500.999 | 0 | 74.001 | 2017-2019 | By April 2021 | 20 | 0 | 20 | 0
Chadwell Heath Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Ilford South | Chadwell Heath, London Borough of Redbridge | Redbridge | London Borough of Redbridge | Development | 200 | 50 | 150 | 25 | 25 | 2017-2019 | By April 2019 | 85 | 0 | 85 | 0
Clayhall Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Ilford North | Clayhall, Ilford | Redbridge | London Borough of Redbridge | Development | 2330.199 | 753.653 | 1576.546 | 100.5 | 602.268 | 2017-2019 | By April 2021 | 220 | 0 | 220 | 0
Woodford Access Improvements - River Roding | East of England | Thames | Hertfordshire and North London | Ilford North | Roding Lane South, Woodford | Redbridge | Environment Agency | Development | 540.016 | 540.016 | 0 | 72.45 | 437.066 | 2017-2019 | By April 2019 | 145 | 0 | 145 | 0
Redhill Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | East Surrey, Reigate | Redhill, Surrey | Reigate and Banstead | Environment Agency | Development | 974.5 | 450 | 524.5 | 0 | 330 | 2017-2019 | By April 2021 | 180 | 0 | 180 | 0
Reigate town centre Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Reigate | Reigate | Reigate and Banstead | Reigate & Banstead Borough Council | Development | 1416.193 | 914.817 | 501.376 | 0 | 914.817 | 2019-2021 | By April 2021 | 65 | 0 | 65 | 0
Burstow Stream at East Horley Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | East Surrey | Horley and Burstow, Surrey | Reigate and Banstead | Environment Agency | Pipeline | 3350 | 1002.788 | 2347.212 | 100 | 672.788 | 2017-2019 | By April 2021 | 0 | 0 | 75 | 0
Mereway Sluice, Twickenham - Gate Replacement | London | Thames | Hertfordshire and North London | Twickenham | Mereway Road, Twickenham, Middlesex, TW2 6RR | Richmond upon Thames | Environment Agency | Development | 853.816 | 853.816 | 0 | 103.5 | 689.816 | 2017-2019 | By April 2019 | 825 | 0 | 825 | 0
Barnes Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Richmond Park | Beverley Brook. Barnes, London | Richmond upon Thames | Environment Agency | Development | 1580 | 1580 | 0 | 300 | 1200 | 2017-2019 | By April 2021 | 380 | 0 | 380 | 0
River Thames Scheme - Community Reslilience Measures | South East | Thames | Thames | Windsor & Maidenhead, Spelthorne, Runnymeade, Elmsbridge, Kingston Upon Thames, Richmond | Lower Thames - Sunbury & Weybridge | Runnymede | Environment Agency | Construction | 12534.821 | 7090 | 5444.821 | 899 | 4691 | By April 2017 | By April 2019 | 380 | 0 | 560 | 0
Lower Thames Guard Piles | South East | Thames | Thames | Various | various | Runnymede | Environment Agency | Construction | 883 | 722.5 | 160.5 | 123.5 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Penton Hook Restoration | South East | Thames | Thames | Runnymede | Chertsey / Staines | Runnymede | Environment Agency | Construction | 8051.299 | 8051.299 | 0 | 730.957 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
River Wey Weir Refurbishment | South East | Thames | Thames | Runnymede | Wey Catchment Tilford to Thames | Runnymede | Environment Agency | Construction | 5378.208 | 5098.522 | 279.686 | 1000 | 2428.991 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Middleton Gardens Flood Alleviation | South East | Thames | Thames | Aldershot | Middleton Gardens, Rushmoor. South of Hawley Lake Stream | Rushmoor | Hampshire County Council | Construction | 285 | 240 | 45 | 0 | 227 | By April 2017 | By April 2019 | 15 | 0 | 15 | 0
Phoenix Green, Flood Alleviation Study | South East | Thames | Thames | North East Hampshire | Phoenix Green, Hampshire | Rushmoor | Hart District Council | Construction | 918 | 748 | 170 | 64.7 | 673.3 | By April 2017 | By April 2019 | 10 | 0 | 10 | 0
Slough Flood Alleviation Scheme | South East | Thames | Thames | Slough | Slough | Slough | Environment Agency | Construction | 1138.023 | 354.186 | 783.837 | 50 | 100 | By April 2017 | By April 2019 | 200 | 0 | 200 | 0
Goring on Thames Flood Risk Management Scheme | South East | Thames | Thames | Henley | Goring on Thames, Oxfordshire | South Oxfordshire | Environment Agency | Development | 385.5 | 126.992 | 258.508 | 76.992 | 0 | 2017-2019 | By April 2019 | 55 | 0 | 55 | 0
Central Camberwell Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Camberwell and Peckham | Camberwell, London Borough of Southwark | Southwark | London Borough of Southwark | Development | 1307 | 1071 | 236 | 0 | 58 | Beyond 2021 | Beyond 2021 | 0 | 0 | 210 | 0
East Camberwell Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Camberwell and Peckham | Camberwell, London Borough of Southwark | Southwark | London Borough of Southwark | Development | 2200 | 517.427 | 1682.573 | 0 | 517.427 | 2017-2019 | By April 2021 | 90 | 0 | 90 | 0
Peckham Rye Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Camberwell and Peckham | Peckham, London Borough of Southwark | Southwark | London Borough of Southwark | Development | 2794 | 2794 | 0 | 100 | 2594 | 2017-2019 | By April 2019 | 255 | 0 | 255 | 0
West Camberwell Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Camberwell and Peckham | Camberwell, London Borough of Southwark | Southwark | London Borough of Southwark | Development | 215 | 215 | 0 | 0 | 50 | Beyond 2021 | Beyond 2021 | 0 | 0 | 55 | 0
River Thames Scheme- Commercial & Procurement Strategy | South East | Thames | Thames | Windsor & Maidenhead, Spelthorne, Runnymeade, Elmsbridge, Kingston Upon Thames, Richmond | Lower Thames - Sunbury & Weybridge | Spelthorne | Environment Agency | Construction | 997 | 997 | 0 | 160 | 557 | By April 2017 | Beyond 2021 | 0 | 0 | 0 | 0
River Thames Scheme- Funding | South East | Thames | Thames | Windsor & Maidenhead, Spelthorne, Runnymeade, Elmsbridge, Kingston Upon Thames, Richmond | Lower Thames - Sunbury & Weybridge | Spelthorne | Environment Agency | Construction | 1358 | 1358 | 0 | 390 | 686 | By April 2017 | Beyond 2021 | 0 | 0 | 0 | 0
River Thames Scheme- Programme Delivery | South East | Thames | Thames | Windsor & Maidenhead, Spelthorne, Runnymeade, Elmsbridge, Kingston Upon Thames, Richmond | Lower Thames - Sunbury & Weybridge | Spelthorne | Environment Agency | Construction | 7293 | 6793 | 500 | 1821 | 3222 | By April 2017 | Beyond 2021 | 0 | 0 | 0 | 0
River Thames Scheme- Property Purchase | South East | Thames | Thames | Windsor & Maidenhead, Spelthorne, Runnymeade, Elmsbridge, Kingston Upon Thames, Richmond | Lower Thames - Sunbury & Weybridge | Spelthorne | Environment Agency | Construction | 1577 | 1577 | 0 | 1500 | 0 | By April 2017 | Beyond 2021 | 0 | 0 | 0 | 0
River Thames Scheme - Capacity Improvements and Flood Channel | South East | Thames | Thames | Windsor & Maidenhead, Spelthorne, Runnymeade, Elmsbridge, Kingston Upon Thames, Richmond | Lower Thames - Sunbury & Weybridge | Spelthorne | Environment Agency | Development | 460782.77 | 117367.038 | 343415.732 | 3351 | 21492.927 | 2019-2021 | Beyond 2021 | 0 | 0 | 12790 | 0
River Ash & Staines Reservoirs Aqueduct | South East | Thames | Hertfordshire and North London | Spelthorne | Staines, Shepperton - River Ash, Colne Brook, County Ditch and Staines Reservoir Aqueduct | Spelthorne | Environment Agency | Development | 1000 | 1000 | 0 | 100 | 805 | 2017-2019 | By April 2021 | 945 | 0 | 945 | 0
London Colney Surface Water and Watercourse Study | East of England | Thames | Hertfordshire and North London | Hertsmere | London Colney Hertfordshire | St Albans | Hertfordshire County Council | Construction | 25 | 25 | 0 | 0 | 25 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Harpenden Flood Alleviation Scheme | West Midlands | Thames | Hertfordshire and North London | Hitchin and Harpenden | Harpenden, Lee | St Albans | Environment Agency | Development | 3325 | 475.895 | 2849.105 | 130 | 295.895 | 2017-2019 | Beyond 2021 | 0 | 0 | 90 | 0
London Colney Flood Risk Study | West Midlands | Thames | Hertfordshire and North London | St. Albans | Salisbury Hall Brook / Colne, Area around Waterside and Lowbell Lane, London Colney, Hertfordshire | St Albans | Environment Agency | Pipeline | 1911.3 | 189.521 | 1721.779 | 30 | 0 | Beyond 2021 | Beyond 2021 | 0 | 0 | 95 | 0
Stevenage Brook Roebuck Gate Combined Flood Risk Assessment | West Midlands | Thames | Hertfordshire and North London | Stevenage | Stevenage, Stevenage Brook | Stevenage | Hertfordshire County Council | Development | 375 | 75 | 300 | 15 | 60 | Beyond 2021 | Beyond 2021 | 0 | 0 | 35 | 0
Bagshot Flood Alleviation Scheme | South East | Thames | Thames | Surrey Heath | Bagshot | Surrey Heath | Environment Agency | Development | 730 | 570.923 | 159.077 | 47.586 | 502.337 | 2017-2019 | By April 2021 | 170 | 0 | 170 | 0
Beddington Park | London | Thames | Kent, South London and East Sussex | Carshalton and Wallington | Beddington Park | Sutton | Environment Agency | Construction | 170 | 110.5 | 59.5 | 0 | 110.5 | By April 2017 | By April 2019 | 200 | 0 | 200 | 0
Covingham & Nythe Flood Alleviation Strategy, Swindon, River Cole, Series of Flood Defence Measures | South West | Thames | Thames | North Swindon | Covingham and Nythe | Swindon | Swindon Borough Council | Development | 550 | 400 | 150 | 175 | 175 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Caterham Bourne Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | Croydon South | Caterham Bourne watercourse, which rises in Caterham, Surrey and flows through whyteleafe, the Kenley and Purley in Croydon | Tandridge | London Borough of Croydon | Development | 1245 | 970 | 275 | 350 | 470 | 2017-2019 | By April 2021 | 210 | 0 | 210 | 0
Caterham Hill Flood Alleviation Scheme | South East | Thames | Kent, South London and East Sussex | East Surrey | Caterham on the Hill | Tandridge | Surrey County Council | Pipeline | 2594 | 481.655 | 2112.345 | 0 | 481.655 | 2019-2021 | By April 2021 | 115 | 0 | 115 | 0
Rickmansworth Combined Flood Risk Study | East of England | Thames | Hertfordshire and North London | South West Hertfordshire | Various sites in Rickmansworth, Hertfordshire | Three Rivers | Hertfordshire County Council | Development | 30 | 30 | 0 | 0 | 30 | 2017-2019 | By April 2021 | 20 | 0 | 20 | 0
Aintree Road, Perivale Surface Water Study | London | Thames | Hertfordshire and North London | Ealing North | Area Around Aintree Road, Perivale | Tunbridge Wells | London Borough of Ealing | Development | 755 | 725 | 30 | 30 | 680 | 2017-2019 | By April 2021 | 135 | 0 | 135 | 0
Stanstead Mountfitchet Flood Alleviation Scheme | East of England | Thames | Hertfordshire and North London | Saffron Walden | Uttlesford, Essex : Ugley Brook | Uttlesford | Environment Agency | Development | 1569.754 | 712.913 | 856.841 | 44 | 628.913 | 2017-2019 | By April 2021 | 50 | 0 | 50 | 0
Abingdon River Ock Flood Storage Area | South East | Thames | Thames | Oxford West and Abingdon | Abingdon, Oxfordshire | Vale of White Horse | Environment Agency | Development | 3654 | 1333 | 2321 | 200 | 730 | 2017-2019 | By April 2019 | 240 | 0 | 240 | 0
Tooting & Earlsfield Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Tooting | Tooting & Earlsfield | Various | London Borough of Wandsworth | Development | 710 | 710 | 0 | 0 | 50 | 2019-2021 | Beyond 2021 | 0 | 0 | 135 | 0
Dagenham Brook Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Walthamstow | Leyton. Dagenham Brook | Waltham Forest | Environment Agency | Development | 5457.7686 | 2157.3996 | 3300.369 | 60.877 | 2021.5226 | 2017-2019 | By April 2021 | 460 | 0 | 460 | 0
Clapham Junction Flood Alleviation Scheme | London | Thames | Kent, South London and East Sussex | Battersea | Clapham Junction | Wandsworth | London Borough of Wandsworth | Development | 950 | 845 | 105 | 300 | 470 | 2019-2021 | By April 2021 | 565 | 0 | 565 | 0
Godalming Flood Alleviation Scheme | South East | Thames | Thames | South West Surrey | Godalming | Waverley | Environment Agency | Development | 2761 | 600 | 2161 | 550 | 0 | 2019-2021 | By April 2021 | 75 | 0 | 75 | 0
Cranleigh Flood Alleviation Scheme | South East | Thames | Thames | Surrey Heath | Cranleigh, Surrey. Cranleigh Waters | Waverley | Surrey County Council | Development | 2535 | 2535 | 0 | 15 | 1520 | Beyond 2021 | Beyond 2021 | 0 | 0 | 485 | 0
Middle Bourne Flood Alleviation Scheme | South East | Thames | Thames | West Surrey | Middle Bourne, Surrey. Middle Bourne and Lower Bourne | Waverley | Surrey County Council | Development | 1035 | 1035 | 0 | 0 | 35 | 2019-2021 | By April 2021 | 0 | 0 | 255 | 0
Newbury & Thatcham Property Level Protection | South East | Thames | Thames | Newbury | Newbury & Thatcham | West Berkshire | West Berkshire Council | Construction | 707.203 | 122 | 585.203 | 0 | 122 | By April 2017 | By April 2019 | 120 | 0 | 120 | 0
West Ilsley | South East | Thames | Thames | Newbury | West Ilsley | West Berkshire | West Berkshire Council | Construction | 282 | 191.941 | 90.059 | 0 | 191.941 | By April 2017 | By April 2019 | 40 | 0 | 40 | 0
Dunstan Park Flood Alleviation Scheme | South East | Thames | Thames | Newbury | Newbury | West Berkshire | West Berkshire Council | Construction | 1946.9994 | 855.8565 | 1091.1429 | 656.283 | 0 | By April 2017 | By April 2019 | 185 | 0 | 185 | 0
Waller Drive, Newbury - PLP Scheme - Main scheme | South East | Thames | Thames | Newbury | Newbury | West Berkshire | West Berkshire Council | Construction | 201 | 112.135 | 88.865 | 80.135 | 0 | By April 2017 | By April 2019 | 30 | 0 | 30 | 0
Great Shefford Flood Mitigation | South East | Thames | Thames | Newbury | Great Shefford - Berkshire | West Berkshire | Environment Agency | Development | 315 | 157.5 | 157.5 | 55 | 88 | 2017-2019 | Beyond 2021 | 20 | 0 | 20 | 0
Pangbourne Flood Alleviation | South East | Thames | Thames | Reading West | Pangbourne | West Berkshire | Environment Agency | Development | 187 | 101.94 | 85.06 | 0 | 67.94 | 2017-2019 | By April 2021 | 25 | 0 | 25 | 0
Boxford Flood Alleviation Scheme | South East | Thames | Thames | Newbury | Boxford | West Berkshire | West Berkshire Council | Development | 585.5 | 156.9644 | 428.5356 | 0 | 5 | 2017-2019 | By April 2019 | 0 | 0 | 25 | 0
Grazeley Green Flood Alleviation Scheme | South East | Thames | Thames | Wokingham | Grazeley Green | West Berkshire | West Berkshire Council | Development | 474 | 82 | 392 | 0 | 7 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Hampstead Norreys | South East | Thames | Thames | Newbury | Hampstead Norreys, West Berkshire | West Berkshire | West Berkshire Council | Development | 122.75 | 43.186 | 79.564 | 0 | 43.186 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Paddle Rymer Package 2 | South East | Thames | Thames | Various | Thames RFDC | West Oxfordshire | Environment Agency | Construction | 4367.778 | 4367.778 | 0 | 15.474 | 5.274 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Paddle and Rymer H and S | South East | Thames | Thames | West Oxfordshire | N/A | West Oxfordshire | Environment Agency | Construction | 8097.014 | 8097.014 | 0 | 4 | 1.2 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Westminster North West Strategy | London | Thames | Hertfordshire and North London | Westminster North | Westminster | Westminster | London Borough of Westminster | Development | 4944 | 3203 | 1741 | 0 | 1203 | 2019-2021 | By April 2021 | 0 | 0 | 395 | 0
Churchill Gardens flood alleviation scheme | London | Thames | Hertfordshire and North London | Cities of London and Westminster | Chuchill Gardens, Pimlico, City of Westminster, London | Westminster | London Borough of Westminster | Development | 2040 | 281 | 1759 | 100 | 141 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Westmoreland Terrace Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Cities of London and Westminster | Westmoreland Terrace, Pimlico, London | Westminster | London Borough of Westminster | Development | 975 | 975 | 0 | 50 | 900 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Bisham - Flood Alleviation | South East | Thames | Thames | Maidenhead | Bisham | Windsor and Maidenhead | Environment Agency | Development | 825.275 | 462.848 | 362.427 | 0 | 230 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Twyford Flood Mitigation | South East | Thames | Thames | Maidenhead | Twyford, Reading | Wokingham | Environment Agency | Development | 153 | 50.4 | 102.6 | 0 | 50.4 | 2017-2019 | By April 2021 | 25 | 0 | 25 | 0
River Loddon Soft Engineering | South East | Thames | Thames | Wokingham | River Loddon at Winnersh | Wokingham | Environment Agency | Pipeline | 169 | 169 | 0 | 0 | 19 | 2017-2019 | By April 2019 | 0 | 0 | 110 | 0
Marlow Flood Alleviation Scheme | South East | Thames | Thames | Wycombe | Marlow | Wycombe | Environment Agency | Construction | 7406.418 | 2609.602 | 4796.816 | 600 | 0 | By April 2017 | By April 2019 | 285 | 0 | 285 | 0
Sands (High Wycombe) Surface Water Flood Risk Management | South East | Thames | Thames | Wycombe | Sands, High Wycombe | Wycombe | Buckinghamshire County Council | Construction | 255 | 57.3 | 197.7 | 57.3 | 0 | By April 2017 | By April 2019 | 20 | 0 | 20 | 0
Marlow Surface Water Drainage Pre-Feasibility Study | South East | Thames | Thames | Buckingham | Marlow, Buckinghamshire | Wycombe | Buckinghamshire County Council | Construction | 1050 | 614.25 | 435.75 | 0 | 303.8 | By April 2017 | Beyond 2021 | 100 | 0 | 100 | 0
Hughenden Road and Coates Lane, High Wycombe Surface Water Management Scheme | South East | Thames | Thames | Wycombe | Hughenden Road and Coates Lane, High Wycombe | Wycombe | Buckinghamshire County Council | Development | 40 | 14.158 | 25.842 | 14.158 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Spondon Sluices Decommissioning, Derby | East Midlands | Trent | East Midlands | Derby South | River Derwent, Spondon | Amber Valley | Environment Agency | Construction | 1034.985 | 908.985 | 126 | 0 | 550 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Lower Tame - Whitacre Heath, Tamworth and Fazeley Flood Risk Management Scheme | Yorkshire & the Humber | Trent | West Midlands | Tamworth Constituency | West Midlands | Barnsley | Environment Agency | Construction | 15640.201 | 15640.201 | 0 | 95 | 90 | By April 2017 | By April 2019 | 240 | 0 | 1670 | 0
Isle of Axholme, West Stockwith Pumping Station Improvements | East Midlands | Trent | East Midlands | Bassetlaw | West Stockwith | Bassetlaw | Environment Agency | Development | 3235.091 | 3235.091 | 0 | 2200 | 523 | 2017-2019 | By April 2019 | 360 | 0 | 360 | 0
Heckdyke, 3 Bridges and 4 Bridges Pumping Station Refurbishment, Nottinghamshire | East Midlands | Trent | East Midlands | Brigg and Goole | Heckdyke, Doncaster | Bassetlaw | Isle of Axholme and North Nottinghamshire Water Level Management Board | Development | 250 | 65 | 185 | 0 | 65 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Retford Beck, Grove Lane and Blackstope Lane Flood Mitigation Scheme, Retford, Nottinghamshire | East Midlands | Trent | East Midlands | Bassetlaw | Retford, Retford Beck | Bassetlaw | Bassetlaw District Council | Development | 989 | 464 | 525 | 0 | 93 | 2019-2021 | Beyond 2021 | 0 | 0 | 110 | 0
Smeath Lane Culvert Replacement Scheme, Clarborough, Nottinghamshire | East Midlands | Trent | East Midlands | Bassetlaw | Clarborough, Bassetlaw District, Notts | Bassetlaw | Bassetlaw District Council | Development | 336 | 119 | 217 | 0 | 119 | 2019-2021 | By April 2021 | 25 | 0 | 25 | 0
Selly Park North (River Rea) Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Birmingham, Hall Green | River Rea, Birmingham | Birmingham | Environment Agency | Construction | 5964.2 | 1022.2 | 4942 | 50 | 0 | By April 2017 | By April 2019 | 125 | 0 | 125 | 0
Selly Park South (River Rea) Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Birmingham, Hall Green | River Rea, Birmingham | Birmingham | Environment Agency | Construction | 2388.908 | 1072 | 1316.908 | 50 | 0 | By April 2017 | By April 2019 | 245 | 0 | 245 | 0
Middle Tame, Perry Barr and Witton, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Birmingham Perry Barr Constituency | River Tame Catchment, Witton, Birmingham | Birmingham | Environment Agency | Construction | 26831.9 | 24767.1 | 2064.8 | 8500 | 4300 | By April 2017 | By April 2019 | 715 | 0 | 715 | 0
Fisher Close Community Protection | West Midlands | Trent | West Midlands | Birmingham, Edgbaston | Frankley, Birmingham | Birmingham | Birmingham City Council | Development | 40 | 35 | 5 | 0 | 35 | 2019-2021 | By April 2021 | 15 | 0 | 15 | 0
River Tame, Bromford, Birmingham, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Birmingham, Hodge Hill . | River Tame Catchment, Bromford, Birmingham | Birmingham | Environment Agency | Development | 14110 | 11410 | 2700 | 1100 | 9850 | 2017-2019 | By April 2021 | 840 | 0 | 840 | 0
Cosby Flood Alleviation Scheme, Leicestershire | East Midlands | Trent | East Midlands | South Leicestershire | Cosby, Leicestershire | Blaby | Environment Agency | Development | 547 | 547 | 0 | 0 | 35 | Beyond 2021 | Beyond 2021 | 0 | 0 | 75 | 0
Rising Brook, Rugeley, Town Centre Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Cannock Chase ituency | Rugeley, Staffordshire | Cannock Chase | Environment Agency | Construction | 3193.107 | 2173.107 | 1020 | 90 | 125 | By April 2017 | By April 2019 | 115 | 0 | 115 | 0
Loughborough Flood Risk Management Scheme, Leicestershire | East Midlands | Trent | East Midlands | Charnwood | Loughborough, Tributaries of the River Soar | Charnwood | Environment Agency | Development | 2271.2024 | 2289.756 | -18.5536 | 1011.234 | 1011.234 | 2017-2019 | By April 2021 | 430 | 0 | 430 | 0
Swithland Brook Flood Alleviation Scheme, Leicestershire | East Midlands | Trent | East Midlands | Charnwood | Swithland Brook , Swithland | Charnwood | Leicestershire County Council | Development | 170 | 70 | 100 | 0 | 70 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Cotton Brook (Upper) Culvert Renewal, Peartree Road Area, Derby | East Midlands | Trent | East Midlands | Derby South | Cotton Brook, Derby | Derby | Derby City Council | Development | 1585.628 | 1435.43 | 150.198 | 1216.055 | 90 | 2017-2019 | By April 2019 | 175 | 0 | 175 | 0
Cuttle Brook Flood Alleviation Scheme, Derby | East Midlands | Trent | East Midlands | Derby South | Cuttle Brook, Derby | Derby | Derby City Council | Development | 551.7228 | 376.2658 | 175.457 | 0 | 376.2658 | 2019-2021 | Beyond 2021 | 110 | 0 | 110 | 0
Isle of Axholme, Waterton Farm Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Don Valley | Isle of Axholme Flood Risk Management Strategy | Doncaster | Environment Agency | Development | 132.6 | 60 | 72.6 | 23.5 | 35 | 2017-2019 | By April 2021 | 35 | 0 | 35 | 0
Isle of Axholme, Goodcop Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | Doncaster | Environment Agency | Development | 597 | 115 | 482 | 43 | 72 | 2019-2021 | Beyond 2021 | 20 | 0 | 20 | 0
River Torne Tributaries Flood Alleviation Study, Rossington, Doncaster | Yorkshire & the Humber | Trent | East Midlands | Doncaster Central | Doncaster | Doncaster | Doncaster Borough Council | Development | 145.3 | 135.3 | 10 | 0 | 135.3 | 2019-2021 | By April 2021 | 45 | 0 | 45 | 0
Isle of Axholme, River Idle Asset Improvements | Yorkshire & the Humber | Trent | East Midlands | Bassetlaw | Isle of Axholme Flood Risk Management Strategy | Doncaster | Environment Agency | Pipeline | 36 | 36 | 0 | 0 | 7.2 | 2019-2021 | Beyond 2021 | 0 | 0 | 15 | 0
Marchington Brook, Marchington, Uttoxeter, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Burton ituency | Marchington | East Staffordshire | Staffordshire County Council | Construction | 220.92 | 216.952 | 3.968 | 160 | 0 | By April 2017 | By April 2019 | 30 | 0 | 30 | 0
Burton Upon Trent Phase 2 Flood Risk Management Scheme | West Midlands | Trent | West Midlands | Burton | Burton Upon Trent Capital Maintenance Scheme | East Staffordshire | Environment Agency | Development | 16700 | 16700 | 0 | 2065 | 14635 | 2019-2021 | By April 2021 | 3360 | 0 | 3360 | 0
Branston Culvert Replacement Scheme | West Midlands | Trent | West Midlands | Burton | Burton Upon Trent | East Staffordshire | Environment Agency | Development | 400 | 400 | 0 | 50 | 350 | Beyond 2021 | Beyond 2021 | 95 | 0 | 95 | 0
Our City Our River - Derby Flood Risk Management Scheme | East Midlands | Trent | East Midlands | Derby North Borough Council and Derby South Borough Council | River Derwent | Erewash | Derby City Council | Construction | 86266.68 | 11668.341 | 74598.339 | 2000 | 888.196 | By April 2017 | Beyond 2021 | 1485 | 0 | 1540 | 0
Breaston Flood Alleviation Scheme, Derbyshire | East Midlands | Trent | East Midlands | Erewash | Breaston, Derbyshire | Erewash | Environment Agency | Development | 295 | 295 | 0 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 65 | 0
Dam Brook Flood Alleviation Scheme, Breadsall, Derbyshire | East Midlands | Trent | East Midlands | Mid Derbyshire | Breadsall, Dam Brook and Boosemoor Brook | Erewash | Derbyshire County Council | Development | 83 | 25 | 58 | 1 | 17 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Ock Brook Flood Alleviation Study, Ockbrook, Derbsyhire, | East Midlands | Trent | East Midlands | Mid Derbyshire | Ockbrook, Ock Brook | Erewash | Derbyshire County Council | Development | 83 | 38.5 | 44.5 | 8.5 | 26 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Titchfield Park Brook Surface Water Scheme, Hucknall, Nottinghamshire | East Midlands | Trent | East Midlands | Sherwood | Hucknall, Titchfield Park Brook | Erewash | Nottinghamshire County Council | Development | 500 | 375 | 125 | 0 | 375 | 2017-2019 | By April 2019 | 90 | 0 | 90 | 0
Broughton Astley Flood Alleviation Scheme, Harborough, Leicestershire | East Midlands | Trent | East Midlands | Harborough | Broughton Astely, Harborough | Harborough | Leicestershire County Council | Development | 50 | 40 | 10 | 0 | 40 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Shardlow Pumping Station Improvements, Derbyshire | East Midlands | Trent | East Midlands | South Derbyshire | Shardlow , Shardlow Dyke | Hinckley and Bosworth | Environment Agency | Development | 610 | 610 | 0 | 40 | 530 | 2017-2019 | By April 2021 | 90 | 0 | 90 | 0
Leicester Flood Risk Management Scheme - conveyance works | East Midlands | Trent | East Midlands | Leicester East | Leicester | Leicester | Environment Agency | Construction | 7819.441 | 7119.441 | 700 | 2432 | 275 | By April 2017 | By April 2019 | 2010 | 0 | 2010 | 0
Leicester Northfields Flood Alleviation Scheme | East Midlands | Trent | East Midlands | Leicester East | Leicester | Leicester | Leicester City Council | Construction | 435 | 435 | 0 | 0 | 435 | By April 2017 | By April 2019 | 85 | 0 | 85 | 0
Braunstone Brook Flood Alleviation Scheme, Leicester | East Midlands | Trent | East Midlands | Leicester West | Braunstone, Leicester, Braunstone Brook | Leicester | Environment Agency | Development | 3195 | 3195 | 0 | 225 | 2905 | 2017-2019 | By April 2021 | 750 | 0 | 750 | 0
Leicester Royal Infirmary Surface Water Flood Alleviation Scheme | East Midlands | Trent | East Midlands | Leicester South | Areas around the LRI to the South of the City of Leicester to the east of the River Soar | Leicester | Leicester City Council | Development | 100 | 57 | 43 | 0 | 4 | 2019-2021 | By April 2021 | 0 | 0 | 5 | 0
Leicester, Egginton Street Surface Water Flood Alleviation Scheme | East Midlands | Trent | East Midlands | Leicester East | Areas around Eggington Street to the East of the City of Leicester to the east of the River Soar | Leicester | Leicester City Council | Development | 150 | 150 | 0 | 0 | 90 | 2019-2021 | Beyond 2021 | 0 | 0 | 15 | 0
Leicester, Oakland Road Surface Water Flood Alleviation Scheme | East Midlands | Trent | East Midlands | Leicester South | Areas around Oakland Road to the South of the City of Leicester to the east of the River Soar | Leicester | Leicester City Council | Development | 250 | 220 | 30 | 0 | 16 | 2017-2019 | By April 2021 | 0 | 0 | 40 | 0
Leicester, Redhill Way Surface Water Flood Alleviation Scheme | East Midlands | Trent | East Midlands | Leicester West | Areas around Redhill Way to the North of the City of Leicester to the west of the River Soar | Leicester | Leicester City Council | Development | 250 | 246 | 4 | 0 | 20 | 2017-2019 | By April 2021 | 0 | 0 | 25 | 0
River Soar Flood Risk Management Scheme, Leicester | East Midlands | Trent | East Midlands | Leicester South | Leicester, Leicestershire | Leicester | Environment Agency | Development | 9156 | 6906 | 2250 | 528 | 6278 | 2017-2019 | By April 2021 | 1660 | 0 | 1660 | 0
Saffron Brook Flood Alleviation Scheme, Leicester | East Midlands | Trent | East Midlands | Leicester South | Aylestone, Leicester, Saffron Brook | Leicester | Environment Agency | Development | 6116 | 6116 | 0 | 456 | 5560 | 2017-2019 | By April 2021 | 695 | 0 | 695 | 0
Willow Brook Flood Alleviation Scheme, Leicester | East Midlands | Trent | East Midlands | Leicester East | Belgrave, Leicester, Willow Brook | Leicester | Environment Agency | Development | 11352 | 10352 | 1000 | 416 | 9836 | 2017-2019 | By April 2021 | 1705 | 0 | 1705 | 0
River Soar Tributaries: Natural Flood Management Scheme, Leicestershire | East Midlands | Trent | East Midlands | Leicester East | Leicestershire, River Soar Tributaries | Leicester | Environment Agency | Pipeline | 626 | 626 | 0 | 153 | 463 | 2017-2019 | By April 2021 | 35 | 0 | 35 | 0
Hamstall Ridware Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Lichfield | Hamstall Ridware | Lichfield | Staffordshire County Council | Development | 75.3 | 37.8 | 37.5 | 0 | 5 | 2019-2021 | By April 2021 | 0 | 0 | 10 | 0
Marsh Lane, Lichfield, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Lichfield | Lichfield, Marsh Lane | Lichfield | Staffordshire County Council | Development | 54.6 | 27 | 27.6 | 0 | 27 | Beyond 2021 | Beyond 2021 | 4 | 0 | 4 | 0
Cocker Beck Flood Alleviation Scheme, Lowdham, Nottinghamshire | East Midlands | Trent | East Midlands | Newark | Lowdham, Nottinghamshire, Cocker Beck | Newark and Sherwood | Environment Agency | Development | 3751.666 | 1451.666 | 2300 | 750 | 570 | 2017-2019 | By April 2019 | 225 | 0 | 225 | 0
Gunthorpe, River Trent Flood Defence Scheme, Nottinghamshire | East Midlands | Trent | East Midlands | Newark | Gunthorpe, Nottinghamshire | Newark and Sherwood | Environment Agency | Development | 1200 | 593 | 607 | 0 | 33 | 2019-2021 | By April 2021 | 0 | 0 | 80 | 0
Lowfield Drain, Lowfield Pumping Station Refurbishment, Nottinghamshire | East Midlands | Trent | East Midlands | Newark | Balderton, Newark | Newark and Sherwood | Trent Valley IDB | Development | 106 | 90 | 16 | 90 | 0 | 2017-2019 | By April 2019 | 55 | 0 | 55 | 0
Southwell Flood Alleviation Scheme, Nottinghamshire | East Midlands | Trent | East Midlands | Newark | Southwell, Potwell Dyke, Halam Hill Watercourse | Newark and Sherwood | Nottinghamshire County Council | Development | 1675 | 720 | 955 | 0 | 720 | 2017-2019 | By April 2019 | 235 | 0 | 235 | 0
Ferry Drain, South Street Pumping Refurbishment, North Lincolnshire | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Epworth, Doncaster | North Lincolnshire | Isle of Axholme and North Nottinghamshire Water Level Management Board | Construction | 399 | 144 | 255 | 133 | 0 | By April 2017 | By April 2019 | 65 | 0 | 65 | 0
Isle of Axholme, Keadby Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole, Doncaster North, Don Valley, Doncaster Central, Bassetlaw | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Development | 39275.515 | 39275.515 | 0 | 2630 | 34302 | 2017-2019 | By April 2021 | 3125 | 0 | 3125 | 0
Isle of Axholme, Tunnel Pits Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Development | 841 | 222.7 | 618.3 | 23.5 | 156 | 2019-2021 | Beyond 2021 | 15 | 0 | 15 | 0
Isle of Axholme, Dirtness Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Development | 311.5 | 9.5 | 302 | 8 | 0 | 2019-2021 | Beyond 2021 | 0 | 0 | 95 | 0
Isle of Axholme, Woodcarr Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Development | 121 | 94.5 | 26.5 | 9.5 | 60 | Beyond 2021 | Beyond 2021 | 80 | 0 | 80 | 0
Isle of Axholme, Candy Farm Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole and Don Valley | Isle of Axholme | North Lincolnshire | Environment Agency | Development | 1185.01 | 510 | 675.01 | 33.5 | 233 | 2019-2021 | Beyond 2021 | 0 | 0 | 90 | 0
Isle of Axholme, Low Bank Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Development | 296.5 | 120 | 176.5 | 41.5 | 77 | 2019-2021 | Beyond 2021 | 85 | 0 | 170 | 0
Isle of Axholme, Bull Hassocks Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Development | 231 | 114.5 | 116.5 | 3.5 | 86 | 2017-2019 | By April 2021 | 75 | 0 | 75 | 0
Isle of Axholme, Snow Sewer Pumping Station Improvements | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Development | 387 | 47 | 340 | 0 | 47 | 2017-2019 | By April 2021 | 0 | 0 | 150 | 0
Keadby Warping Drain Outfall Improvements, North Lincolnshire | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | River Trent, Keadby | North Lincolnshire | Environment Agency | Development | 350 | 350 | 0 | 40 | 250 | 2019-2021 | Beyond 2021 | 0 | 0 | 80 | 0
Isle of Axholme, North Soak Syphon Automatic Weedscreen | Yorkshire & the Humber | Trent | East Midlands | Brigg and Goole | Isle of Axholme Flood Risk Management Strategy | North Lincolnshire | Environment Agency | Pipeline | 246 | 246 | 0 | 36 | 0 | 2019-2021 | By April 2021 | 0 | 0 | 5 | 0
Polesworth,Tamworth, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | North Warwickshire | Polesworth | North Warwickshire | Warwickshire County Council | Development | 60 | 60 | 0 | 0 | 12 | Beyond 2021 | Beyond 2021 | 0 | 0 | 20 | 0
Long Whatton and Diseworth Flood Alleviation Scheme, Leicestershire | East Midlands | Trent | East Midlands | North West Leicestershire | Long Whatton and Diseworth, North West Leicestershire on the Long Whatton and Diseworth Brook | North West Leicestershire | Leicestershire County Council | Development | 130 | 110 | 20 | 0 | 110 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
Nottingham Trent Left Bank Flood Alleviation Scheme | East Midlands | Trent | East Midlands | Long Eaton, Broxtowe, Nottingham South & Gedling | Nottingham, River Trent | Nottingham | Environment Agency | Construction | 6978.4358 | 6978.4358 | 0 | 207.3729 | 602.1188 | By April 2017 | By April 2019 | 0 | 0 | 16380 | 0
Day Brook Flood Alleviation Scheme, Old Basford, Nottingham | East Midlands | Trent | East Midlands | Nottingham North | Old Basford, Nottingham | Nottingham | Environment Agency | Development | 2350 | 1020 | 1330 | 0 | 231.108 | 2019-2021 | By April 2021 | 0 | 0 | 230 | 0
Mapperley Park Surface Water Management Scheme, Nottingham | East Midlands | Trent | East Midlands | Nottingham East | Mapperley Park, Nottingham | Nottingham | Nottingham City Council | Development | 970 | 820 | 150 | 0 | 780 | 2019-2021 | By April 2021 | 175 | 0 | 175 | 0
Tottle Brook Flood Alleviation Scheme, Nottingham | East Midlands | Trent | East Midlands | Nottingham North | Wollaton, Nottingham | Nottingham | Nottingham City Council | Development | 799 | 357 | 442 | 0 | 30 | Beyond 2021 | Beyond 2021 | 0 | 0 | 50 | 0
Nuneaton Flood Relief Channel Refurbishment | West Midlands | Trent | West Midlands | Nuneaton | Nuneaton | Nuneaton and Bedworth | Environment Agency | Development | 450 | 450 | 0 | 50 | 400 | 2017-2019 | By April 2019 | 570 | 0 | 570 | 0
Kelverley Grove flood defence repairs | West Midlands | Trent | West Midlands | West Bromwich East | West Bromwich | Sandwell | Environment Agency | Construction | 192 | 192 | 0 | 3 | 6 | By April 2017 | By April 2019 | 140 | 0 | 140 | 0
Upper Tame, Sandwell, Titford Culvert, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Warley Constituency | River Tame Catchment, Oldbury, Birmingham | Sandwell | Environment Agency | Construction | 295.311 | 295.311 | 0 | 5 | 10 | By April 2017 | By April 2019 | 0 | 0 | 145 | 0
Collins Road Sheet Pile Refurbishment | West Midlands | Trent | West Midlands | West Bromwich East | Wednesbury, West Bromwich | Sandwell | Environment Agency | Development | 200 | 125 | 75 | 0 | 125 | 2017-2019 | By April 2019 | 60 | 0 | 60 | 0
Thimblemill Brook, Smethwick, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Warley | Smethwick, West Midlands | Sandwell | Sandwell Borough Council | Development | 815.085 | 750 | 65.085 | 700 | 0 | 2017-2019 | By April 2019 | 255 | 0 | 255 | 0
Dickens Heath balancing pond improvement works | West Midlands | Trent | West Midlands | Solihull | On the south edge of Dickens Heath, off Rumbush Brook which is a tributary of the Mount Brook | Solihull | Solihull Borough Council | Development | 230 | 98 | 132 | 0 | 78 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Lower Dove Flood Alleviation Scheme | East Midlands | Trent | West Midlands | South Derbyshire | Scropton to the Trent. Derbyshire/Staffordshire | South Derbyshire | Environment Agency | Construction | 7683.231 | 7674.831 | 8.4 | 12 | 24 | By April 2017 | By April 2019 | 0 | 0 | 1620 | 0
Foston Brook Flood Alleviation Study, Scropton, Derbyshire, | East Midlands | Trent | East Midlands | South Derbyshire | Foston Brook, Scropton | South Derbyshire | Derbyshire County Council | Development | 146 | 79 | 67 | 79 | 0 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Perton, Surface Water Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Staffordshire | Perton, Staffordshire | South Staffordshire | Staffordshire County Council | Construction | 194.1 | 150 | 44.1 | 108 | 0 | By April 2017 | By April 2019 | 220 | 0 | 220 | 0
Lower Penn Flood Alleviation Scheme | West Midlands | Trent | West Midlands | South Staffordshire | Lower Penn, near Smestow Brook | South Staffordshire | Staffordshire County Council | Development | 90 | 36.2 | 53.8 | 0 | 2 | 2019-2021 | By April 2021 | 0 | 0 | 5 | 0
Dunston, River Penk, Property Level Resilience Scheme | North West | Trent | West Midlands | Staffordshire | Dunston | South Staffordshire | Staffordshire County Council | Development | 23 | 8 | 15 | 0 | 8 | 2017-2019 | By April 2021 | 3 | 0 | 3 | 0
Hobnock Road Property Level Resilience | West Midlands | Trent | West Midlands | South Staffordshire | Essington | South Staffordshire | Staffordshire County Council | Development | 15 | 12 | 3 | 12 | 0 | 2017-2019 | By April 2019 | 3 | 0 | 3 | 0
Norton Lane Property Level Resilience | West Midlands | Trent | West Midlands | South Staffordshire | Great Wyrley | South Staffordshire | Staffordshire County Council | Development | 15 | 12 | 3 | 12 | 0 | 2017-2019 | By April 2019 | 3 | 0 | 3 | 0
Huntington, Cannock, Surface Water Flood Alleviation Scheme | West Midlands | Trent | West Midlands | South Staffordshire | Huntingdon, South Staffs | Stafford | Staffordshire County Council | Construction | 200.28 | 180 | 20.28 | 152.5 | 0 | By April 2017 | By April 2019 | 30 | 0 | 30 | 0
Rising Brook Flood Alleviation Scheme , Rising Brook, Stafford | West Midlands | Trent | West Midlands | Stafford | Stafford, Rising Brook | Stafford | Environment Agency | Development | 826 | 278.16 | 547.84 | 20 | 228.16 | 2019-2021 | By April 2021 | 35 | 0 | 35 | 0
Brown Edge Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Staffordshire Moorlands | Brown Edge, Staffordshire Moorlands | Staffordshire Moorlands | Staffordshire County Council | Development | 94 | 90 | 4 | 0 | 90 | 2019-2021 | By April 2021 | 25 | 0 | 25 | 0
Village Brook (Endon) Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Staffordshire Moorlands | Village Brook , Endon | Staffordshire Moorlands | Staffordshire County Council | Development | 172 | 172 | 0 | 150 | 0 | 2017-2019 | By April 2019 | 60 | 0 | 60 | 0
Fowlea Brook, Stoke on Trent, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Stoke-on-Trent Central | Stoke-on-Trent | Stoke-on-Trent | Environment Agency | Development | 1943.538 | 1778.538 | 165 | 421 | 1184 | 2017-2019 | By April 2019 | 360 | 0 | 360 | 0
Old Ford Brook, Walsall, Culvert Recondition Works | West Midlands | Trent | West Midlands | Walsall South | Tower Street, Walsall | Walsall | Walsall Borough Council | Development | 400 | 200 | 200 | 25 | 175 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Sewer Drain, Torksey Pumping Station Replacement, Lincolnshire | East Midlands | Trent | East Midlands | Gainsborough | Torksey, Lincoln | West Lindsey | Trent Valley IDB | Construction | 749 | 500 | 249 | 237 | 127 | By April 2017 | By April 2019 | 480 | 0 | 480 | 0
Jenny Hurn Drain, Jenny Hurn Pumping Station Refurbishment, Lincolnshire | East Midlands | Trent | East Midlands | Gainsborough | Wildsworth, Gainsborough | West Lindsey | Scunthorpe and Gainsborough Water Management Board | Development | 260 | 79 | 181 | 0 | 79 | 2019-2021 | By April 2021 | 85 | 0 | 85 | 0
Jenny Hurn Drain, Whoofer Pumping Station Refurbishment, Lincolnshire | East Midlands | Trent | East Midlands | Gainsborough | Wildsworth, Gainsborough | West Lindsey | Scunthorpe and Gainsborough Water Management Board | Development | 67 | 10 | 57 | 0 | 10 | 2019-2021 | By April 2021 | 5 | 0 | 5 | 0
Marton Pumping Station Refurbishment, Gainsborough | East Midlands | Trent | East Midlands | Gainsborough | Marton , Gainsborough | West Lindsey | Trent Valley IDB | Development | 412 | 305 | 107 | 0 | 305 | 2019-2021 | By April 2021 | 55 | 0 | 55 | 0
South Ings Drain, Susworth Pumping Station Refurbishment, Lincolnshire | East Midlands | Trent | East Midlands | Gainsborough | Susworth, Scunthorpe | West Lindsey | Scunthorpe and Gainsborough Water Management Board | Development | 150 | 42 | 108 | 0 | 42 | 2019-2021 | By April 2021 | 45 | 0 | 45 | 0
Tidal Trent, Torksey Gate Automation Improvements, Lincolnshire | East Midlands | Trent | East Midlands | Gainsborough | Tidal Trent Flood Risk Management Strategy | West Lindsey | Environment Agency | Development | 200 | 200 | 0 | 26 | 164 | 2017-2019 | By April 2019 | 100 | 0 | 100 | 0
Weston Coyney, Stoke-on-Trent, Surface Water Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Stoke-on-Trent, South | Stoke-on-Trent | Wrexham | Stoke-on-Trent City Council | Development | 615 | 550 | 65 | 250 | 250 | 2017-2019 | By April 2021 | 115 | 0 | 115 | 0
Bath Flood Defence Scheme | South West | Wessex | Wessex | Bath | Bath Flood Defence Scheme | Bath and North East Somerset | Environment Agency | Development | 49050 | 12000 | 37050 | 0 | 3000 | 2019-2021 | Beyond 2021 | 0 | 0 | 1120 | 0
Bristol Avon Boat Ramps Improvements | South West | Wessex | Wessex | TBC | Bristol Avon Catchment | Bath and North East Somerset | Environment Agency | Pipeline | 200 | 200 | 0 | 50 | 150 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Bournemouth Beach Management Phase 1 | South West | Wessex | Wessex | Bournemouth East & Bournemouth West | Bournemouth, Dorset | Bournemouth | Bournemouth Borough Council | Construction | 17081.733 | 14481.733 | 2600 | 2942.5 | 1500 | By April 2017 | By April 2021 | 0 | 1595 | 0 | 1595
Bournemouth Beach Management Phase 2 | South West | Wessex | Wessex | Bournemouth East & Bournemouth West | Bournemouth, Dorset | Bournemouth | Bournemouth Borough Council | Development | 13766.366 | 11117 | 2649.366 | 0 | 6390 | 2019-2021 | Beyond 2021 | 0 | 655 | 0 | 1115
Avonmouth Severnside Enterprise Area (ASEA) Ecology Mitigation and Flood Defence Project | South West | Wessex | Wessex | Bristol North West | Avonmouth (Bristol) Severnside (South Glos) | Bristol, City of | Environment Agency | Development | 76955 | 10299 | 66656 | 70 | 67 | 2019-2021 | Beyond 2021 | 0 | 0 | 3595 | 0
Longmoor Tunnel Refurbishment | South West | Wessex | Wessex | Bristol South | Bristol | Bristol, City of | Environment Agency | Development | 487 | 487 | 0 | 87 | 300 | 2017-2019 | By April 2021 | 75 | 0 | 75 | 0
Dalby Avenue Trash Screen Improvements | South West | Wessex | Wessex | Various | Bristol | Bristol, City of | Environment Agency | Development | 60 | 60 | 0 | 0 | 60 | 2019-2021 | By April 2021 | 20 | 0 | 20 | 0
Brislington Flood Defence Scheme Improvements | South West | Wessex | Wessex | Bristol South | Brislington, Bristol. | Bristol, City of | Environment Agency | Development | 1330 | 297 | 1033 | 85 | 177 | 2019-2021 | By April 2021 | 65 | 0 | 65 | 0
Christchurch Priory Quay | South West | Wessex | Wessex | Christchurch | Christchurch Harbour, Christchurch, Dorset. | Christchurch | Environment Agency | Development | 211.365 | 157.98 | 53.385 | 27.5 | 122.48 | 2019-2021 | By April 2021 | 40 | 0 | 40 | 0
Christchurch Willow Way / Riverside | South West | Wessex | Wessex | Christchurch | Christchurch Harbour, Christchurch, Dorset. | Christchurch | Environment Agency | Development | 411.251 | 211.87 | 199.381 | 27.5 | 175.37 | 2019-2021 | By April 2021 | 35 | 0 | 35 | 0
Wimborne Flood Defence Scheme Improvements | South West | Wessex | Wessex | Mid Dorset and North Poole | Wimborne, Dorset | East Dorset | Environment Agency | Development | 380 | 106 | 274 | 66 | 0 | 2017-2019 | By April 2019 | 100 | 0 | 100 | 0
Flights Hole Weir Fish Pass Improvements | South West | Wessex | Wessex | Somerton and Frome | Baltonsborough / River Brue, Somerset | Mendip | Environment Agency | Development | 675.6 | 644.6 | 31 | 416.6 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Congresbury Yeo Tidal Banks | South West | Wessex | Wessex | Weston-Super-Mare | Congresbury Yeo Tidal Banks (Tutshill to Wick) | North Somerset | Environment Agency | Construction | 3880.82 | 3880.82 | 0 | 5 | 15 | By April 2017 | By April 2019 | 4100 | 0 | 4100 | 0
Weston Bay beach recycling | South West | Wessex | Wessex | Weston-Super-Mare | Weston-super-Mare, Knightstone to Uphill | North Somerset | North Somerset Council | Development | 100 | 75 | 25 | 15 | 45 | 2017-2019 | By April 2021 | 1115 | 0 | 1115 | 0
Hucker's Bow Replacement | South West | Wessex | Wessex | North Somerset | Woodspring Bay, Wick St Lawrence, North Somerset | North Somerset | Environment Agency | Development | 492.3 | 392.3 | 100 | 233 | 8 | 2017-2019 | By April 2019 | 125 | 0 | 125 | 0
Land Yeo Lower & Blind Yeo Asset Improvements | South West | Wessex | Wessex | North Somerset | Blind Yeo Outfall Clevedon North Somerset | North Somerset | Environment Agency | Development | 1045 | 703 | 342 | 90 | 548 | 2019-2021 | By April 2021 | 100 | 0 | 100 | 0
Wessex Property Level Protection | South West | Wessex | Wessex | Various | Various sites in Wessex patch | not possible | Environment Agency | Construction | 4322.31 | 2110.655 | 2211.655 | 230 | 243.545 | By April 2017 | By April 2019 | 370 | 0 | 500 | 0
Wessex Property Level Protection Phase 2 | South West | Wessex | Wessex | Various | Various sites in Wessex patch | not possible | Environment Agency | Development | 5000 | 2500 | 2500 | 100 | 2400 | 2017-2019 | Beyond 2021 | 360 | 0 | 500 | 0
Central Poole Flood Defences | South West | Wessex | Wessex | Poole | Poole Town Centre, Dorset | Poole | Borough of Poole | Construction | 720 | 720 | 0 | 0 | 188 | By April 2017 | By April 2021 | 30 | 0 | 75 | 0
Poole Dolphin Haven Works | South West | Wessex | Wessex | Poole | Poole, Dorset | Poole | Environment Agency | Construction | 2006 | 806 | 1200 | 230 | 0 | By April 2017 | By April 2019 | 95 | 0 | 95 | 0
Holes Bay SPA Restoration | South West | Wessex | Wessex | Poole | Poole Harbour SPA/SSSI | Poole | Borough of Poole | Development | 450 | 285 | 165 | 90 | 105 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Fleetsbridge & Hatch Pond Poole Flood Attenuation | South West | Wessex | Wessex | Poole | Fleetsbridge & Hatch Pond, Poole, Dorset | Poole | Borough of Poole | Development | 1020 | 610 | 410 | 20 | 590 | 2017-2019 | By April 2021 | 140 | 0 | 140 | 0
Sterte Pumping Station | South West | Wessex | Wessex | Poole | Sterte, Poole | Poole | Borough of Poole | Development | 412 | 412 | 0 | 412 | 0 | 2017-2019 | By April 2019 | 210 | 0 | 210 | 0
Creekmoor Flood Defences | South West | Wessex | Wessex | Poole | Creekmoor, Poole, Dorset | Poole | Borough of Poole | Development | 500 | 290 | 210 | 290 | 0 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Swanage Reservoir 1 Section 10 Bank Slippage | South West | Wessex | Wessex | South Dorset | Swanage, Dorset | Purbeck | Environment Agency | Construction | 220 | 220 | 0 | 7 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Wareham Coastal Change | South West | Wessex | Wessex | Mid Dorset and North Poole & South Dorset | Wareham, Dorset | Purbeck | Environment Agency | Development | 18647 | 17466 | 1181 | 605 | 4158 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Lower Axe Urban Drainage Improvements - Brent Knoll and East Brent | South West | Wessex | Wessex | Wells | East Brent, Somerset | Sedgemoor | Axe Brue IDB | Construction | 130 | 75 | 55 | 50 | 0 | By April 2017 | By April 2019 | 15 | 0 | 15 | 0
Cannington Flood Defence Scheme | South West | Wessex | Wessex | Bridgwater and West Somerset | Cannington, Somerset | Sedgemoor | Environment Agency | Construction | 3871 | 994 | 2877 | 0 | 15 | By April 2017 | By April 2019 | 115 | 0 | 115 | 0
Parrett Estuary - Cannington Bends | South West | Wessex | Wessex | Somerton and Frome | River Parrett between Bridgwater and Combwich, Somerset | Sedgemoor | Environment Agency | Development | 2593.43 | 1944.715 | 648.715 | 1495 | 0 | 2017-2019 | By April 2019 | 460 | 0 | 460 | 0
Bridgwater Tidal Barrier | South West | Wessex | Wessex | Bridgwater and West Somerset | Chilton Tinity, Bridgwater, Somerset | Sedgemoor | Environment Agency | Development | 53720 | 25036 | 28684 | 30 | 90 | Beyond 2021 | Beyond 2021 | 0 | 0 | 8400 | 0
Dunball Sluice Gates Refurbishment | South West | Wessex | Wessex | Bridgwater and West Somerset | Dunball sluice, Kings Sedgemoor Drain, Somerset | Sedgemoor | Environment Agency | Development | 258.75 | 207 | 51.75 | 207 | 0 | 2017-2019 | By April 2019 | 130 | 0 | 130 | 0
Yate Chipping Sodbury Defence Improvements | South West | Wessex | Wessex | Thornbury and Yate | River Frome, Yate, Bristol | South Gloucestershire | Environment Agency | Development | 2695 | 466 | 2229 | 140 | 321 | 2019-2021 | By April 2021 | 130 | 0 | 130 | 0
Westmoor & Southmoor Asset Improvements | South West | Wessex | Wessex | Somerton and Frome | Midelney Pumping Station, Somerset | South Somerset | Environment Agency | Development | 114.75 | 91.8 | 22.95 | 60 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Henley Sluice / Lower River Cary | South West | Wessex | Wessex | Somerton and Frome | Somerton, Somerset | South Somerset | Environment Agency | Development | 750 | 750 | 0 | 0 | 715 | 2017-2019 | By April 2019 | 2 | 0 | 2 | 0
Currymoor Pumping Station Improvements | South West | Wessex | Wessex | Bridgwater and West Somerset | Currymoor pumping station, River Tone, Somerset | Taunton Deane | Environment Agency | Construction | 396.885 | 305.82 | 91.065 | 105 | 0 | By April 2017 | By April 2019 | 75 | 0 | 75 | 0
West Sedgemoor Pumping Station Improvements | South West | Wessex | Wessex | Bridgwater and West Somerset | West Sedgemoor pumping station, River Parrett, Somerset | Taunton Deane | Environment Agency | Development | 296.925 | 166.275 | 130.65 | 166.275 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
French Weir Remedials, River Tone | South West | Wessex | Wessex | Taunton Deane | River Tone, Taunton, Somerset | Taunton Deane | Environment Agency | Pipeline | 345.186 | 345.186 | 0 | 236.6 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
West Bay Coast Protection Works Beach Management Plan (BMP + Works) 2017/18 onwards | South West | Wessex | Wessex | West Dorset | West Bay, Dorset | West Dorset | West Dorset District Council | Development | 402 | 402 | 0 | 56 | 178 | 2017-2019 | Beyond 2021 | 210 | 70 | 365 | 125
Lyme Regis Coast Protection Works Beach Management Plan (BMP & Works) 2017/18 onwards | South West | Wessex | Wessex | West Dorset | Lyme Regis, Dorset | West Dorset | West Dorset District Council | Development | 330 | 330 | 0 | 60 | 135 | 2017-2019 | Beyond 2021 | 0 | 85 | 0 | 135
Haywards Yard Flood Wall Repair | South West | Wessex | Wessex | West Dorset | Haywards Yard, Bridport, Dorset | West Dorset | Environment Agency | Development | 151 | 151 | 0 | 70 | 5 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
West Bay Coastal Improvements | South West | Wessex | Wessex | West Dorset | West Bay, near Bridport, Dorset | West Dorset | Environment Agency | Development | 2375 | 1285 | 1090 | 450 | 600 | 2017-2019 | By April 2019 | 255 | 0 | 255 | 0
Bridport | South West | Wessex | Wessex | West Dorset | Bridport Dorset. | West Dorset | Environment Agency | Development | 569.765 | 168.13 | 401.635 | 70 | 98.13 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Dorchester Flood Defence Scheme Improvements | South West | Wessex | Wessex | West Dorset | Dorchester, Dorset. | West Dorset | Environment Agency | Development | 1010 | 138 | 872 | 0 | 138 | 2019-2021 | By April 2021 | 65 | 0 | 65 | 0
Steart Coastal Management Project | South West | Wessex | Wessex | Bridgwater and West Somerset | Steart, Somerset | West Somerset | Environment Agency | Construction | 20837.5 | 20837.5 | 0 | 42 | 63.5 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Minehead Urban Drainage Improvements | South West | Wessex | Wessex | Bridgwater and West Somerset | Minehead, Somerset | West Somerset | Parrett IDB | Development | 200 | 100 | 100 | 75 | 0 | 2017-2019 | By April 2019 | 180 | 0 | 180 | 0
Williton Flood Defence Scheme | South West | Wessex | Wessex | Bridgwater and West Somerset | Williton, West Somerset. | West Somerset | Environment Agency | Development | 2644.439 | 1098 | 1546.439 | 120 | 858 | 2017-2019 | By April 2021 | 240 | 0 | 240 | 0
Weymouth Bay Coastal Defences Phase 1 - BMP & Works | South West | Wessex | Wessex | South Dorset & West Dorset | Weymouth | Weymouth and Portland | Weymouth & Portland Borough Council | Development | 1183 | 1123 | 60 | 0 | 51 | 2017-2019 | By April 2019 | 270 | 0 | 740 | 0
Weymouth Harbour Tidal Defence Scheme Phase 1a - raising harbour walls Commercial Rd & Westham Bridge | South West | Wessex | Wessex | South Dorset & West Dorset | Weymouth Harbour | Weymouth and Portland | Weymouth & Portland Borough Council | Development | 35900 | 6460 | 29440 | 0 | 1560 | 2017-2019 | Beyond 2021 | 0 | 0 | 595 | 0
Downton Pumping Station Infiltration Repairs | South West | Wessex | Wessex | Salisbury | Downton | Wiltshire | Environment Agency | Construction | 180.7 | 180.7 | 0 | 2 | 0 | By April 2017 | By April 2019 | 0 | 0 | 0 | 0
Bradford -on-Avon Flood Defence Scheme | South West | Wessex | Wessex | Chippenham | Bradford -on-Avon, Wiltshire. Bristol Avon. | Wiltshire | Environment Agency | Development | 366.73 | 131.73 | 235 | 61.73 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Tisbury Asset Improvements | South West | Wessex | Wessex | Salisbury | Tisbury, Wiltshire | Wiltshire | Environment Agency | Development | 122.93 | 61.465 | 61.465 | 0 | 61.465 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Chitterne Attenuation of Surface Water | South West | Wessex | Wessex | Salisbury | Chitterne, Wiltshire | Wiltshire | Wiltshire Council | Development | 135 | 45 | 90 | 0 | 45 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Orcheston Surface Water Attenuation (minor works) | South West | Wessex | Wessex | Salisbury | Orcheston, Wiltshire | Wiltshire | Wiltshire Council | Development | 70 | 20 | 50 | 20 | 0 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Salisbury City Centre Flood Alleviation Scheme | South West | Wessex | Wessex | Weston-Super-Mare | Salisbury, Wiltshire | Wiltshire | Environment Agency | Development | 4983.3532 | 3757 | 1226.3532 | 90 | 3400 | 2017-2019 | By April 2021 | 585 | 0 | 585 | 0
Wilton Wylye Flood Bank | South West | Wessex | Wessex | Salisbury | Wilton River Avon SSSI | Wiltshire | Environment Agency | Development | 210 | 31 | 179 | 26 | 0 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Hemingfield - Tingle Bridge | Yorkshire & the Humber | Yorkshire | Yorkshire | Barnsley East | Barnsley | Barnsley | Barnsley Borough Council | Development | 15 | 3.45 | 11.55 | 0 | 3.45 | 2017-2019 | By April 2019 | 3 | 0 | 3 | 0
Wombwell Ings Flood Storage Scheme, Darfield, Barnsley | Yorkshire & the Humber | Yorkshire | Yorkshire | Barnsley East | Barnsley | Barnsley | Barnsley Borough Council | Development | 810.081 | 213 | 597.081 | 213 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Renishaw Flood Alleviation Scheme | East Midlands | Yorkshire | Yorkshire | North East Derbyshire | Renishaw | Bolsover | Derbyshire County Council | Development | 1477.1299 | 1317.6724 | 159.4575 | 800 | 500 | 2017-2019 | By April 2021 | 135 | 0 | 135 | 0
Keighley and Stockbridge Flood Alleviation | Yorkshire & the Humber | Yorkshire | Yorkshire | Keighley | Keighly & Stockbridge, Bradford | Bradford | Bradford City Council | Development | 3010 | 3010 | 0 | 3000 | 0 | 2017-2019 | By April 2019 | 690 | 0 | 690 | 0
Keighley Replacement of "Ski Jump", Aireworth Road | Yorkshire & the Humber | Yorkshire | Yorkshire | Keighley | Keighley, River Worth | Bradford | Environment Agency | Development | 101 | 101 | 0 | 100 | 0 | 2017-2019 | By April 2019 | 125 | 0 | 125 | 0
Skipton Road | Yorkshire & the Humber | Yorkshire | Yorkshire | Keighley | Skipton Road, Keighley | Bradford | Bradford City Council | Development | 300 | 300 | 0 | 300 | 0 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Calderdale Flood Action Plan Implementation | Yorkshire & the Humber | Yorkshire | Yorkshire | Calder Valley | Mytholmroyd, Calderdale | Calderdale | Environment Agency | Construction | 54835 | 12082 | 42753 | 4500 | 2550 | By April 2017 | By April 2021 | 1375 | 0 | 1760 | 0
Avenue Flood Balancing Reservoir, Chesterfield | East Midlands | Yorkshire | Yorkshire | Chesterfield | River Rother, Chesterfield | Chesterfield | Environment Agency | Construction | 2506.36 | 1821.5554 | 684.8046 | 26.25 | 0 | By April 2017 | By April 2019 | 90 | 0 | 90 | 0
Skipton Coach Street Culvert - ECI | Yorkshire & the Humber | Yorkshire | Yorkshire | Skipton and Ripon | Skipton, Eller-Embsay Beck | Craven | Environment Agency | Development | 110 | 110 | 0 | 10 | 100 | 2019-2021 | By April 2021 | 125 | 0 | 125 | 0
Bentley PS Replacement | Yorkshire & the Humber | Yorkshire | Yorkshire | Doncaster North | Bentley, North Swaith Dike | Doncaster | Environment Agency | Development | 4272.413 | 1517.413 | 2755 | 1100 | 20 | 2017-2019 | By April 2019 | 500 | 0 | 500 | 0
Dearne Washlands Optimisation | Yorkshire & the Humber | Yorkshire | Yorkshire | Doncaster North | Bolton Upon Dearne, River Dearne | Doncaster | Environment Agency | Development | 300 | 300 | 0 | 0 | 300 | 2019-2021 | By April 2021 | 190 | 0 | 190 | 0
Kearsley Brook Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Don Valley | Conisbrough, Doncaster | Doncaster | Doncaster Borough Council | Development | 218.5 | 165 | 53.5 | 150 | 0 | 2017-2019 | By April 2019 | 35 | 0 | 35 | 0
Mile Thorne Bank Refurbishment | Yorkshire & the Humber | Yorkshire | Yorkshire | Doncaster Central | Doncaster, River Don | Doncaster | Environment Agency | Development | 3077.029 | 3077.029 | 0 | 0 | 100 | Beyond 2021 | Beyond 2021 | 0 | 0 | 265 | 0
Skellow Rail Bridge Parapet Raising | Yorkshire & the Humber | Yorkshire | Yorkshire | Doncaster North | Skellow, The Skell | Doncaster | Environment Agency | Development | 262.286 | 262.286 | 0 | 162.5 | 0 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Stainforth Dunston Hill Bridge Bank Refurbishment | Yorkshire & the Humber | Yorkshire | Yorkshire | Doncaster North | Stainforth, River Don | Doncaster | Environment Agency | Development | 1700 | 1700 | 0 | 1400 | 300 | 2017-2019 | By April 2019 | 715 | 0 | 715 | 0
Anlaby and East Ella Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | Anlaby | East Riding of Yorkshire | East Riding of Yorkshire Council | Construction | 22390.213 | 16472.7542 | 5917.4588 | 1890 | 12803.519 | By April 2017 | By April 2021 | 1765 | 0 | 1765 | 0
Hull and Holderness Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Humber Estuary | East Riding of Yorkshire | East Riding of Yorkshire Council | Construction | 6056.004 | 2127 | 3929.004 | 823.004 | 0 | By April 2017 | By April 2019 | 610 | 0 | 610 | 0
Mill Beck Reservoir Works, Market Weighton | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Market Weighton, Mill Beck Reservoir | East Riding of Yorkshire | Environment Agency | Construction | 2860.248 | 2860.248 | 0 | 5 | 0 | By April 2017 | By April 2019 | 0 | 0 | 65 | 0
Aldbrough Seaside Road | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Aldbrough | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 35 | 25 | 10 | 25 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Beeford Village Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Beeford | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 300 | 200 | 100 | 200 | 0 | 2017-2019 | By April 2019 | 160 | 0 | 160 | 0
Beverley Model Farm Drain | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Beverley | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 250 | 250 | 0 | 0 | 100 | 2019-2021 | Beyond 2021 | 0 | 0 | 265 | 0
Beverley Victoria Road Culvert Reinstatement | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Beverley | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 100 | 90 | 10 | 90 | 0 | 2017-2019 | By April 2019 | 90 | 0 | 90 | 0
Bubwith Culvert Connection | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | Bubwith | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 20 | 10 | 10 | 10 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Burnby Culvert Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Hayton | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 60 | 40 | 20 | 40 | 0 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Causeway Dale Weel | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Causeway Dale Weel | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 7 | 7 | 0 | 7 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Cherry Burton The Meadows | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Cherry Burton | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 230 | 90 | 140 | 0 | 90 | 2017-2019 | By April 2019 | 140 | 0 | 140 | 0
Constable Drain North Frodingham | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Constable Drain North Frodingham | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 10 | 10 | 0 | 10 | 0 | 2017-2019 | By April 2019 | 2 | 0 | 2 | 0
Cottingham and Orchard Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | Cottingham | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 22132.31 | 17024.6229 | 5107.6871 | 311.828 | 15925.172 | 2017-2019 | By April 2019 | 1930 | 0 | 1930 | 0
Cross Drain Leven | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Cross Drain Leven | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 10 | 10 | 0 | 10 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Driffield Kellythorpe Groundwater Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Driffield | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 80 | 70 | 10 | 70 | 0 | 2017-2019 | By April 2019 | 90 | 0 | 90 | 0
Firth Drain Leven | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Firth Drain Leven | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 10 | 10 | 0 | 10 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Flamborough Hartendale Gutter Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Flamborough | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 20 | 20 | 0 | 20 | 0 | 2017-2019 | By April 2019 | 20 | 0 | 20 | 0
Fox Drain Tributary Dunswell | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Fox Drain Tributary Dunswell | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 8 | 8 | 0 | 0 | 8 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Hards Covert Burton Agnes | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Hards Covert Burton Agnes | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 6 | 6 | 0 | 0 | 6 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
Hempholme and Wilfholme Pumping Station Refurb and Ownership Transfer | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Hull | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 1200 | 360 | 840 | 300 | 0 | 2017-2019 | By April 2019 | 85 | 0 | 85 | 0
Hessle Tidal Defences | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Hessle Foreshore between the Humber Bridge and Fleet Drain at Hessle Haven. Defences to be built along Cliff Road, Redcliff Road and Livingstone Road. | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 7839 | 5839 | 2000 | 218.919 | 1532.431 | 2019-2021 | By April 2021 | 4500 | 0 | 4500 | 0
Hornsea Mere Water Level and Quality Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Hornsea | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 460 | 400 | 60 | 350 | 0 | 2017-2019 | By April 2019 | 230 | 0 | 230 | 0
Howden East Drainage Improvements | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | Howden | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 40 | 40 | 0 | 40 | 0 | 2017-2019 | By April 2019 | 40 | 0 | 40 | 0
Hull Road East Drain Woodmansey | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Hull Road East Drain Woodmansey | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 6 | 6 | 0 | 6 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Hull Road West Drain Woodmansey | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Hull Road West Drain Woodmansey | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 6 | 6 | 0 | 6 | 0 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Humber: Estuary-wide Monitoring | Yorkshire & the Humber | Yorkshire | Yorkshire | Brigg and Goole | Humber Estuary | East Riding of Yorkshire | Environment Agency | Development | 2928.505 | 2928.505 | 0 | 200 | 450 | 2019-2021 | Beyond 2021 | 0 | 0 | 0 | 0
Humber: Goole Fields to Crowle | Yorkshire & the Humber | Yorkshire | Yorkshire | Brigg and Goole | Old Goole, Swinefleet Village, Swinefleet to Reedness | East Riding of Yorkshire | Environment Agency | Development | 6050 | 6050 | 0 | 0 | 1050 | 2019-2021 | Beyond 2021 | 0 | 0 | 940 | 0
Humber: Skeffling Land Purchase and Managed Realignment | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Skeffling, River Humber | East Riding of Yorkshire | Environment Agency | Development | 16587.936 | 16587.936 | 0 | 822 | 11897.32 | 2017-2019 | By April 2021 | 0 | 0 | 0 | 0
Keyingham North Culvert Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Keyingham | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 150 | 70 | 80 | 10 | 60 | 2017-2019 | By April 2019 | 120 | 0 | 120 | 0
Kilham Village Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Kilham | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 150 | 114 | 36 | 114 | 0 | 2017-2019 | By April 2019 | 215 | 0 | 215 | 0
Langtoft Village Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Langtoft | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 150 | 50 | 100 | 0 | 50 | 2019-2021 | By April 2021 | 65 | 0 | 65 | 0
Lockington Village Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Lockington | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 100 | 25 | 75 | 25 | 0 | 2017-2019 | By April 2019 | 65 | 0 | 65 | 0
Middleton on the Wolds Culverting Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Middleton | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 120 | 100 | 20 | 0 | 100 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Mill Dam Beck Brandesburton | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Mill Dam Beck Brandesburton | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 15 | 15 | 0 | 0 | 15 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Molescroft Sister Beck Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Molescroft | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 220 | 190 | 30 | 0 | 190 | 2019-2021 | By April 2021 | 190 | 0 | 190 | 0
North Bullock Arram | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | North Bullock Arram | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 15 | 15 | 0 | 15 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
North Cave New Cut to Wetlands | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | North Cave | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 75 | 25 | 50 | 0 | 25 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
North Ferriby Church Street | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | North Ferriby | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 110 | 80 | 30 | 80 | 0 | 2017-2019 | By April 2019 | 80 | 0 | 80 | 0
Nunburnholme Watercourse Improvements | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Nunburnholme | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 30 | 30 | 0 | 0 | 30 | 2019-2021 | Beyond 2021 | 30 | 0 | 30 | 0
Parting Dike Eske | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Parting Dike Eske | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 7 | 7 | 0 | 0 | 7 | 2019-2021 | By April 2021 | 3 | 0 | 3 | 0
Patrington Haven Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Patrington | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 80 | 50 | 30 | 0 | 50 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
Pocklington Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Pocklington | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 4523.001 | 1025.001 | 3498 | 927 | 0 | 2017-2019 | By April 2019 | 135 | 0 | 135 | 0
Rawcliffe DB Pumping Stations Refurbishment & Other Works (3502) | Yorkshire & the Humber | Yorkshire | Yorkshire | Brigg and Goole | Rawcliffe (River Aire and River Don) | East Riding of Yorkshire | Rawcliffe IDB | Development | 833.584 | 435.9644 | 397.6196 | 0 | 66.9571 | Beyond 2021 | Beyond 2021 | 55 | 0 | 395 | 0
Rotsea Drain Hempholme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Rotsea Drain Hempholme | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 10 | 10 | 0 | 10 | 0 | 2017-2019 | By April 2019 | 3 | 0 | 3 | 0
South Cave Village Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | South Cave | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 800 | 600 | 200 | 500 | 0 | 2017-2019 | By April 2019 | 410 | 0 | 410 | 0
Swinefleet Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Brigg and Goole | Swinefleet | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 50 | 10 | 40 | 10 | 0 | 2017-2019 | By April 2019 | 25 | 0 | 25 | 0
Swinemoor North Tickton | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Swinemoor North Tickton | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 10 | 10 | 0 | 10 | 0 | 2017-2019 | By April 2019 | 10 | 0 | 10 | 0
Upper and Middle Hull Embankment Repairs | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Beverley, River Hull | East Riding of Yorkshire | Environment Agency | Development | 2000 | 2000 | 0 | 125 | 625 | 2019-2021 | Beyond 2021 | 0 | 0 | 2690 | 0
Western Drain Woodmansey | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Western Drain Woodmansey | East Riding of Yorkshire | Beverley & North Holderness IDB | Development | 10 | 10 | 0 | 10 | 0 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Wilberfoss Flood Attenuation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Wilberfoss | East Riding of Yorkshire | East Riding of Yorkshire Council | Development | 40 | 20 | 20 | 20 | 0 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
Downstream Paull - Thorngumbald Clough [SoN] | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | South Pasture, Thorngumbald Road, Paull | East Riding of Yorkshire | Environment Agency | Pipeline | 2923.26 | 2919.26 | 4 | 2377 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Dunswell Embankment Improvements | Yorkshire & the Humber | Yorkshire | Yorkshire | Haltemprice and Howden | Hull | East Riding of Yorkshire | East Riding of Yorkshire Council | Pipeline | 5200 | 1040 | 4160 | 40 | 0 | 2019-2021 | By April 2021 | 0 | 0 | 240 | 0
Hull and Holderness Flood Alleviation Scheme P2 (Inland) | Yorkshire & the Humber | Yorkshire | Yorkshire | Beverley and Holderness | Humber Estuary | East Riding of Yorkshire | East Riding of Yorkshire Council | Pipeline | 25256 | 25256 | 0 | 817 | 0 | 2019-2021 | Beyond 2021 | 0 | 0 | 2295 | 0
Humber: Estuary Erosion Protection (HEEP) Works 2 | Yorkshire & the Humber | Yorkshire | Yorkshire | Brigg and Goole | Humber Estuary | East Riding of Yorkshire | Environment Agency | Pipeline | 3047.538 | 3047.538 | 0 | 1595.08 | 1181.4 | 2017-2019 | Beyond 2021 | 800 | 0 | 800 | 0
Main Foss (053) Channel Improvements Ainsty 2008 IDB | Yorkshire & the Humber | Yorkshire | Yorkshire | York Outer | Willowgarth,Poppleton York | Harrogate | Ainsty (2008) IDB | Development | 35 | 18 | 17 | 18 | 0 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Hull River Defences | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull North | Hull | Kingston upon Hull, City of | Environment Agency | Construction | 25146.502 | 25146.502 | 0 | 8282.612 | 11587.747 | By April 2017 | By April 2021 | 3960 | 0 | 3960 | 0
Bund alongside Old Fleet Drain close to Annandale Road, Kingston upon Hull - Design & Construction | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull East | Kingston upon Hull, Old Fleet Drain. | Kingston upon Hull, City of | Hull City Council | Development | 590 | 590 | 0 | 30 | 560 | 2019-2021 | By April 2021 | 295 | 0 | 295 | 0
Holderness Drain Flood Alleviation Scheme (including East Hull and Gt Culvert PS) | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull East | East Hull | Kingston upon Hull, City of | Environment Agency | Development | 15112.594 | 8372.594 | 6740 | 750 | 4260 | 2017-2019 | By April 2021 | 1100 | 0 | 1100 | 0
Hull Tidal Surge Barrier - Reconfiguration | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull West and Hessle | Hull | Kingston upon Hull, City of | Environment Agency | Development | 5800 | 4640 | 1160 | 160 | 4400 | 2017-2019 | By April 2021 | 600 | 0 | 600 | 0
Humber: Hull frontage | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull North | Hull | Kingston upon Hull, City of | Environment Agency | Development | 29369.188 | 29369.188 | 0 | 1250 | 26500 | 2017-2019 | By April 2021 | 24795 | 0 | 24795 | 0
Newland Flood Alleviaiton Scheme - Sustainable Drainage retrofit | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull North | Kingston upon Hull, Newland | Kingston upon Hull, City of | Hull City Council | Development | 2534 | 2534 | 0 | 40 | 1298.8 | Beyond 2021 | Beyond 2021 | 260 | 0 | 1295 | 0
Old Main Drain Wawne 2 | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Old Main Drain Wawne | Kingston upon Hull, City of | Beverley & North Holderness IDB | Development | 15 | 15 | 0 | 0 | 15 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Riston Pumping Station | Yorkshire & the Humber | Yorkshire | Yorkshire | East Yorkshire | Arnold & Riston Drain near the White Cross Roundabout Leven | Kingston upon Hull, City of | Beverley & North Holderness IDB | Development | 32 | 32 | 0 | 0 | 32 | 2019-2021 | By April 2021 | 0 | 0 | 0 | 0
River Hull Channel/Conveyance Improvements | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull North | Hull | Kingston upon Hull, City of | East Riding of Yorkshire Council | Development | 870 | 175 | 695 | 175 | 0 | 2017-2019 | By April 2019 | 30 | 0 | 30 | 0
River Hull Natural Flood Management | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull North | Hull | Kingston upon Hull, City of | Hull City Council | Development | 372 | 372 | 0 | 100 | 200 | 2017-2019 | By April 2019 | 55 | 0 | 55 | 0
Sutton Ings Flood Alleviation Scheme - Sustainable Drainage retrofit | Yorkshire & the Humber | Yorkshire | Yorkshire | Kingston upon Hull East | Kingston upon Hull, Sutton Ings | Kingston upon Hull, City of | Hull City Council | Development | 3510 | 3510 | 0 | 40 | 2294 | 2019-2021 | By April 2021 | 410 | 0 | 2055 | 0
Kirklees Culvert Programme | Yorkshire & the Humber | Yorkshire | Yorkshire | Various | Various - locations across Kirklees LLFA | Kirklees | Kirklees Borough Council | Construction | 2035.1 | 1420.9333 | 614.1667 | 207.65 | 458.8 | By April 2017 | Beyond 2021 | 270 | 0 | 270 | 0
Batley Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Batley and Spen | Batley, Kirklees, West Yorkshire | Kirklees | Kirklees Borough Council | Development | 1808.6 | 1788.6 | 20 | 50 | 250 | 2017-2019 | By April 2021 | 315 | 0 | 315 | 0
Grimscar Dyke Culverts Repairs | Yorkshire & the Humber | Yorkshire | Yorkshire | Huddersfield | Huddersfield, Grimscar Dyke | Kirklees | Environment Agency | Development | 175 | 175 | 0 | 175 | 0 | 2017-2019 | By April 2019 | 110 | 0 | 110 | 0
Huddersfield A62 Corridor Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Dewsbury | A62 Corridor, north-east Huddersfield, Kirklees, West Yorkshire | Kirklees | Kirklees Borough Council | Development | 1330.101 | 1200.1008 | 130.0002 | 540 | 540 | 2017-2019 | By April 2019 | 455 | 0 | 455 | 0
Priority Clusters #2 (Holmfirth/Meltham/Thongsbridge) | Yorkshire & the Humber | Yorkshire | Yorkshire | Colne Valley | Kirklees, West Yorkshire | Kirklees | Kirklees Borough Council | Development | 700 | 700 | 0 | 100 | 200 | 2017-2019 | By April 2019 | 415 | 0 | 415 | 0
Ravensthorpe and Mirfield Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Dewsbury | Ravensthorpe, Kirklees, West Yorkshire | Kirklees | Kirklees Borough Council | Development | 2855 | 1830 | 1025 | 100 | 1700 | 2017-2019 | By April 2021 | 940 | 0 | 940 | 0
Lower Mickletown Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Elmet and Rothwell | Mickletown, Leeds. River Aire | Leeds | Leeds City Council | Development | 1100 | 275 | 825 | 0 | 275 | 2019-2021 | Beyond 2021 | 0 | 0 | 300 | 0
Lowther Penstock / Outfall replacement & barrier bank Refurbishment | Yorkshire & the Humber | Yorkshire | Yorkshire | Elmet and Rothwell | Allerton Bywater, River Aire | Leeds | Environment Agency | Development | 220 | 220 | 0 | 0 | 20 | Beyond 2021 | Beyond 2021 | 0 | 0 | 0 | 0
Mickletown Pit Lane Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Elmet and Rothwell | Mickletown, Leeds. River Aire | Leeds | Leeds City Council | Development | 400 | 125 | 275 | 125 | 0 | 2017-2019 | By April 2019 | 55 | 0 | 55 | 0
Potternewton Surface Water Flood Alleviation Scheme, Leeds. | Yorkshire & the Humber | Yorkshire | Yorkshire | Leeds North East | Potternewton, Leeds. Unamed Watercourse | Leeds | Leeds City Council | Development | 250 | 174 | 76 | 0 | 174 | 2019-2021 | By April 2021 | 0 | 0 | 35 | 0
St Aiden's Reforming banks | Yorkshire & the Humber | Yorkshire | Yorkshire | Elmet and Rothwell | Mickletown, River Aire | Leeds | Environment Agency | Development | 220 | 220 | 0 | 0 | 220 | 2019-2021 | By April 2021 | 145 | 0 | 145 | 0
Thorner Beck Flood Alleviation Scheme, Thorner, Leeds | Yorkshire & the Humber | Yorkshire | Yorkshire | Leeds North East | Thorner, Leeds. Thorner Beck | Leeds | Leeds City Council | Development | 150 | 96 | 54 | 0 | 96 | 2019-2021 | Beyond 2021 | 0 | 0 | 15 | 0
Wyke Beck Improvements, Leeds | Yorkshire & the Humber | Yorkshire | Yorkshire | Leeds East | East Leeds. Wyke Beck | Leeds | Leeds City Council | Development | 1330.998 | 560 | 770.998 | 0 | 560 | 2017-2019 | By April 2021 | 220 | 0 | 220 | 0
Leeds Flood Alleviation Scheme Phase 2 | Yorkshire & the Humber | Yorkshire | Yorkshire | Leeds Central | Leeds River Aire | Leeds | Leeds City Council | Pipeline | 64900 | 4900 | 60000 | 1400 | 3000 | 2017-2019 | Beyond 2021 | 0 | 0 | 200 | 0
Otley Flood Alleviation Scheme Leeds Metropolitan Borough | Yorkshire & the Humber | Yorkshire | Yorkshire | Leeds North West | River Wharfe, Otley | Leeds | Leeds City Council | Pipeline | 1950 | 1950 | 0 | 300 | 1650 | 2017-2019 | By April 2021 | 55 | 0 | 55 | 0
River Wiske Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Richmond (Yorks) | River Wiske | Richmondshire | North Yorkshire County Council | Development | 1817.2 | 1687.2 | 130 | 0 | 50 | Beyond 2021 | Beyond 2021 | 0 | 0 | 190 | 0
Stokesley & Great Ayton Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Richmond (Yorks) | Stokesley & Great Ayton | Richmondshire | North Yorkshire County Council | Development | 679.84 | 615.84 | 64 | 0 | 123.168 | Beyond 2021 | Beyond 2021 | 0 | 0 | 70 | 0
Swale Upland & Catterick Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Richmond (Yorks) | Swale Upland & Catterick | Richmondshire | North Yorkshire County Council | Development | 1884.592 | 1694.592 | 190 | 0 | 1694.592 | Beyond 2021 | Beyond 2021 | 240 | 0 | 240 | 0
Swale Washlands West Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Richmond (Yorks) | Swale Washlands West | Richmondshire | North Yorkshire County Council | Development | 605.696 | 525.696 | 80 | 0 | 331.56 | 2019-2021 | Beyond 2021 | 0 | 0 | 75 | 0
Catcliffe Woodhouse Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Rother Valley | Catcliffe and Woodhouse, River Rother | Rotherham | Environment Agency | Development | 1871.035 | 1871.035 | 0 | 1671.3 | 0 | 2017-2019 | By April 2021 | 515 | 0 | 515 | 0
Herringthorpe Valley Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Rotherham | Herringthorpe Valley Flood, Rotherham, South Yorkshire | Rotherham | Rotherham Borough Council | Development | 300 | 300 | 0 | 270 | 0 | 2017-2019 | By April 2019 | 110 | 0 | 110 | 0
Parkgate Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Wentworth and Dearne | Parkgate, Rotherham, South Yorkshire | Rotherham | Rotherham Borough Council | Development | 300 | 300 | 0 | 270 | 0 | 2017-2019 | By April 2019 | 15 | 0 | 15 | 0
Whiston Brook Flood Storage | Yorkshire & the Humber | Yorkshire | Yorkshire | Rother Valley | Whiston Brook, Whiston, Rotherham, South Yorkshire | Rotherham | Rotherham Borough Council | Development | 350 | 320 | 30 | 270 | 0 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
Holbeck Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Thirsk and Malton | Holbeck | Ryedale | North Yorkshire County Council | Development | 539.44 | 459.44 | 80 | 45.944 | 229.72 | Beyond 2021 | Beyond 2021 | 55 | 0 | 55 | 0
Middle Hull Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Thirsk and Malton | Middle Hull | Ryedale | North Yorkshire County Council | Development | 140.4 | 100.4 | 40 | 0 | 20.08 | Beyond 2021 | Beyond 2021 | 0 | 0 | 10 | 0
Pickering & Costa Becks Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Thirsk and Malton | Pickering & Costa Becks | Ryedale | North Yorkshire County Council | Development | 682.96 | 602.96 | 80 | 60.296 | 301.48 | Beyond 2021 | Beyond 2021 | 70 | 0 | 70 | 0
River Dove Uplands Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Thirsk and Malton | River Dove Uplands | Ryedale | North Yorkshire County Council | Development | 675.14 | 595.14 | 80 | 59.744 | 298.72 | Beyond 2021 | Beyond 2021 | 70 | 0 | 70 | 0
River Rye Uplands Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Thirsk and Malton | River Rye Uplands | Ryedale | North Yorkshire County Council | Development | 658 | 558 | 100 | 55.8 | 446.4 | Beyond 2021 | Beyond 2021 | 65 | 0 | 65 | 0
River Seven Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Thirsk and Malton | River Seven | Ryedale | North Yorkshire County Council | Development | 160.4 | 100.4 | 60 | 10.04 | 50.2 | Beyond 2021 | Beyond 2021 | 10 | 0 | 10 | 0
Robin Hoods Bay PAR & Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Scarborough and Whitby | Robin Hoods Bay, North Yorkshire, YO22 | Scarborough | Scarborough Borough Council | Construction | 692 | 505 | 187 | 455 | 0 | By April 2017 | By April 2019 | 0 | 60 | 0 | 60
Runswick Bay Appraisal and Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Scarborough and Whitby | Runswick Bay Village, North Yorkshire TS13 | Scarborough | Scarborough Borough Council | Construction | 1082 | 982 | 100 | 300 | 0 | By April 2017 | By April 2019 | 0 | 50 | 0 | 50
Scarborough South Bay Beach Management Programme | Yorkshire & the Humber | Yorkshire | Yorkshire | Scarborough and Whitby | Scarborough North Yorkshire, YO11 | Scarborough | Scarborough Borough Council | Construction | 94.8 | 94.8 | 0 | 10 | 0 | By April 2017 | By April 2019 | 0 | 0 | 30 | 0
Scarborough South Bay Spa Seawall Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Scarborough and Whitby | Scarborough North Yorkshire, YO11 | Scarborough | Scarborough Borough Council | Construction | 17300 | 15000 | 2300 | 10742 | 3581 | By April 2017 | By April 2019 | 0 | 380 | 0 | 380
Whitby Church Street Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Scarborough and Whitby | Whitby, North Yorkshire, YO21 Abbey Cliff SSSI, River Esk | Scarborough | Scarborough Borough Council | Construction | 1191.8182 | 884.8182 | 307 | 503 | 0 | By April 2017 | By April 2019 | 55 | 0 | 55 | 0
Filey Flood Alleviation Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Thirsk and Malton | Filey, North Yorkshire, YO15 | Scarborough | Scarborough Borough Council | Development | 4583 | 2843 | 1740 | 1917 | 0 | 2017-2019 | By April 2019 | 595 | 0 | 595 | 0
Whitby Harbour Works MU17 & MU18 | Yorkshire & the Humber | Yorkshire | Yorkshire | Scarborough and Whitby | Whitby, North Yorkshire, YO21 | Scarborough | Scarborough Borough Council | Development | 8969.532 | 4838.6569 | 4130.8751 | 1918 | 2303 | 2017-2019 | By April 2019 | 15 | 360 | 15 | 360
Bond Ings Pumping Station | Yorkshire & the Humber | Yorkshire | Yorkshire | Selby and Ainsty | South of Sherburn in Elmet | Selby | Selby Area IDB | Development | 95 | 42.75 | 52.25 | 24.75 | 0 | 2017-2019 | Beyond 2021 | 5 | 0 | 5 | 0
Cawood Foreshore Erosion | Yorkshire & the Humber | Yorkshire | Yorkshire | Selby and Ainsty | Cawood, River Ouse | Selby | Environment Agency | Development | 100 | 100 | 0 | 0 | 100 | 2019-2021 | By April 2021 | 125 | 0 | 125 | 0
Little Airmyn Pumping Station | Yorkshire & the Humber | Yorkshire | Yorkshire | Selby and Ainsty | Airmyn, west of Goole, River Aire | Selby | Selby Area IDB | Development | 850 | 382.5 | 467.5 | 0 | 382.5 | 2019-2021 | By April 2021 | 30 | 0 | 30 | 0
North York Flood Risk Management Plan | Yorkshire & the Humber | Yorkshire | Yorkshire | Selby and Ainsty | North York | Selby | North Yorkshire County Council | Development | 685.12 | 605.12 | 80 | 0 | 150 | 2019-2021 | Beyond 2021 | 0 | 0 | 65 | 0
Temple Hirst Pumping Station | Yorkshire & the Humber | Yorkshire | Yorkshire | Selby and Ainsty | Temple Hirst, River Aire | Selby | Selby Area IDB | Development | 125 | 125 | 0 | 125 | 0 | 2017-2019 | By April 2019 | 5 | 0 | 5 | 0
Blackburn Brook Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Sheffield, Brightside and Hillsborough | Sheffield/Blackburn Brook, Charlton Brook | Sheffield | Sheffield City Council | Development | 2600 | 1325 | 1275 | 225 | 1000 | 2019-2021 | Beyond 2021 | 0 | 0 | 250 | 0
Ellin Street Culvert Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Sheffield Central | Sheffield, Porter Brook | Sheffield | Environment Agency | Development | 250 | 250 | 0 | 250 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Sheaf Catchment Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Sheffield, Heeley | Sheffield/River Sheaf, Porter Brook | Sheffield | Sheffield City Council | Development | 24599.783 | 9402.0732 | 15197.7098 | 600 | 6923.6 | 2019-2021 | Beyond 2021 | 685 | 0 | 685 | 0
Sheaf Screen Study and Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Sheffield Central | Sheffield, River Sheaf | Sheffield | Environment Agency | Development | 400 | 400 | 0 | 400 | 0 | 2017-2019 | By April 2019 | 0 | 0 | 0 | 0
Sheffield Upper Don Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Sheffield, Brightside and Hillsborough | Sheffield/Upper River Don, River Loxley | Sheffield | Sheffield City Council | Development | 31907.634 | 12699.924 | 19207.71 | 600 | 9624 | 2019-2021 | Beyond 2021 | 375 | 0 | 375 | 0
Sheffield Watercourses Culvert Renewal Survey Programme | Yorkshire & the Humber | Yorkshire | Yorkshire | Sheffield Central | Sheffield, South Yorkshire/Critical Watercourse Culverts | Sheffield | Sheffield City Council | Development | 4676.541 | 2432.8907 | 2243.6502 | 100 | 1856 | 2017-2019 | By April 2021 | 475 | 0 | 475 | 0
Three Brooks Environmental Scheme, Manor, Sheffield | Yorkshire & the Humber | Yorkshire | Yorkshire | Sheffield Central | Sheffield/Car Brook, Kirkbridge Dyke, Jervis Lumb watercourses | Sheffield | Sheffield City Council | Development | 2882.883 | 1730.1562 | 1152.7268 | 0 | 1491 | 2019-2021 | Beyond 2021 | 150 | 0 | 150 | 0
Carr Beck - Flood Alleviation Scheme Phase 1 | Yorkshire & the Humber | Yorkshire | Yorkshire | Wakefield | Cutsyke, Castleford Carr Beck area | Wakefield | Wakefield City Council | Development | 580 | 295 | 285 | 90 | 205 | 2019-2021 | By April 2021 | 205 | 0 | 205 | 0
Ea Beck - Flood Alleviation Scheme Phase 1 | Yorkshire & the Humber | Yorkshire | Yorkshire | Hemsworth | South Kirkby/South Elmsall Area, EA beck | Wakefield | Wakefield City Council | Development | 740 | 350 | 390 | 270 | 80 | 2017-2019 | By April 2021 | 205 | 0 | 205 | 0
Lower Calder and Aire Washland Study | Yorkshire & the Humber | Yorkshire | Yorkshire | Elmet and Rothwell | Lower Calder | Wakefield | Environment Agency | Development | 6500 | 6500 | 0 | 100 | 100 | Beyond 2021 | Beyond 2021 | 0 | 0 | 500 | 0
Water End Flood Alleviation Scheme, York | Yorkshire & the Humber | Yorkshire | Yorkshire | York Outer | York | York | Environment Agency | Construction | 4294.46 | 3159.14 | 1135.32 | 2.5 | 2.5 | By April 2017 | By April 2019 | 0 | 0 | 380 | 0
Clifton Ings Barrier Bank | Yorkshire & the Humber | Yorkshire | Yorkshire | York Outer | York, River Ouse | York | Environment Agency | Development | 2080.997 | 2067.997 | 13 | 1495.651 | 0 | 2017-2019 | By April 2019 | 300 | 0 | 300 | 0
River Foss (020) Channel Improvements Foss 2008 IDB | Yorkshire & the Humber | Yorkshire | Yorkshire | York Outer | Earswick,York | York | Ainsty (2008) IDB | Development | 20 | 20 | 0 | 20 | 0 | 2017-2019 | By April 2019 | 50 | 0 | 50 | 0
York Flood Defence Improvements (Ouse & Foss) | Yorkshire & the Humber | Yorkshire | Yorkshire | York Central | City of York | York | Environment Agency | Pipeline | 69300 | 49200 | 20100 | 3400 | 39000 | 2017-2019 | Beyond 2021 | 1750 | 0 | 2000 | 0

## Phased and Completed Projects
Flood and Coastal Erosion Risk Management (FCERM) Projects Better Protecting Homes - England
January RFCC consented programme (updated February 2017)
Please note: Some of these projects are not fully complete but provide better protection to homes in phases. These may also appear in the 2017-18 to 2020-21 Programme tab.
Project Name | Office of National Statistics Region | Regional Flood and Coastal Committee | Environment Agency Area | Lead Risk Management Authority Type | Number of homes better protected from Flooding and Coastal Erosion to date
Cherry Hinton Estate, Cambridge, Surface Water Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | Lead Local Flood Authority | 25
Flood Proofing of Properties-Oakington | East of England | Anglian Central | East Anglia | Environment Agency | 41
Flood Proofing of Properties-Riseley | East of England | Anglian Central | East Anglia | Environment Agency | 2
Hunstanton/Heacham Beach Management | East of England | Anglian Central | East Anglia | Environment Agency | 115
Pix Brook Flood Alleviation Scheme | East of England | Anglian Central | East Anglia | Internal Drainage Board | 74
Pumping plant refurbishment - Washways pumping station | East of England | Anglian Central | East Anglia | Internal Drainage Board | 90
Ransonmoor Pumping Station Refurbishment | East of England | Anglian Central | East Anglia | Internal Drainage Board | 33
Ten Mile Bank Emergency repairs | East of England | Anglian Central | East Anglia | Environment Agency | 39
Barnby - North Cove Reorganisation | East of England | Anglian Eastern | East Anglia | Internal Drainage Board | 11
Clacton Holland on Sea Management Plan Implementation Phase 1 (Zones B and C) | East of England | Anglian Eastern | East Anglia | Local Authority | 1576
Cromer Coast Protection Scheme | East of England | Anglian Eastern | East Anglia | Local Authority | 157
Great Yarmouth Tidal Defences | East of England | Anglian Eastern | East Anglia | Environment Agency | 414
Happisburgh to Winterton Stages 1 and 2 | East of England | Anglian Eastern | East Anglia | Environment Agency | 161
Hazel cottage and Brooklands Property Level Protection | East of England | Anglian Eastern | East Anglia | Environment Agency | 1.59
Scratby Coast Protection Scheme (was Scratby Rock Berm Extension) | East of England | Anglian Eastern | East Anglia | Local Authority | 37
Sheringham Coast Protection Scheme | East of England | Anglian Eastern | East Anglia | Local Authority | 60
Wagtail Drive Flood Alleviation Scheme | East of England | Anglian Eastern | East Anglia | Lead Local Flood Authority | 20
Hobhole Refurbishment Programme | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Internal Drainage Board | 478
Humber Grimsby Docks | Yorkshire & the Humber | Anglian Northern | Lincolnshire and Northamptonshire | Environment Agency | 12179
Lincshore 2010 to 2015 | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Environment Agency | 4372
Stewards House Drain Improvments | East of England | Anglian Northern | Lincolnshire and Northamptonshire | Internal Drainage Board | 30
Vernatts Sluice | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Internal Drainage Board | 22
Washingborough - Flood Risk and Drainage Improvement Scheme | East Midlands | Anglian Northern | Lincolnshire and Northamptonshire | Lead Local Flood Authority | 40
Aston Cantlow, Property Level Protection Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 38
Broad Lane/Banner Lane, Brookstray, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 8
Cambridge, Gloucestershire Flood Alleviation Scheme | South West | English Severn and Wye | West Midlands | Internal Drainage Board | 8
Contribution to Deerhurst Walton | South West | English Severn and Wye | West Midlands | Environment Agency | 7
Cradley Brook, Cradley, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 1
Dinglewell, Gloucester Property Level Protection | South West | English Severn and Wye | West Midlands | Lead Local Flood Authority | 13
Eathorpe | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 4
Ketley Town, Surface Water Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Local Authority | 15
Kinver, River Stour, Property Level Protection Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 1
Mushroom Green Dam, Dudley, Mousesweet Brook, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 42
North East Bomere Heath, Shropshire, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 6
Pentre Perfa Bank Refurbishment | West Midlands | English Severn and Wye | West Midlands | Environment Agency | 36
Pooley Lane, Moreton, Surface Water Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 1
Princethorpe, Rugby, Property Level Protection Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 2
Shropshire Property Level Protection Schemes | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 3
Sudbrook, Gloucester Property Level Protection | South West | English Severn and Wye | West Midlands | Lead Local Flood Authority | 40
The Beck, Mousesweet Brook, Dudley Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Environment Agency | 46
The Grove, Minsterley, Shropshire, Flood Alleviation Scheme | West Midlands | English Severn and Wye | West Midlands | Lead Local Flood Authority | 6
Upper Lydbrook Flood Alleviation Scheme | South West | English Severn and Wye | West Midlands | Local Authority | 36
Wick, Worcestershire, Property Level Protection Scheme | West Midlands | English Severn and Wye | West Midlands | Local Authority | 14
Anchorsholme Coast Protection Scheme | North West | North West | Cumbria and Lancashire | Lead Local Flood Authority | 4814
Broadfleet Remedial Works | North West | North West | Cumbria and Lancashire | Environment Agency | 607
Crossens Pumping Station Refurbishment | North West | North West | Cumbria and Lancashire | Environment Agency | 660
Croston Village Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Environment Agency | 347
Elliot Park, Keswick Surface Water Mgmt Scheme | North West | North West | Cumbria and Lancashire | Lead Local Flood Authority | 66
Hesketh OM East Mgd Realignment | North West | North West | Cumbria and Lancashire | Environment Agency | 140
Hest Bank Flood Protection Scheme LDW 41546 | North West | North West | Cumbria and Lancashire | Local Authority | 4
Jacks Key Reservoir Improvements, Darwen | North West | North West | Cumbria and Lancashire | Environment Agency | 1098
Marton Mere Pumping Station and Spillway improvements | North West | North West | Cumbria and Lancashire | Lead Local Flood Authority | 38
Rossall Coastal Defence Improvement Scheme | North West | North West | Cumbria and Lancashire | Local Authority | 2499
Slyne with Hest Flood Alleviation Scheme | North West | North West | Cumbria and Lancashire | Lead Local Flood Authority | 96
Starr Hills Sand Dunes Environmental Work | North West | North West | Cumbria and Lancashire | Lead Local Flood Authority | 501
Yellow Dam, Gategill Beck | North West | North West | Cumbria and Lancashire | Environment Agency | 35
A530 Bradfield Green, Crewe | North West | North West | Greater Manchester Merseyside and Cheshire | Lead Local Flood Authority | 15
Beech Gardens, Rainford | North West | North West | Greater Manchester Merseyside and Cheshire | Lead Local Flood Authority | 10
Calder Avenue, Littleborough Flood Alleviation Scheme | North West | North West | Greater Manchester Merseyside and Cheshire | Lead Local Flood Authority | 66
Dee Lock Improvements, Chester | North West | North West | Greater Manchester Merseyside and Cheshire | Environment Agency | 71
Gorsefield Avenue, Eastham, Wirral | North West | North West | Greater Manchester Merseyside and Cheshire | Lead Local Flood Authority | 11
Northwich Town Centre | North West | North West | Greater Manchester Merseyside and Cheshire | Environment Agency | 230
Padgate Lane, Padgate | North West | North West | Greater Manchester Merseyside and Cheshire | Lead Local Flood Authority | 10
Pennington Pumping Station Replacement | North West | North West | Greater Manchester Merseyside and Cheshire | Environment Agency | 262
River Mersey Warrington FRM Scheme | North West | North West | Greater Manchester Merseyside and Cheshire | Environment Agency | 66
Staggs Brook Culvert, Whitchurch | West Midlands | North West | Greater Manchester Merseyside and Cheshire | Environment Agency | 35
Bishop Auckland SW Drainage and Culvert Works | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 7
Blyth South Beach Dune Management Scheme | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 9
Brunton Park Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Environment Agency | 85
Chester le Street SW Flood Management Works | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 14
Fellgate Estate - Appraisal, Design and Construction | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 204
Forest Hall Culvert Remedials | North East | Northumbria | Northumberland Durham and Tees | Environment Agency | 12
Green Lane, Dudley Appraisal, Design and Construction | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 47
Hardwick Property Level Protection Scheme | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 9
Hood Street, St Johns Chapel | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 6
Morpeth Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Environment Agency | 812
Oak Grove Appraisal, Design and Construction | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 39
Oakenshaw Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 13
Seaham Harbour Design and Construction | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 84
Skinningrove Coastal Protection Works | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 176
Town Wall Model Study Construction C6-3, Hartlepool | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 230
Waldridge Surface Water Scheme | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 21
Witton Gilbert Flood Alleviation Scheme | North East | Northumbria | Northumberland Durham and Tees | Lead Local Flood Authority | 52
Adelphi Road Flood Alleviation Scheme (Property Level Protection) | South West | South West | Devon Cornwall and the Isles of Scilly | Lead Local Flood Authority | 4
Branscombe Flood Improvements | South West | South West | Devon Cornwall and the Isles of Scilly | Lead Local Flood Authority | 20
Devon and Cornwall Floods Recovery 2012 | South West | South West | Devon Cornwall and the Isles of Scilly | Environment Agency | 321
Devon County Council Property Level Protection | South West | South West | Devon Cornwall and the Isles of Scilly | Lead Local Flood Authority | 60
Perranporth (Bolingey River) Flood Defence Scheme | South West | South West | Devon Cornwall and the Isles of Scilly | Environment Agency | 107
Polruan Cliff Stabilisation Works | South West | South West | Devon Cornwall and the Isles of Scilly | Lead Local Flood Authority | 8
Salcombe Town Tidal Gates | South West | South West | Devon Cornwall and the Isles of Scilly | Local Authority | 12
Teignmouth Sea Wall Void repair | South West | South West | Devon Cornwall and the Isles of Scilly | Environment Agency | 88
The Ride Gypsy and travellers site food defence, Plymouth | South West | South West | Devon Cornwall and the Isles of Scilly | Local Authority | 8
Tommys Polruan | South West | South West | Devon Cornwall and the Isles of Scilly | Lead Local Flood Authority | 2
Allington Sluice Repairs | South East | Southern | Kent, South London and East Sussex | Environment Agency | 24
Aylesford Property Level Protection | South East | Southern | Kent, South London and East Sussex | Environment Agency | 45
Broomhill Sands Coastal Defence Scheme | South East | Southern | Kent, South London and East Sussex | Environment Agency | 1388
Denge Beach Management 2011-15 | South East | Southern | Kent, South London and East Sussex | Environment Agency | 580
Front Brents Flood Alleviation Scheme | South East | Southern | Kent, South London and East Sussex | Environment Agency | 22
Greatstone Dunes Management (2012 - 2016) | South East | Southern | Kent, South London and East Sussex | Local Authority | 155
Hythe to Folkestone Beach Management 2015 - 2020 | South East | Southern | Kent, South London and East Sussex | Local Authority | 438
Littlestone Beach Recharge | South East | Southern | Kent, South London and East Sussex | Environment Agency | 3802
Northern Sea Wall | South East | Southern | Kent, South London and East Sussex | Environment Agency | 98
Pett Shingle Renourishment Ph 2-6 | South East | Southern | Kent, South London and East Sussex | Environment Agency | 456
Rye Harbour Terminal Groyne | South East | Southern | Kent, South London and East Sussex | Environment Agency | 234
Sandwich Town Tidal Defences | South East | Southern | Kent, South London and East Sussex | Environment Agency | 486
SoN Beckenham Hill Trash Screen | London | Southern | Kent, South London and East Sussex | Environment Agency | 218
Sundridge Weir Project | South East | Southern | Kent, South London and East Sussex | Lead Local Flood Authority | 14
Tonbridge Town Lock Town Walls | South East | Southern | Kent, South London and East Sussex | Environment Agency | 100
Walmer to Kingsdown Timber Groyne Replacement | South East | Southern | Kent, South London and East Sussex | Local Authority | 197
Whitstable Harbour Flood Defence Works | South East | Southern | Kent, South London and East Sussex | Local Authority | 2378
Hambledon Groundwater Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Lead Local Flood Authority | 124
Nore Farm Stream Emsworth, Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Environment Agency | 9
Pagham Beach Erosion Management Option | South East | Southern | Solent and South Downs | Local Authority | 10
Pagham Harbour Inland Banks Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Environment Agency | 83
PEVENSEY BAY SEA DEFENCES PPP | South East | Southern | Solent and South Downs | Environment Agency | 3101
Portsea Island - Flood Cell 4: North Portsea Island Coastal Flood and Erosion Risk Management Scheme | South East | Southern | Solent and South Downs | Lead Local Flood Authority | 340
Ringmer Flood Alleviation Scheme | South East | Southern | Solent and South Downs | Environment Agency | 31
Seaford Beach Shingle Recycling 2013-14 to 2017-18 | South East | Southern | Solent and South Downs | Environment Agency | 240
Selsey, Bracklesham and East Wittering Beach Management | South East | Southern | Solent and South Downs | Local Authority | 135
Richard White and Kiora Radial Gates Gantry Replacement | East of England | Thames | Hertfordshire and North London | Environment Agency | 1500
Salmons Brook Flood Alleviation Scheme | London | Thames | Hertfordshire and North London | Environment Agency | 1387
RB Kingston-Upon-Thames Surbiton Stream refurbishment | London | Thames | Kent, South London and East Sussex | Lead Local Flood Authority | 42
Robinhood Way Replacement Trash screen | London | Thames | Kent, South London and East Sussex | Lead Local Flood Authority | 13
TBAG BMS and PA System Upgrade | London | Thames | Kent, South London and East Sussex | Environment Agency | 146
TBAG Drive Equipment | London | Thames | Kent, South London and East Sussex | Environment Agency | 237
TBAG works - Next 5 yrs Approval Period and Beyond | London | Thames | Kent, South London and East Sussex | Environment Agency | 583
TBAG2 PLA Thames Barrier Act Navigation Reimbursements | London | Thames | Kent, South London and East Sussex | Environment Agency | 125
TBAG2 TB Bearings Procurement | London | Thames | Kent, South London and East Sussex | Environment Agency | 27
TBAG2 Thames Barrier MEICA Works | London | Thames | Kent, South London and East Sussex | Environment Agency | 66
Team 2100 Programme - Thames Delivery | London | Thames | Kent, South London and East Sussex | Environment Agency | 774
Team 2100 Programme IDT Services Thames | East of England | Thames | Kent, South London and East Sussex | Environment Agency | 187
Thames Barrier Anti-slip flooring | London | Thames | Kent, South London and East Sussex | Environment Agency | 24
Thames Barrier Control System Refurbishment | London | Thames | Kent, South London and East Sussex | Environment Agency | 15
Thames Barrier control tower lift refurbishment | London | Thames | Kent, South London and East Sussex | Environment Agency | 9
Aldbourne Flood Alleviation Scheme | South West | Thames | Thames | Lead Local Flood Authority | 5
Boxford Flood Alleviation Scheme | South East | Thames | Thames | Lead Local Flood Authority | 5
Cheney Manor Flood Mitigation Works | South West | Thames | Thames | Lead Local Flood Authority | 179
Eastbury Flood Alleviation Scheme | South East | Thames | Thames | Environment Agency | 10
Grazeley Green Flood Alleviation Scheme | South East | Thames | Thames | Lead Local Flood Authority | 13
Great Bedwyn Surface Water Drainage Improvements | South West | Thames | Thames | Lead Local Flood Authority | 66
Harness Close Surface water Flood Alleviation Scheme | South East | Thames | Thames | Lead Local Flood Authority | 12
River Thames Scheme - Community Reslilience Measures | South East | Thames | Thames | Environment Agency | 208
Temporary defence enabling works package | South East | Thames | Thames | Environment Agency | 250
Wanborough Flood Mitigation Scheme | South West | Thames | Thames | Lead Local Flood Authority | 53
Wheatley South-East Flood Alleviation | South East | Thames | Thames | Local Authority | 5
Eggington Brook, Mickleover, Flood Risk Reduction Scheme | East Midlands | Trent | East Midlands | Lead Local Flood Authority | 10
Isle of Axholme, Owston Ferry Flood Defence | Yorkshire & the Humber | Trent | East Midlands | Environment Agency | 124
Leicester Flood Risk Management Scheme - conveyance works | East Midlands | Trent | East Midlands | Environment Agency | 1436
Nottingham City Council Individual Property Protection Programme | East Midlands | Trent | East Midlands | Lead Local Flood Authority | 30
Paper Mill Dyke, Tickhill, Flood Defence Wall | Yorkshire and The Humber | Trent | East Midlands | Lead Local Flood Authority | 9
River Soar, Sharnford, Property Level Protection | East Midlands | Trent | East Midlands | Environment Agency | 14
River Trent, Amcotts, Crowle Pumped Catchments Capital Works | Yorkshire & the Humber | Trent | East Midlands | Internal Drainage Board | 298
River Trent, North Muskham, Flood Alleviation Scheme | East Midlands | Trent | East Midlands | Environment Agency | 35
Skyers Drain, Greenholme Pumping Station Refurbishment | Yorkshire & the Humber | Trent | East Midlands | Internal Drainage Board | 25
Steelgoose Drain and Tributary Improvements, Belton, North Lincolnshire | Yorkshire and The Humber | Trent | East Midlands | Internal Drainage Board | 3
West Park Penstock Improvement Works | East Midlands | Trent | East Midlands | Environment Agency | 660
Woolsington Close, Strelley: Surface Water Management Scheme | East Midlands | Trent | East Midlands | Lead Local Flood Authority | 11
Acacia crescent, Bilbrook | West Midlands | Trent | West Midlands | Lead Local Flood Authority | 1
Bells Lane, Birmingham, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Lead Local Flood Authority | 8
Callow Brook, Rubery Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Local Authority | 4
Hobnock Road Property Level Protection | West Midlands | Trent | West Midlands | Lead Local Flood Authority | 3
Kelverley Grove flood defence repairs | West Midlands | Trent | West Midlands | Environment Agency | 140
Longmore Street, River Rea, CM Scheme | West Midlands | Trent | West Midlands | Environment Agency | 191
Lower Tame - Whitacre Heath, Tamworth and Fazeley | Yorkshire & the Humber | Trent | West Midlands | Environment Agency | 241
Lower Tean, River Tean, Flood Alleviation Scheme | West Midlands | Trent | West Midlands | Lead Local Flood Authority | 9
Pensby Close Community Protection | West Midlands | Trent | West Midlands | Lead Local Flood Authority | 7
Sheepy Magna, River Sence, Flood Alleviation Scheme | East Midlands | Trent | West Midlands | Environment Agency | 4
Stapenhill Brook Culvert Capital Maintenance | West Midlands | Trent | West Midlands | Environment Agency | 9
SWWM Trent RFCC Local Levy Package | West Midlands | Trent | West Midlands | Environment Agency | 15
Bournemouth Beach Management Phase 1 | South West | Wessex | Wessex | Lead Local Flood Authority | 730
Bristol City, Surface Water Management, Southmead Site - LDW 41635 | South West | Wessex | Wessex | Lead Local Flood Authority | 9
Charminster | South West | Wessex | Wessex | Environment Agency | 8
Congresbury Yeo Tidal Banks | South West | Wessex | Wessex | Environment Agency | 4101
Cumberland Road Wall - LDW 41683 | South West | Wessex | Wessex | Lead Local Flood Authority | 124
Dorset Property Level Protection LA - LL 148 | South West | Wessex | Wessex | Lead Local Flood Authority | 94
Kingston Seymour Asset Improvements | South West | Wessex | Wessex | Environment Agency | 103
Lyme Regis Coast Protection Works Beach Management Plan (BMP Works) - CPW 3000 | South West | Wessex | Wessex | Local Authority | 27
Lyme Regis Environmental Improvements Phase 4 - CPW 2071. | South West | Wessex | Wessex | Local Authority | 480
Poole Dolphin Haven Works | South West | Wessex | Wessex | Environment Agency | 20
Poole Frontage Mgmt Plan Works - Beach Renourishment 15/16 - CPW 3081e CPW 3020 | South West | Wessex | Wessex | Lead Local Flood Authority | 795
Swanage FSR No.1 Embankment Failure | South West | Wessex | Wessex | Environment Agency | 400
Wessex Property Level Protection | South West | Wessex | Wessex | Environment Agency | 116
West Bay Coast Protection Works Beach Management | South West | Wessex | Wessex | Local Authority | 70
Aston and Swallownest Property Level Protection - Phase 2 | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 57
Atkinson Lane Property Level Protection | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 2
Boggle Hole Youth Hostel Coastal Erosion Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Local Authority | 1
Brampton, Chesterfield Property Level Flood Protection | Yorkshire & the Humber | Yorkshire | Yorkshire | Local Authority | 67
Bridge near Bethells Bridge Hempholme | Yorkshire & the Humber | Yorkshire | Yorkshire | Internal Drainage Board | 3
Burstwick New Clough | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 360
Chesterfield Hollis Lane Property Resilience | Yorkshire & the Humber | Yorkshire | Yorkshire | Local Authority | 3
Denaby Main Property Level Protection Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 31
Gilroyd - Water Royd Drive | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 4
Hawthorne Terrace, Garforth | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 10
Humber: Estuary Erosion Protection Works | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 20
Kirkby Wharfe Property Level Protection scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Local Authority | 7
Leconfield Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 55
Leeds - Ramsden Street, Kippax | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 32
New Mill Road (Brockholes) Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 4
Newport Floodwalls | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 270
Package 5 - Yorkshire - Humber inc Kilnsea Chalky Point [Recovery] | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 12
Pickering Flood Storage Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 50
Sandholme Road Bridge Leven | Yorkshire & the Humber | Yorkshire | Yorkshire | Internal Drainage Board | 10
Sandsend Coast Protection Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 10
Snaith Ings Reservoir Repairs Project | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 57
The Drain, Bolton Percy Property Level Protection | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 7
Upper Calder Flood Risk Reduction Schemes | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 32
Walsden Water-Todmorden Flood Alleviation Scheme Phase 3 | Yorkshire & the Humber | Yorkshire | Yorkshire | Environment Agency | 58
Willerby and Derringham Flood Alleviation Scheme | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 8085
Wilthorpe - Huddersfield Road | Yorkshire & the Humber | Yorkshire | Yorkshire | Lead Local Flood Authority | 4