## Read Me
Proposed programme of measures for Upper Costa Beck: This spreadsheet lists the proposed programme of measures for Upper Costa Beck, identifying the actions that can be justified by the currently available evidence. The programme of measures consists of two groups of measures: A) The first worksheet lists the mitigation measures that may be required for Upper Costa Beck to achieve Good Ecological Potential. Mitigation measures are actions intended to reduce the ecological impact of the modifications that were made to Upper Costa Beck to support the designated uses such as land drainage. In order to achieve Good Ecological Potential, all relevant mitigation measures must be in place. Further work is needed to evaluate whether each mitigation measure is feasible in Upper Costa Beck and if so what specific on-the-ground actions can be put in place to support achievement of Good Ecological Potential. B) The second worksheet lists the measures associated with each reason for not achieving good (RNAG) linked to the Fish classification element. The RNAG data were reviewed and updated by the Environment Agency as a first step in reviewing and updating the programme of measures for Upper Costa Beck. Each individual measure being proposed in the programme of measures reflects the level of confidence in the associated reason for not achieving good, with "suspected" reasons requiring further investigation to improve confidence before specific interventions, such as changes to environmental permits, can be justified.
For a full glossary of terms used in this spreadsheet use the following link:
https://environment.data.gov.uk/catchment-planning/help/glossary
SWMI: significant water management issue
RNAG: reason for not achieving good

## A) Mitigation measures
Note: Further work is required to determine which of the mitigation measure actions listed below are relevant to Upper Costa Beck and, if so, what site specific actions are technically feasible and needed to support achieving the objective of Good Ecological Potential |  | Designated uses for Upper Costa Beck as a heavily modified water body "Yes" indicates the mitigation measure is applicable to the designated use
Mitigation Measure description | Action description | Other human sustainable development - fish farms | Flood protection | Land drainage
Action(s) that improve the physical form and functioning of a water body | Modify channel to allow increased natural processes e.g. Remeandering of straightened river channels, through both creation of a new meandering course and reconnection of cut off meanders | yes
Action(s) that improve the physical form and functioning of a water body | Removal or re-location of set-back embankments |  | yes
Action(s) that improve the physical form and functioning of a water body | Restoration of lateral connectivity with the water bodies surrounding floodplain e.g. flood plain spillways |  | yes
Action(s) that improve the physical form and functioning of a water body | Managed realignment of flood defence assets |  | yes
Action(s) that improve the physical form and functioning of a water body | Activity to create new habitat where it did not exist before | yes | yes
Action(s) that improve the physical form and functioning of a water body | Removal of hard engineering structures that modify the natural flow and sediment regime, including weirs, locks, floodgates, sluices, and erosion control structures | yes | yes
Action(s) that improve the physical form and functioning of a water body | Removal/softening of hard engineering structures that modify natural bank profile | yes | yes
Action(s) that improve the physical form and functioning of a water body | Preserve and/or restore existing in stream and riparian/shoreline habitats | yes | yes | yes
Action(s) that improve the physical form and functioning of a water body | Restore or increase in-channel morphological diversity e.g. riffle and pool creation and bar creation etc. | yes | yes | yes
Action(s) that improve the physical form and functioning of a water body | Rehabilitation of degraded bankside habitats to improve their physical structure and the condition of the riparian zone. Bank rehabilitation includes bank reprofiling, the creation of aquatic ledges and removal of hard bank protection etc. | yes | yes
Action(s) that improve the physical form and functioning of a water body | Re-opening of covered culverts |  | yes
Action(s) that improve the physical form and functioning of a water body | Bed of culvert altered to allow decreased flow conditions and to allow longitudinal connectivity of both biota and sediments |  | yes
Action(s) to remove or enhance structures that have a detrimental impact on the ecology of the water body | Structural modification or enhancement of hard structures to improve ecological value, where structure cannot be removed | yes
Action(s) to remove or enhance structures that have a detrimental impact on the ecology of the water body | Installation of structures designed to facilitate and improve the passage of migratory (e.g. salmon and sea trout) and non-migratory fish where structures cannot be removed | yes | yes
Action(s) to remove or enhance structures that have a detrimental impact on the ecology of the water body | Modification of structure to prevent/reduce fish entrainment e.g. screens | yes | yes
Action(s) to remove or enhance structures that have a detrimental impact on the ecology of the water body | Retro-fitting existing structures to accommodate niche habitats, as opposed to more substantial structural modifications that would be likely to deliver greater hydromorphological change but may not be possible given the use | yes | yes | yes
Action(s) to remove or enhance structures that have a detrimental impact on the ecology of the water body | Structural changes to locks, sluices, weirs, beach control | yes | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Good practice management of in channel and riparian vegetation works or maintenance practices (e.g. macrophyte cutting), carried out in a manner that considers the impacts of the activity upon ecology and hydromorphology | yes | yes | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Action(s) to reduce the extent and spread of invasive non-native species, including actions on our own assets | yes | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Leaving habitat or parts of natural habitat while undertaking operations or maintenance in a water body |  | yes | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Implement an active sediment management strategy (develop and revise) which could include a) substrate reinstatement, b) sediment traps, c) allow natural recovery minimising maintenance, d) riffle construction, e) reduce all bar necessary management in flood risk areas | yes | yes | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Ensure best practice techniques are applied when undertaking maintenance activities to minimise impacts to the habitat | yes | yes | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Ensure best practice is applied when undertaking maintenance works e.g. coffer dam placement, working during appropriate flow conditions | yes | yes | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Appropriate channel maintenance strategies and techniques, e.g. remove woody debris only upstream of, or within, areas of urban flood risk |  | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Reduction of re-suspension of sediments | yes
Action(s) to change existing operational and /or maintenance practices to improve the ecology of a water body | Implement an active sediment management regime | yes
Action(s) concerned with the impacts of water resource activities such as impoundments and abstractions | Maintain flows that can move sediment through the water body | yes
Action(s) concerned with the impacts of water resource activities such as impoundments and abstractions | Ensure good dissolved oxygen levels are recorded down stream of impoundments and abstractions | yes
Action(s) concerned with the impacts of water resource activities such as impoundments and abstractions | Implement a downstream flow regime that does not impact the ecology (applies to rivers and reservoirs) | yes | yes
Action(s) to educate the public and raise awareness of impacts on water bodies | Raise public awareness of invasive species e.g. leaflets, media campaigns, app development | yes
Action(s) to educate the public and raise awareness of impacts on water bodies | Raise public awareness of the impacts and responsibilities of landowners |  | yes | yes

## B) Measures linked to each RNAG
Reason for not achieving good (RNAG)
Quality element | Current classification | Pressure | SWMI | SWMI certainty | Activity | Activity certainty | Category | Category certainty | Measure | Lead organisation | Environment Agency Area
Mitigation Measures Assessment | Moderate or less Ecological Potential | For details of potential mitigation measures for Upper Costa Beck see worksheet A
Fish | Moderate status | Dissolved oxygen | Diffuse source | Suspected | Poor nutrient management | Suspected | Agriculture and rural land management | Suspected | Ongoing regulation of farms of their nutrient management to ensure compliance under Reduction and Prevention of Agricultural Diffuse Pollution Regulations 2018 (Farming Rules for Water), Silage, Slurry and Agricultural Fuel Oil Regulations 2010, Nitrate Pollution Prevention Regulations 2015, Water Resources Act 1991 and EPR in the Upper Costa Beck catchment. Carry out further investigations to identify if any additional site specific measures are required. | Environment Agency | Yorkshire
Fish | Moderate status | Sediment | Diffuse source | Suspected | Poor soil management | Suspected | Agriculture and rural land management | Suspected | Ongoing regulation of farms of their soil management to ensure compliance under Reduction and Prevention of Agricultural Diffuse Pollution Regulations 2018 (Farming Rules for Water), Silage, Slurry and Agricultural Fuel Oil Regulations 2010, Nitrate Pollution Prevention Regulations 2015, Water Resources Act 1991 and EPR in the Upper Costa Beck catchment. Carry out further investigations to identify any additional site specific measures that may be required. | Environment Agency | Yorkshire
Fish | Moderate status | Dissolved oxygen | Point source | Suspected | Sewage discharge (continuous) | Suspected | Water industry | Suspected | Ongoing regulation to ensure compliance with existing permit conditions. Review and where appropriate tighten limits on environmental permits for water discharge activities under the Environmental Permitting (England and Wales) Regulations 2016 (EPR). | Environment Agency | Yorkshire
Fish | Moderate status | Sediment | Point source | Suspected | Sewage discharge (continuous) | Suspected | Water industry | Suspected | Ongoing regulation to ensure compliance with existing permit conditions. Review and where appropriate tighten limits on environmental permits for water discharge activities under the Environmental Permitting (England and Wales) Regulations 2016 (EPR). | Environment Agency | Yorkshire
Fish | Moderate status | Dissolved oxygen | Point source | Suspected | Trade/Industry discharge | Suspected | Commercial fisheries | Suspected | Ongoing regulation to ensure compliance with existing permit conditions. Review and where appropriate tighten limits on environmental permits for water discharge activities under the Environmental Permitting (England and Wales) Regulations 2016 (EPR). | Environment Agency | Yorkshire
Fish | Moderate status | Sediment | Point source | Confirmed | Trade/Industry discharge | Confirmed | Commercial fisheries | Confirmed | Ongoing regulation to ensure compliance with existing permit conditions. Review and where appropriate tighten limits on environmental permits for water discharge activities under the Environmental Permitting (England and Wales) Regulations 2016 (EPR) | Environment Agency | Yorkshire
Fish | Moderate status | Morphology | Physical modification | Suspected | Barrier to fish migration | Suspected | Central Government | Suspected | Carry out further investigations to determine if gauging weir is having an impact and, if so, what site specific measures to improve fish passage are required. | Environment Agency | Yorkshire
Fish | Moderate status | Sediment | Diffuse source | Suspected | Transport drainage | Suspected | Urban and transport | Suspected | Carry out further investigations to identify any sediment inputs from highway drainage and assess impacts in order to determine what, if any, site specific measures are required. | Environment Agency | Yorkshire
Mercury and its compounds | Fail |  | National and international measures are already in place to address this problem. Awaiting recovery. No further actions required in Upper Costa Beck
Polybrominated diphenyl ethers (PBDEs) | Fail |  | National and international measures are already in place to address this problem. Awaiting recovery. No further actions required in Upper Costa Beck