## Avonmouth
Element | Element Duration (Weeks) | Task | Sub Task | Sub Task Duration (Days) | Status (%) | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April. |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March
 | time axis 2025-06-02 to 2027-03-29
PPC A - Secondary Containment Implementation Plan |  |  | Design | bar: 2025-06-02 to 2026-08-24
Implementation / Construction Phase
| 50 | Written “secondary containment implementation plan” . Plan to include finalised designs, implementation schedule and be produced by qualified civil or structural engineers. | E3MP |  | 100%
Element A |  |  | Concept and feasibility | 50 | bar: 2025-06-02 to 2025-08-04
|  |  | Outline design | 80 | bar: 2025-08-11 to 2025-11-24
|  |  | HS1 (@ project concept / options stage ) | 25 | bar: 2025-10-13 to 2025-11-10
|  |  | Final design (including designs and specifications of the proposed secondary containment proposals) | 130 | bar: 2025-12-01 to 2026-07-20
|  |  | HS2 (@ project definition) | 20 | bar: 2026-03-09 to 2026-04-20
|  |  | Update to spill modelling | 20 | bar: 2025-12-29 to 2026-01-19
|  |  | Implementation Schedule | 30 | bar: 2026-07-06 to 2026-08-10
|  |  | HS3 - HazOp (@ project detailed design) | 20 | bar: 2026-07-20 to 2026-08-10
|  |  | EA submission / review | 14 | bar: 2026-08-17 to 2026-08-24
| 145 |  | Procurement | 130 | bar: 2026-06-01 to 2026-11-23
|  |  | Construction | 650 | bar: 2026-09-14 to 2027-03-29
PPC B - Enclosure and abatement plan for Pre-Digestion Tanks |  |  | Design | bar: 2025-06-02 to 2026-03-16
Implementation / Construction Phase
Element B | 27 | Enclosure and abatement plan to contain final designs and installation of covers/enclosures for pre-digestion assets | Concept and feasibility | 50 | bar: 2025-06-02 to 2025-08-04
|  |  | Abatement plan development (incl final design and schedule) | 125 | bar: 2025-08-11 to 2026-02-16
|  |  | EA submission / review | 20 | bar: 2026-02-23 to 2026-03-16
| 57 |  | Procurement | 110 | bar: 2026-02-02 to 2026-06-29
|  |  | Construction | 235 | bar: 2026-04-06 to 2027-02-22
PPC C - Post Anaerobic digestion vessel cover plan |  |  | Design | bar: 2025-06-02 to 2026-10-26
Implementation / Construction Phase
Element C | 52 | Written 'post AD vessel cover' plan containing the final designs and implementation schedule for the secondary digesters. Plan to include details of the proposed gas utilisation/abatement plant, gas storage infrastructure for biogas, PRV and gas pipework. | Compile RBP report |  | 100%
|  |  | Digestate RBP report review (internal) | 20 | bar: 2025-08-04 to 2025-08-25
|  |  | RBP report EA submission | 14 | bar: 2025-09-01 to 2025-09-08
|  |  | Concept and feasibility | 50 | bar: 2025-06-23 to 2025-08-25
|  |  | Outline design | 60 | bar: 2025-09-01 to 2025-12-29
|  |  | HS1 (@ project concept / options stage ) | 35 | bar: 2025-10-06 to 2025-11-24
|  |  | AD vessel cover plan development (incl final design and schedule) | 185 | bar: 2026-01-05 to 2026-10-26
|  |  | HS2 (@ project definition) | 25 | bar: 2026-04-13 to 2026-05-25
|  |  | Implementation Schedule | 30 | bar: 2026-09-07 to 2026-10-12
|  |  | HS3 - HazOp (@ project detailed design) | 30 | bar: 2026-08-17 to 2026-09-21
|  |  | EA submission / review | 14 | bar: 2026-11-02 to 2026-11-09
| 145 |  | Procurement | 130 | bar: 2026-08-03 to 2027-01-25
|  |  | Construction | 650 | bar: 2026-11-16 to 2027-03-29