## Sheet1
Odour Improvement Plan Longreach STW
Review Date |  | 2023-08-31
Process Stage | Owner | Plan | Action | Expected difficulties | Measures to mitigate | Timeframe
THP | David Bourne | Measure pre & post filter for media effectiveness | Cake building OCU media condition assessment has been carried out. Awaiting quotes for required work on media and other works. | achieve funding | None required currently | 2024-01-01
THP | David Bourne | Replacement | one fan (number 3) internals worn - risk in place to replace | achieve funding | run duty assist 2 so mitigations required | 2024-01-01
OCUs general | David Bourne | Action recommendations in monthly OCU health checks | Action recommendations in monthly OCU health checks | achieve funding | N/A | ongoing
Sniff Testing | Odour Specialist | implement sniff testing | Procedure written for sniff testing,in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | resource | Daily checks and monthly OCU health checks | 6 months from permit issue