## Sheet1
Odour Improvement Plan Aylesbury STW
Review Date | 2023-10-18
Process Stage | Owner | Problem | Risk number | Plan what is required | Actions and who is responsible | Expected difficulties | Measures to mitigate | Timeframe
Press House | Gareth Burton | Old press house, not self cleansing | AMP7 | New Press house with self cleansing presses | AMP7 | Funding is available, timescales for delivery | Temporary Centrifge, in lorry and odour mitigted | 2024-03-01
Cake pad | Gareth Burton | Open cake pad | - | Raise walls of cake pad |  | timescales for delivery | None | 2024-03-01
sniff testing | odour specialist | implement sniff testing procedure |  | implement sniff testing procedure | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | resource | daily site rounds | 6 months from permit issue