## Sheet1
Odour Improvement Plan Beckton STW
Review Date |  | 2023-11-01
Process Stage | Owner | Plan | Action | Expected difficulties | Measures to mitigate | Timeframe
Odour Control Packages | Luke Parkinson | Sludge Thickening OCU replacement | Complete replacement of Odour Control Unit needed. Significant work undertaken to scope and understand all options. Risk raised. circa 3 million | Funding | Best practice for management of sources to existing OCU | AMP8
OCU | Luke Parkinson | Action recommendations laid out by monthly health checks | Action recommendations laid out by monthly health checks | Funding |  | Ongoing
Sniff testing | Odour Specialist | Implement sniff testing procedure | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | Resource | Site Round, Monthly health checks | 6 months from permit issues