## Sheet1
Odour Implementation Plan Deephams STW
Review Date |  | 2023-10-19
Process Stage | Owner | Summary - Plan | Action | Challenges | Measures to mitigate | Timescale for completion
Storm Tanks | Tony Fiske | Jet mixing system improvement | Raise ASPS risk to bring the swing amjet ceaning system back into fully automated operation. Risk rasied -112721 | This is part of the washwater projetct now, need to split out | Assessment of all amjets to understand cause of issues completed. Control panel rewired where required to allow cleaning operation to begin through a manual start up from the control room | AMP8
Sniff Testing | Odour Specialist | Implement Sniff Testing | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | Resource | daily site rounds, monthly OCU inspections | 6 months from permit issue
Sludge OCU | Tony Fiske | Get Sludge OCU Operational | Not currently operational. Make chamber bigger to get submiersible pumps in, to get OCU operational again. Funding achieved. |  | daily site rounds | 2024-01-01
OCU | Tony Fiske | Action recommendations laid out by monthly health checks | Action recommendations laid out by monthly health checks | Funding | daily site rounds | Ongoing