## Env Aspects
Contract Name: |  | Project Wind Phase 1 Enabling Works | Contract No: | 30173 |  |  |  | Task / Activity |  |  |  | Date: | 2025-09-09
Assessment Originator: |  | Paul Hutchinson | Assessment Approver(s): | John Pringle |  |  |  | The first phase of work will focus on preparing the site for construction. |  |  |  | Rev No.: | 0
The Contract Environmental Aspects and Impacts Register represents an overview of the typical environmental risks associated with the this contract The initial Aspects Register will be used to assist and guide the development of specific project plans required in the contract and which accurately reflect the project specific environmental risk and liabilities. The initial aspects register is completed at the start of the project and is to be reviewed regularly i.e. at changes to scope of works. This template contains generic information that must be customised for your site. Delete individual impacts / risks – or even whole parts – if they are not relevant to the contract and add in other contract-specific risks.
Contract Phase | Aspect & Risk Item | Environmental Aspect (Activity) | Environmental Impact | Legislative Category | Significance (Before Controls) |  |  | What controls are required? (Reference to Site Controls or RAMS) | Significance (After Controls in Place) |  |  | Action Owner | Opportunity
[5 empty] | Severity | Likelihood | Risk |  | Severity | Likelihood | Risk
Tender Pre-Construction Construction Post Construction | Waste Management | Containment | Discharge to ground, watercourses, air or off-site due to poorly stored waste. | Waste, Water, Contaminated Land, Materials, Nuisance | -3 | 4 | -12 | We will carefully consider issues such as wind-blown waste, filling / manual handling issues, suitability for transportation, etc., when determining container types, both for local on-site collection and bulk disposal off-site. Allowing waste to escape into the environment not only causes a nuisance to neighbours and generates a poor public image, but it is also illegal. All waste storage containers will be regularly inspected to ensure that: - Waste is securely stored to prevent unauthorised access - Containers are of good quality and stored in designated areas to prevent damage - Waste storage areas and containers are located away from watercourses or drains, or these features are protected - Waste storage containers and areas are free from spills, leaks, waste escape and deterioration. Audit Process Management of Hazardous & Non-Hazardous Waste RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 11: Waste | -3 | 1 | -3 | MGL Group / Supply Chain | Publicity from the management of a particular aspect of the works.
Tender Pre-Construction Construction Post Construction | Waste Management | Segregation | The mixing of hazardous and non-hazardous waste (resulting in the need to re-classify the non-hazardous as hazardous, possible mis-description of the waste in legal records, and increased disposal costs). | Waste | -3 | 3 | -9 | Waste classified as hazardous will not be mixed with non-hazardous, inert, or other types of hazardous waste. Site management will ensure adequate provision for the segregation of waste and that all wastes are labelled correctly. Site operatives will be briefed on the locations and management of specific waste on-site during the site induction or the Daily SHEQ Briefing. Audit Process Management of Hazardous & Non-Hazardous Waste SmartWaste Plan Waste Duty of Care (DoC) Written Information RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 11: Waste | -3 | 1 | -3 | MGL Group / Supply Chain | Publicity from the management of a particular aspect of the works. Reuse of certain types of material. Reducing waste.
Construction | Waste Management | Compliance with Duty of Care (DoC) Requirements | Failure to meet Duty of Care Requirements. | Waste | -3 | 3 | -9 | RCL will ensure that waste generated by our activities is managed following legislative frameworks. We will take all reasonable steps to manage the waste properly. - Prevent the escape of waste under MGL control and store it safely and securely. - Prevent waste from causing harm to the environment. - To transfer waste only to registered waste carriers for deposit at an authorised facility - To provide a completed waste transfer note (or hazardous/special waste consignment note) - Ensure waste is deposited only at facilities with a suitable permit or licence. - Subcontractors that remove waste from the project in their vehicles must be registered waste carriers. - Subcontractors that source their waste skips/containers must provide RCL with details of waste carriers, their waste facilities, and the associated registration certificates/permits. - MGL Demolition (RCL Sister Company) is a registered Upper Tier Carrier, Registration Number CBDU93565. It operates a Waste Transfer Facility, Permit number RP3397ZM at Riversdale Way, Newburn Haugh Industrial Estate, Newcastle Upon Tyne, NE15 8SF. All waste carriers and permitted facilities will be listed on the project SmartWaste Plan (SWMP) In addition, checks will occasionally be made to ensure that the waste has been taken to its intended destination. Audit Process Management of Hazardous & Non-Hazardous Waste SmartWaste Plan Waste Duty of Care (DoC) Written Information RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 11: Waste | -3 | 1 | -3 | MGL Group / Supply Chain | Publicity from the management of a particular aspect of the works
Construction | Waste Management | Diversion from Landfill | Increase in landfill sites due to failure in applying the waste hierarchy. Inappropriate disposal may lead to legislative non-compliance. | Waste | -3 | 3 | -9 | Although completing a site waste management plan (SWMP) is no longer a legal requirement, RCL will produce one. The SHEQ Dept. will produce the SWMP subject to any agreed-upon thresholds. The SWMP and the updating process will be via the BRE SmartWaste online platform. The SHEQ Dept. will regularly undertake subsequent updates, not exceeding three months. Additional updates may be undertaken if significant scope changes or additional wastes are identified. A log of when the plan was monitored and any outcomes will be maintained. Audit Process Management of Hazardous & Non-Hazardous Waste Waste Duty of Care (DoC) Written Information RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 11: Waste | -3 | 1 | -3 | MGL Group / Supply Chain | On-site recycling opportunities. Publicity from the management of a particular aspect of the works. Set printers to print on both sides by default. Do not print out emails and other documents unless it is really necessary. Use hand driers instead of hand towels.
Pre-Construction Construction | Responsible use of Materials | Timber will be used on-site | Risk of using non-sustainable timber on-site. | Materials Procurement | -3 | 3 | -9 | All timber products specified/purchased for either temporary or permanent inclusion in the works will be certified as legally and sustainably sourced, as defined by the UK Government Central Point of Expertise on Timber (CPET). FSC and PEFC are the two Certification schemes currently approved by CPET. Purchase orders will reinforce the requirements. Procurement Policy Sustainability Policy RAMS Compliance Evaluation Process CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section: 9.2.3 (Timber) and Section 9: Appendix 1(Legal and Sustainable Timber and Timber Product Procurement) | -3 | 1 | -3 | MGL Group / Supply Chain
Pre-Construction Construction | Responsible use of Materials | Use of Cement, Glass and Steel. | Risk of using materials that have not been responsibly sourced. | Materials Procurement | -3 | 3 | -9 | To reduce the climate change impacts of the cement, glass, and steel manufacturing process, RCL will endeavour to procure from manufacturers who can demonstrate an established strategy for CO2 emission reduction, which may include maximising the recycled content of their products. In the case of reinforcing bar, the CARES Certification Scheme will be required. This scheme includes requirements regarding environmental impact issues for manufacturers seeking certification. Where practicable, we will only procure/specify sustainably sourced materials certified to the framework of BES 6001 Responsible Sourcing Sector Certification Schemes for Construction Products - specification. Procurement Policy Sustainability Policy RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section: 9.2.7 Cement, Glass and Steel | -3 | 1 | -3 | MGL Group / Supply Chain
Pre-Construction Construction | Ecology | Protected species are present, or may be present, on-site. | Disturbance of, or harm to wildlife, habitats or nests. | Ecology | -4 | 3 | -12 | Before starting work on site, contract documentation, existing studies, surveys, and Environmental Statements/Environmental Impact Assessments will be reviewed to determine how the construction works may impact ecology and wildlife. This will be repeated and reviewed immediatly prior to the BRS placement operation, and recorded and logged within the BRS varidation document for the permit surrender. Protected species are not anticipated Early consultation with the relevant Statutory Nature Conservation Organisation (SNCO) will be sought if there is a potential impact on ecology or wildlife during or as a result of construction, but this is not expected. Additional considerations will be undertaken prior to the BRS placement works. Bats: Low levels of bat activity were recorded, with no roosts found, but three trees have potential for hibernation roosts. Control: Pre-work checks, supervision by a licensed bat ecologist, and provision of bat boxes. Breeding Birds: Nesting birds may be present in woodland, scrub, and buildings. Control: Nest checks will be conducted within 48 hours of work during March–August; work is to stop if active nests are found; the ecologist's advice is to be followed. Invertebrates: Loss of habitat for grayling and wall butterflies. Control: Ecological Clerk of Works (ECoW) supervision of vegetation clearance, retention of larval food plants, and creation of suitable habitat on and off-site. Should any species be found on site, the Senior RCL Person present at the time of the incident will immediately notify the Client's Senior Person, enabling mitigation measures to be deployed. A General Code of Practice when working with ecologically sensitive areas will be developed (CIP 7.4: Construction General Code of Practice) Tool Box Talks - Nature Conservation Additionally, refer to the CIP Environmental Manual, Section 07 - Ecology, for information on individual species. RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register | -4 | 1 | -4 | MGL Group / Supply Chain | Habitat Creation. Ecological Enhancement. Publicity from the management of a particular aspect of the works.
Pre-Construction Construction Post Construction | Ecology | Invasive species are present, or may be present, on-site. | Invasive plants may be inadvertently spread through relocation of infested soil, regrowth from viable fragments, or transportation by water of riverbank and aquatic species. | Waste, Water, Contaminated Land, Materials, Ecology | -1 | 1 | -1 | Japanese knotweed, Japanese rose, New Zealand pigmyweed, and other Invasive Non-Native Species are present on the site. Control: Exclusion zones, biosecurity measures, and eradication methods will be implemented and supervised by the Ecological Clerk of Works (ECoW). Tool Box Talks - Nature Conservation Additionally, refer to the CIP Environmental Manual, Section 07 - Ecology, for information on individual species. RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section: 7.15 - 7.19 Invasive Plant Species INNS burial, movement or placement onsite will not be undertaken without correct environmental approvals etc in place. If/when these works occur, they will not be undertaken at the same time as the BRS placement to avoid cross-contamination of the BRS. | -1 | 1 | -1 | MGL Group / Supply Chain | Publicity from the management of a particular aspect of the works.
Pre-Construction Construction Post Construction | Ecology | Trees (including TPO trees) and hedgerows may be affected by the works. | Potential damage to trees. Potential damage to visual / natural environment. Loss of habitat. Disturbance of protected species. | Materials, Ecology | -1 | 1 | -1 | No specific tree protection measures had been reported to RCL at the time of writing. If works must be undertaken within the root protection area (RPA), special alternative protection measures will be required, and the work will be carried out following the recommendations of Section 7 of BS 5837:2012. Otherwise, entry into the RPA will not be permitted, and the RPA will not be used for material storage. The RPA required will be calculated as an area equivalent to a circle with a radius 12 times the diameter of the stem measured at a point 1.5m above ground level. Tool Box Talks - TBT - 3031 - HE4 – Working Around Trees and Hedgerows RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register British Standard BS5837: 2012 Trees in Relation to Design, Demolition and Construction – Recommendations CIP Environmental Manual Section: 7.19 Trees and 7.20 Hedgerows | -1 | 1 | -1 | MGL Group / Supply Chain | Publicity from the management of a particular aspect of the works.
Pre-Construction Construction Post Construction | Heritage and Archaeology | Historic (Listed or otherwise protected) structures or other archaeological remains known or suspected or potentially affected by the planned work. | Damage to known heritage features and discovery of heritage features during the works. | Heritage | -1 | 1 | -1 | The site is located in an area with local and national heritage interest. Two nearby listed buildings (the war memorial and the West Staithes) have been identified as potentially sensitive to visual and aural impacts during construction. There are also historic features within the site, including ridge and furrow earthworks, a railway footbridge, and a railway overbridge abutment. • A Cultural Heritage Desk-Based Assessment and Heritage Statement has been completed, identifying significant effects and proposing mitigation. • Temporary impacts will be mitigated through standard environmental procedures, including screening, careful siting of compounds, and advance notice to the community for disruptive activities (e.g., hammer piling). • The Construction Traffic Management Plan will designate routes and schedules to reduce disruption near heritage assets. • The ridge and furrow earthworks and historic field boundary will be preserved and kept in situ as open space, acting as a green buffer between the development and residents. • The railway footbridge and overbridge abutment will be retained as part of the masterplan, maintaining links to the site’s industrial heritage. • Woodland planting will be used to reduce the visual impact of the development on heritage assets, notably the listed War Memorial. • Access to national trails, including the England Coast Path, is not anticipated to be affected. Tool Box Talks - TBT - 3028 - HE1 – Archaeology RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 6: Heritage & Archaeology | -1 | 1 | -1 | Client
Construction | Ecology | Pest Control | Unnecessary suffering of pests and vermin during their extermination resulting in fines or imprisonment. | Ecology | -3 | 3 | -9 | Weil’s disease is a potential risk. All workers should wear appropriate protective clothing (thoroughly cleaned after each work period) and avoid exposing the skin, as infection can enter through abrasions. Lanolin-based barrier cream should be used before and after work; the hands, face, and forearms should be washed with hot water and soap. The nails should be scrubbed, but not the skin, as this can roughen the skin surface and increase the risk of infection. Even the most minor scratch should be washed and covered with an antiseptic dressing, and every trivial accident should be reported to the person in charge of the work. Eating, drinking, and smoking must not be allowed until the personal hygiene rules have been observed. Routine hygiene is easier to observe if mobile vans contain toilets, proper hot water washing facilities, and first aid on site. Exposure to contaminants, whether in solid, liquid, or gaseous form, can affect the eyes. Hands should be kept away from the face while at work. If the eyes become accidentally splashed or feel irritated, the affected person should leave the workplace and obtain first aid. Only specialists will exterminate pests. From an animal welfare point of view, humane deterrence and prevention are always better. If a problem has already arisen, then the correct use of traps may result in fewer welfare problems than rodenticides. However, the humaneness of lethal methods may vary considerably according to how they are used. | -3 | 1 | -3 | MGL Group / Supply Chain
Pre-Construction Construction | Statutory Nuisance | Noise and Vibration will be resulting during normal working hours. | Stakeholder Disturbance. Disturbance of Wildlife. Complaints to EHO - Section 60 Notices. | Nuisance | -3 | 4 | -12 | RCL will verify contract planning permissions to ensure conformance to any specific conditions regarding nuisance management, as well as to any prescribed restricted working hours. 07:30 and 18:00 (Mon-Thu), 07:30 and 15:30 (Fri) and 07:30 and 13:00 (Sat). No works will be permitted on Sundays and Bank Holidays unless agreed in writing with NCC. The site is surrounded by a mix of: Industrial/previously developed land (including hardstanding, sealed surfaces, and remnants of the power station), Residential areas (adjacent to the south of the site), Woodland and scrub (some planted, some naturally regenerated), Estuarine and coastal habitats (mudflats, salt marsh, dunes, and intertidal zones nearby). The positioning of loading areas and entrance and egress points will be given careful consideration so that sensitive receptors are not exposed to potential nuisance issues. Before site work commences, stakeholders will be informed of the works (by QTS), and regular communication will keep them informed about current progress and forthcoming works. Best Practicable Means (BPM) will always be used to mitigate the effects of noise and vibration. Where practicable, low-noise and vibration equipment and methods will be used. If not available, works will be planned/timed to minimise disturbance to neighbours. If not possible, acoustic screens will be used. Equipment will be well-maintained and not left running needlessly. White Sound & Multi-frequency Alarms and/or banksmen should be used for HGVS; beeper-type reversing alarms should not be used where practicable. All identified operations will follow the Environmental Nuisance Control Hierarchy (Eliminate, Reduce, Isolate, and Control, E.R.I.C.). Tool Box Talks - TBT - 3032 - NU1 – Be a Good Neighbour, TBT - 3033 - NU2 – Dust and Air Quality and TBT - 3034 - NU3 – Noise and Vibration Stakeholder Communication Form Stakeholder Communication Register Stakeholder Communication - Contract News Stakeholder Communication - Notification of Work BRE 456 Control of Dust and Emissions from Construction and Construction – Good Practice Guide Refer to CIP Environmental Manual Section 10: Nuisance | -3 | 1 | -3 | MGL Group / Supply Chain
Pre-Construction Construction | Statutory Nuisance | Noisy works will be required outside normal working hours (e.g. power floating large pours, deliveries requiring road closures). | Stakeholder Disturbance. Complaints to EHO - Section 60 Notices. | Nuisance | -3 | 3 | -9 | No work will be undertaken outside of permitted working hours without the express permission of the client and, where appropriate, the permission of the local planning authority (under application to extend, etc.). 07:30 and 18:00 (Mon-Thu), 07:30 and 15:30 (Fri) and 07:30 and 13:00 (Sat). No works will be permitted on Sundays and Bank Holidays unless agreed in writing with NCC. Stakeholder Communication and associated processes/information sources as noted above. RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 10: Nuisance | -3 | 1 | -3 | MGL Group / Supply Chain
Pre-Construction Construction | Statutory Nuisance | Site conditions or activities will lead to excessive dust from vehicular movements. Site conditions or activities will lead to excessive dust (construction, Construction etc.). | Dust Nuisance to Stakeholders and Wildlife / Ecology. Complaints to EHO - Section 60 Notices. Disruption of normal activities from dust Contamination of goods and materials from dust. Contamination of open water from dust Exposure to asbestos and other hazardous substances (Harm). Contamination of the surrounding environment. | Nuisance, Waste, Water, Contaminated Land | -3 | 3 | -9 | Dust and odour generation will be minimised, and where possible, we will contain effects within the site boundaries by using the most effective and practical solution for the site. Daily weather reports and visual observations will be reviewed and discussed at the start of each working day. Where weather reports indicate inclement weather that may impact the works, the RCL Site Manager will complete the Dust Management Plan. The Dust Management Plan will be completed as routine and reactive relative to the conditions. Site Management: All dust and air quality complaints will be recorded, the cause(s) identified, appropriate measures to reduce emissions taken promptly, and the measures taken. The complaints log will be made available to the Client upon request. Any exceptional incidents that cause dust and air emissions will be recorded (on or off-site). In addition, the action taken to resolve the situation will be recorded. Monitoring: Daily on-site and off-site inspections will be conducted where receptors (including roads) are nearby to monitor dust. When abnormal results are found, they will be recorded in the site diary. The person(s) accountable for air quality and dust issues on site will increase the frequency of site inspections when activities with a high potential to produce dust will be carried out during prolonged dry or windy conditions. Dust monitoring will be reviewed to check for unexpected dust levels or statutory nuisance occurrences. Breaches and elevated dust levels will result in further control measures being identified and implemented, including working methods, mitigation, and work timing. Further control measures will also include adopting a different mitigation strategy that will include real-time dust monitoring techniques to determine the deposition of dust and the level of dust soiling, dependent on the sensitivity of the environment. QTS will be notified of such proposals to ensure agreement from all parties. The Site Specific RAMS will outline the project-specific mitigation measures to be employed on the project. Tool Box Talks - TBT - 3032 - NU1 – Be a Good Neighbour, TBT - 3033 - NU2 – Dust and Air Quality and TBT - 3034 - NU3 – Noise and Vibration CIP Environmental Manual Section 10 Nuisance Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register | -3 | 1 | -3 | MGL Group / Supply Chain
Pre-Construction Construction | Statutory Nuisance | Lighting arrangements may disturb stakeholders or wildlife. | Light shining into adjacent stakeholder properties. Disturbance of wildlife / ecology. Complaints to EHO - Section 60 Notices. | Nuisance, Ecology | -3 | 2 | -6 | Potential effects of excessive light intrusion into residential properties, potential ecological impact, the influence on the night sky, and visual amenity aspects will be considered. RCL will target using artificial lighting only during the hours of darkness, when there are low levels of natural light, or during specific work methods or phases. Where a high level of illumination is required, it will be suitably controlled to minimise the effect on local stakeholders, the environment, wildlife, ecology, and road and Construction traffic. It will be limited to the specific construction task area and for the length of the task only. Tool Box Talks - TBT - 3032 - NU1 – Be a Good Neighbour Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 10: Nuisance | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Statutory Nuisance | Stakeholder communications received including comments, compliments and complaints. | Reputational damage or enhancement. Complaints to EHO - Section 60 Notices. | Nuisance | -3 | 2 | -6 | Where a communication is either issued or received, all relevant details will be immediately logged. All actions arising from communications will be closed out within an appropriate time frame to satisfy the stakeholder. Stakeholder Communication Form Stakeholder Communication Register Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Planning Permissions | Specific planning permissions are in place covering the contract. | Non-compliance with planning permissions resulting in negative environmental impact. | Contaminated Land Design Procurement Heritage Ecology Contaminated Land Materials Nuisance Waste Energy and Climate Change Water | -3 | 2 | -6 | Planning restrictions regarding out-of-hours work are in place. No works will be permitted on Sundays and Bank Holidays unless agreed in writing with NCC. Compliance Evaluation Process CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Contaminated Land | Working to an agreed remediation strategy. | Failure to remediate contaminated ground in accordance with the agreed remediation strategy. | Contaminated Land Waste Water | -3 | 1 | -3 | Recent ground investigations have identified localised contamination at the Cambois Data Centre Campus, specifically asbestos fibres in the soils. To ensure that potential risks to human health, controlled waters, and construction workers are minimised, Dunelm Geotechnical & Environmental Ltd. have been appointed to prepare and implement remediation strategies for the project.. Site-Specific Remediation Strategy CL: AIRE Code of Practice Site Materials Input Record Material Testing Instruction Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 8.6: Remediation treatments | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Contaminated Land | Stockpiling of contaminated land is required. | The spread of contamination to uncontaminated ground or watercourse. | Contaminated Land Waste Water | -3 | 1 | -3 | RCL will not stockpile contaminated soil unless it cannot be avoided. If necessary, we will stockpile only on a hard-standing area to prevent contamination of the underlying ground; this will be noted on any Site-Specific Remediation Strategy produced at the time. RCL will cover stockpiled material to prevent wind-blown dust (potentially contaminated), rainwater ingress, and surface drainage from the stockpiled area. Site-Specific Remediation Strategy CL: AIRE Code of Practice Site Materials Input Record Material Testing Instruction Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 8.6: Remediation treatments | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Contaminated Land | Contaminated Land may be discovered during the works. | The spread of contamination to uncontaminated ground or watercourse. | Contaminated Land Waste Water | -4 | 2 | -8 | During boring, digging, excavating and similar operations, plant operators and operatives will observe the uncovered ground and watch out for visual signs of contamination; additionally, the release of noxious fumes, petrol, oils, solvents, chemical residues and smells that may indicate contamination. When contamination is suspected, RCL will: 1. Stop work immediately. 2. Report the discovery to the Site Manager, who must seek expert advice. 3. Seal off the area and contain any spread of contaminants. 4. Clear the affected area of the site to ensure there is nothing that could cause a fire or explosion 5. Contact the regulator (usually the Local Authority) if it is suspected or likely that contamination has been found. 6. Ensure that the suspected contamination is tested and characterised, and agree on changes to any existing remediation plan or produce a remediation plan if none exists. 7. Follow the remediation plan to remediate the land. Works will only be restarted once the nature and extent of the contamination have been confirmed and, if required, controlling strategies developed. Compliance Evaluation Processes RAMS CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 8: Contaminated Land | -4 | 1 | -4 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Energy and Climate Change | Energy Consumption / Carbon Production including transport. | Energy use leading to depletion of resource and increase in CO2 | Energy and Climate Change | -3 | 2 | -6 | To minimise the impact of the construction process on the environment, RGL will measure all resources used. We will specify efficient temporary site accommodation, with a focus on high thermal efficiency (insulation) as a minimum. Other measures that will be considered will include controls for lighting, heating, and ventilation and alternative on-site energy sources, e.g., solar PV, and efficient LED lighting. We will specify efficient equipment to be used on-site. We will utilise LED lighting for site lighting, e.g., hoarding lights, and where practicable, we will also consider LED lighting for task and general emergency lighting. We will identify alternative options to supply energy requirements more efficiently on-site, following MGL Group's carbon reduction plan/strategy. We will ask plant suppliers about any options available and ask for life cycle costs rather than hire / purchase costs. Where opportunities exist for verified carbon reduction projects, these will be considered and implemented if viable. PPN-0621-Carbon-Reduction-Plan MGL Group Tool Box Talk - Resource Efficiency RAMS SHEQ Objectives and Targets Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register RAMS CIP Environmental Manual Section 12: Energy, Climate Change and Greenhouse Gas Mitigation | -3 | 1 | -3 | Client / MGL Group / Supply Chain | Switching off equipment that is not being used. Not leaving equipment on standby (e.g. monitors left on overnight). Switching off lights at the end of the day. Unplugging chargers. Filling kettles only with the amount of water that is needed. Not using air conditioning units unnecessarily. Fitting energy-saving light bulbs. Publicity from the management of a particular aspect of the works.
Pre-Construction Construction Post Construction | Water Consumption | Water will be consumed on the project. | Poorly managed water use leading to water scarcity. | Water | -2 | 2 | -4 | To conserve water and use resources efficiently, where RCL is responsible for the supply, main water supplies will be metered to allow site water use to be monitored and managed. Before starting work on site, if a meter is not already in place, the local water supplier will be contacted to arrange for a metered standpipe to be installed on all main water supply points. If temporary supplies of mains water are to be obtained through a standpipe, not only will the consent of the water undertaker be obtained, but also the successful completion of the Calm Network training to ensure the correct procedures for use are followed, to prevent the risk of serious implications for drinking water quality. SHEQ Objectives and Targets RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 13: Water | -2 | 1 | -2 | Client / MGL Group / Supply Chain | Publicity from the management of a particular aspect of the works. Fitting taps with automatic shut off. Fitting ‘save-a-flush’ or a similar device to all cisterns. Fitting PIR (passive infrared) devices in close proximity to urinals. The urinal will then flush only when used resulting in significant savings.
Pre-Construction Construction Post Construction | Water | Working will take place in or near a Main Watercourse (A main river is defined as any watercourse shown as a ‘blue line’ on the flood map published by the EA / NRW / SEPA.) | Poorly managed works leading to water pollution. | Water | -1 | 1 | -1 | There are several on-site and Adjacent Watercourses; however, none are main rivers. Permits and Consents Checklist Tool Box Talk Suite - Pollution Prevention RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 13: Water | -1 | 1 | -1 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Water | Working will take place within 10m of an Ordinary Watercourse (An ordinary watercourse includes any other river, stream, ditch, drain, cut, dyke, sluice, sewer (not public sewer), dry ditch or passage through which water flows or may flow.) | Poorly managed works leading to water pollution. | Water | -3 | 2 | -6 | Project Wind, located at a former power station, is identified as being at a very low risk of surface water flooding across most of its area. The site is approximately 102 hectares and is a mix of impervious hardstandings, vegetation, PFA mounds, and semi-natural ground. Localised areas near the Cow Gut and Maw Burn outfalls may fall within a higher flood risk zone due to tidal influence. The primary pollution concern is managing surface water runoff to prevent the spread of suspended solids, such as silt and sediment. In addition, the RCL The Surface Water Management Plan for the project outlines several key strategies and control measures to manage surface water during the construction phase and prevent contaminants from leaving the site. This includes the construction of temporary swales, catch pits, and silt traps, as well as the re-profiling of Maw Burn and Cow Gut to replace culverts with open channels. Earthworks will be designed with specific falls to direct runoff away from active areas and into temporary sumps, where collected water can be pumped out. Silt fences will be installed in disturbed areas to capture and control runoff, with regular inspections to ensure their effectiveness. To prevent contamination, designated concrete washout areas with containment systems will be established, and spill kits will be kept readily available for immediate response to spills. Furthermore, dust control measures like water spraying will be employed to minimise dust generation and prevent it from entering watercourses. Finally, all construction waste, materials, and fuels will be stored in designated areas away from watercourses and drainage systems, with secure, bunded storage for fuels and oils to prevent leaks and spills. Tool Box Talk Suite - Pollution Prevention RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 13: Water | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Water | Water will be discharged from the contract. | Discharge to ground or watercourse due to poorly controlled waste water / liquid. | Water | -1 | 1 | -1 | Discharges to water will be managed in accordance with any and all discharge consent conditions. This ensures that all necessary permits, licenses, and consents are obtained to meet regulatory standards. The risk of non-compliance is minimised through specific monitoring and testing requirements outlined below: • Pollution Prevention Plan: Develop and implement a plan to minimise contaminants generated, such as silt, and prevent contaminated water from reaching water bodies. • Emergency Protocols: Prepare emergency control measures, such as silt fences, sediment basins, or other containment systems, to capture and treat unplanned discharges. • Water Quality Monitoring: Regularly monitor key parameters such as suspended solids, turbidity, pH, and chemical oxygen demand (COD) using appropriate equipment and methods. • Laboratory Analysis: Send water samples to accredited laboratories for detailed analysis. Tool Box Talk Suite - Pollution Prevention RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 13: Water EA position statement: Dewatering building sites and other excavations: environmental permits. | -1 | 1 | -1 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Water | Work will be abstracted. | Negative effect on local hydrology due to the abstraction of water. | Water | -1 | 1 | -1 | No water will be abstracted. Tool Box Talk Suite - Pollution Prevention RAMS Compliance Evaluation Process CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 13: Water | -1 | 1 | -1 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Materials | Materials will be stockpiled during the course of the contract. | Discharge to watercourses or the air, in the form of dust, due to poor stockpiling. | Water Nuisance Materials | -3 | 2 | -6 | In planning the site establishment, consideration will be given to the effect of runoff when creating or adding to stockpiles of soil or similar material. RCL will avoid placing them near watercourses as silty runoff may cause pollution. Storage requirements for topsoil. - Short-term storage (less than a month): 1 meter maximum (ideally 0.5-1 meter) - Long-term storage (more than a month): 0.5-1 meter maximum Lower storage heights are always preferable for maintaining topsoil quality. They help: - Prevent compaction. - Retain beneficial soil biota (micro-organisms). - Minimise nutrient loss. Therefore, while a maximum of 1 meter is acceptable for short-term storage, aiming for lower heights whenever possible is the best practice to ensure the quality and viability of the topsoil. RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 9.5: Storage and Distribution of Solid Materials | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Materials | Materials will be delivered to and stored on site prior to use. | The unnecessary generation of waste due to the poor storage of materials, their inefficient use, and the disposal of materials with potential re-use value. | Waste Materials Procurement | -3 | 2 | -6 | Materials storage locations will be carefully considered. RCL will encourage good on-site materials management, which will reduce overall waste. Materials will not be stored in any area at risk from flooding, wind, vandalism, or where a release or escape could lead to off-site pollution. We will store perishable materials inside, undercover, or in containers. Materials will not be stored near drains or watercourses where overspill could lead to pollution. Before arriving on-site, we will ensure the correct measures to deal with the material are available, i.e. fire fighting measures, spill kits, drip trays, sheeting, etc. All materials will be identified, assessed and stored in compliance with the COSHH Regulation, where applicable, and a COSHH assessment will be produced for any applicable materials being stored. RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 9.3: Prevention of Material Waste CIP Environmental Manual Section 9.5: Storage and Distribution of Solid Materials | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Oils, Fuel and Chemicals | There will be Delivery, Storage, Refuelling, Bunding and Disposal of Oils, Fuel and Chemicals (>200 litres). | Spillage of hazardous materials onto the ground or drainage systems due to accidents, incidents or container failure. | Waste Materials Water | -3 | 4 | -12 | Oils will be stored in a container of sufficient strength and structural integrity to ensure that it is unlikely to burst or leak in ordinary use. General: Any oil container with a capacity greater than 200 litres shall be stored within a Secondary Containment System, having a capacity of at least 110% of the volume of the container for a single container or, if there is more than one container, at least 110% of the largest container’s storage volume or at least 25% of the total volume (whichever is greater). Containment will be positioned or protected to minimise any risk of damage by impact. Mobile bowsers: Any bowser used on an RCL site will comply with the following regulations, and where a subcontractor brings a bowser onto the site, it will be checked to make sure it fully complies: Taps or valves permanently fixed to the unit through which oil can be discharged to the open will be fitted with a lock and locked shut when not in use. Where oil is delivered through a flexible pipe permanently attached to the unit, the pipe will be fitted with a manually operated pump or a valve at the delivery end that closes automatically when not in use. The pump or valve will be provided with a lock and be locked shut when not in use, and the pipe will be fitted with a lockable valve at the end where it leaves the container and will be locked shut when not in use. Any spillages will be dealt with promptly, in accordance with the Site Spill Response Plan. In the event of a significant incident (i.e., an incident resulting in a significant impact requiring management by external authorities and/or a high level of resources for response and remedy managed by external authorities, e.g., contamination of potable water), the responsible manager can immediately contact Adler & Allan, RCL emergency response contractor, on 0800 592 827. Emergency Preparedness and Response (refer to Adler & Allan 24/7 Emergency Spill Response contact details and guidance) RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 9.6.1: Oils and Chemicals | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Pre-Construction Construction Post Construction | Oils, Fuel and Chemicals | There will be Delivery, Storage, Refuelling, Bunding and Disposal of Oils, Fuel and Chemicals (<200 litres). | Spillage of hazardous materials onto the ground or drainage systems due to accidents, incidents or container failure. | Waste Materials Water | -3 | 4 | -12 | Where any drum is used for the storage of the oil in conjunction with a drip tray as a secondary containment system, it will be deemed sufficient if the tray has a capacity of not less than 25% of the drum’s storage capacity or if more than one drum is used at the same time with the tray, 25% of the aggregate storage capacity of the drums. Point of use: Containers in use at the workface, with a capacity of fewer than 200 litres, can be used legally without any form of secondary containment. However, the guidelines above will be followed to prevent spillage and subsequent pollution incidents. Refuelling Protocol: Refuelling and all tank filling will be carried out in the designated protected refuelling area. Suitably protected bowsers are only used where refuelling at the protected area is impractical due to the nature of the machinery in use. Remote filling points will be used. An emergency spill kit containing sand or suitable absorbent materials will be readily available in case of spillage in the main fuel storage area. All bowsers will carry an emergency spill kit where mobile refuelling is necessary. Bowsers must be equipped with an automatic cut-out mechanism. Valves and taps will not be left open unattended and will be locked when not in use. Personnel carrying out refuelling will be made aware of this refuelling protocol and trained in the use of spill kits and emergency procedures. Any spillages will be dealt with promptly, in accordance with the Site Spill Response Plan. In the event of a significant incident (i.e., an incident resulting in a significant impact requiring management by external authorities and/or a high level of resources for response and remedy managed by external authorities, e.g., contamination of potable water), the responsible manager can immediately contact Adler & Allan, RCL emergency response contractor, on 0800 592 827. Emergency Preparedness and Response (refer to Adler & Allan 24/7 Emergency Spill Response contact details and guidance) RAMS Compliance Evaluation Processes CIP Environmental Manual Section 03: Legislation Register/MGL Group Legal Register CIP Environmental Manual Section 9.6.1: Oils and Chemicals | -3 | 1 | -3 | Client / MGL Group / Supply Chain
Construction | Management of Burt Red Shale | BRS will be excavated from stockpiles and placed as an engineered general fill to Zone B as outlined in the BRS Engineering Proposal. The BRS will form part of the General Engineered Fill and must be placed in line with the Earthworks Specification | Release of dust during the excavation, haulage and placement of the BRS | Waste Materials Water | -2 | 3 | -6 | BRS placement works will be undertaken in strict accordance with the BRS Dust and Emissions Managament Plan (DEMP), which seeks to remove or reduce (to an acceptable level) the impact of dust release during the BRS placement and to reduce the risk of impact to local receptors. Regular review and adjustment of the opperation, including pausing of the works during unfavourable conditions. Regular review and adjustment (following inspection and audit) of the BRS DEMP to be undertaken by senior management | -1 | 1 | -1 | Client / MGL Group / Supply Chain
Construction | Management of Burt Red Shale | BRS will be excavated from stockpiles and placed as an engineered general fill to Zone B as outlined in the BRS Engineering Proposal. The BRS will form part of the General Engineered Fill and must be placed in line with the Earthworks Specification | Placement of BRS outside of the accepted area of deposition, or outside of accepted standards of engineering | Waste Materials Water | -2 | 3 | -6 | The placement of the BRS is to be undertaken in strict accordance with the BRS Engineering Proposal, which outlines the location, specification, depth etc of the BRS placement. TBT and Task-Specific briefings are to be presented to the delivery team to ensure the works are undertaken correctly and in line with the allowable activities under the Permit. Regular inspections and reporting to be undertaken to ensure delivery procedures are aligned with the approved practices outlined in the Permit documents. BRS depostion is to take place within a defined area onsite which is not to be exceeded or adjusted. The BRS is to be placed in a single 'block' (i.e. not layered with other material streams) and in an unbroken area onsite for simple recording and management. Future excavation/disposal/re-use of BRS is not considered in this suite of documents. On completion, detailed surveys will be provided to all stakeholders so that future BRS management can be undertaken (i.e. for waste designation purposes during future excavation works). | -1 | 1 | -1 | Client / MGL Group / Supply Chain
Construction | Management of Burt Red Shale | BRS will be excavated from stockpiles and placed as an engineered general fill to Zone B as outlined in the BRS Engineering Proposal. The BRS will form part of the General Engineered Fill and must be placed in line with the Earthworks Specification | BRS specific activity impacting sensitive features within the local area. | Waste Materials Water | -2 | 3 | -6 | A review of the Hydrological Pathway-Receptor model by Cundalls (as shown in the ESSD and Waste Recovery Plan) outline the breakage in the Pathway such the placement of BRS in the proposed location represents no risk to local features. Also see attached summary report outlining the distances from the BRS locations to the features detailed in the Nature and Heritiage Conservation Screening Report, which show all local features to lie outside of the screening distance. By following the DEMP and the Engineering Proposal, the risk of impacting local Environmentally sensitive features is reduced to an acceptable level | -1 | 1 | -1 | Client / MGL Group / Supply Chain
Construction | Management of Burt Red Shale | BRS will be excavated from stockpiles and placed as an engineered general fill to Zone B as outlined in the BRS Engineering Proposal. The BRS will form part of the General Engineered Fill and must be placed in line with the Earthworks Specification | Out of specification BRS is placed within the works which may have different physical characteristics than intended | Waste Materials Water | -2 | 3 | -6 | The BRS is only to be placed as a compliant General Fill material in accordance with the site wide earthworks specifications. The permit conditions only allow for natural aeration of the BRS, and therefore no additive modification (I,e, lime), or screening activities can take place prior to placement. Therefore it is key that the works are undertaken in a methodical manner with close attention paid to prevailing weather conditions. If BRS is found to be too wet to place, and the weather conditions are not conducive to aeration, then the operation may be paused till dry weather is forecast. Under no circumstance will non-compliant BRS be placed, or with BRS have any process applied to it other than natural aeration. | -1 | 1 | -1 | Client / MGL Group / Supply Chain
|  | Others |  |  |  |  | 0 |  | 0 |  | 0
Review & Approval
|  | Prepared By: MGL Group | Approved By: MGL Group | Approved By: Client / Others |  |  | Comments
Name: |  | Paul Hutchinson | John Pringle
Signature:
Date: |  | 2025-09-09 | 2025-09-09

## ENV List (hidden)
Contaminated Land
Design
Procurement |  | 1
Heritage | 1 | -1
Ecology | 2 | -2
Contaminated Land | 3 | -3
Materials | 4 | -4
Nuisance | 5 | -5
Waste
Energy and Climate Change
Water

## ENV Impact Rating
Calculation of Significance
Consequence x Likelihood = Overall Estimated Risk
Likelihood | 1 | 2 | 3 | 4 | 5
| Very Low | Low | Medium | High | Very High
Consequence | <10% | 10-40% | 40-60% | 60-80% | >80%
Opportunity | 1 | 2 | 3 | 4 | 5
-1: Insignificant | -1 | -2 | -3 | -4 | -5
-2: Minor | -2 | -4 | -6 | -8 | -10
-3: Significant | -3 | -6 | -9 | -12 | -15
-4: Severe | -4 | -8 | -12 | -16 | -20
-5: Very Severe | -5 | -10 | -15 | -20 | -25
Rating of 1 to 5: Opportunity | The environmental aspect requires management control to ensure that the opportunities are correctly managed. Information should be included within the Env Aspects Register and / or associated risk assessments and method statements (RAMS).
Risk Rating of -1 to -4: Not Significant | The environmental aspect does not require further management attention beyond the standard controls included within the environmental guidance contained in the Env Aspects Register.
Risk Rating of -5 to -11: Significant (medium priority) | The environmental aspect is significant and requires control through the CPP and / or RAMS, either through monitoring or an operational control procedure.
Risk Rating of -12 to -25: Significant (high priority) | The environmental aspect is significant and management control is of high priority. Managed through site environmental control plan in the CPP and / or RAMS.

## Legislation
The primary legislation (Acts) and secondary legislation (Statutory Instruments, i.e. Regulations/Orders etc.) creating specific obligations and offences are shown in each relevant Subsection. The primary legislation under which secondary legislation is made is not necessarily shown in the subsection but can be found in the introductory text to the legislation, which is available to view or download from http://www.legislation.gov.uk
General Legislation Enabling Enforcement: Primary Legislation (Acts etc.)
Natural Heritage (Scotland) Act 1991
Environment Act 1995
Building Act 1984
Building (Scotland) Act 2003
Natural Environment & Rural Communities Act 2006
Regulatory Enforcement and Sanctions Act 2008
Marine and Coastal Access Act 2009
Regulatory Reform (Scotland) Act 2014
Environment (Wales) Act 2016
Environment Act 2021
General Legislation Enabling Enforcement: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Environmental Civil Sanctions (England) Order 2010
The Environmental Civil Sanctions (Wales) Order 2010
The Environmental Civil Sanctions (Miscellaneous Amendments) (England) Regulations 2010
The Environmental Civil Sanctions (Miscellaneous Amendments) (Wales) Regulations 2010
The Natural Resources Body for Wales (Establishment) Order 2012
The Natural Resources Body for Wales (Functions) Order 2013
The Environmental Regulation (Relevant Offences) (Scotland) Order 2014
The Environmental Regulation (Liability where Activity Carried Out by Arrangement with Another) (Scotland) Order 2014
The Environmental Regulation (Significant Environmental Harm) (Scotland) Order 2014
The Environmental Regulation (Enforcement Measures) (Scotland) Order 2015
Design: Primary Legislation (Acts etc.)
Building Act 1984
Building (Scotland) Act 2003
Design: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Building (Scotland) Regulations 2004
The Building (Miscellaneous Amendments) (Scotland) Regulations 2013
The Building Regulations 2010
The Building Regulations &c. (Amendment) Regulations 2012
The Building Regulations &c. (Amendment) (Wales) Regulations 2013
Procurement : Primary Legislation (Acts etc.)
Modern Slavery Act 2015
Procurement: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Forest Law Enforcement, Governance and Trade Regulations 2012
The Timber and Timber Products (Placing on the Market) Regulations 2013
Modern Slavery Act 2015 (Transparency in Supply Chains) Regulations 2015
Heritage Legislation: Primary Legislation (Acts etc.)
Historic Building and Ancient Monuments Act 1953
Protection of Wrecks Act 1973
Ancient Monuments and Archaeological Areas Act 1979
Disused Burial Grounds Acts 1884 and 1981
National Heritage Act 1983
Protection of Military Remains Act 1986
Planning (Listed Buildings and Conservation Area) Act 1990
Natural Heritage (Scotland) Act 1991
Treasure Act 1996
Planning (Listed Buildings and Conservation Areas) (Scotland) Act 1997
National Heritage Act 2002
Marine (Scotland) Act 2010
Historic Environment (Amendment) (Scotland) Act 2011
Historic Environment Scotland Act 2014
Historic Environment (Wales) Act 2016
Heritage Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Town and Country Planning (Listed Buildings and Buildings in Conservation Areas) (Scotland) Regulations 1987
The Planning (Listed Buildings and Conservation Areas) Regulations 1990
The Planning (Listed Buildings and Conservation Areas) (Wales) Regulations 2012
Treasure (Designation) (Amendment)Order 2023
Ecology Legislation: Primary Legislation (Acts etc.)
Wildlife and Countryside Act 1981
Environmental Protection Act 1990
Town and Country Planning Act 1990
Protection of Badgers Act 1992
Countryside and Rights of Way Act 2000
Nature Conservation (Scotland) Act 2004
Natural Environment & Rural Communities Act 2006
The Wildlife and Natural Environment (Scotland) Act 2011
Anti-social Behaviour, Crime and Policing Act 2014
Infrastructure Act 2014
Ecology Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Wildlife and Countryside Act 1981 (Variation of Schedules) Order 1988, 1989, 1991, 1992, 1992, 1992(2), 1997, 1998 1999 (England) 2008, 4 June 2022 (Wales) 2008, (England and Wales) 2010, 2011, (Scotland) 2005, 2012, 2013
The Wildlife and Countryside Act 1981 (England & Wales) (Amendment) Regulations 2004
The Wildlife and Countryside Act 1981 (Amendment) (Wales) Regulations 2004
The Wildlife and Countryside Act 1981 (Amendment) (Scotland) Regulations 2001
The Conservation (Natural Habitats, &c.) Regulations 1994
The Conservation (Natural Habitats, &c.) (Amendment) (Scotland) Regulations 2004
The Hedgerows Regulations1997
The Town & Country Planning (Environmental Impact Assessment) (England and Wales) Regulations 1999
The Town & Country Planning (Environmental Impact Assessment) (Amendment) (Wales) Regulations 2006
The Environmental Impact Assessment (Scotland) Regulations 1999
The Environmental Impact Assessment (Uncultivated Land and Semi-Natural Areas) (England) Regulations 2001
The Environmental Impact Assessment (Uncultivated Land and Semi-Natural Areas) (Wales) Regulations 2002
The Environmental Impact Assessment (Uncultivated Land and Semi-Natural Areas) (Scotland) Regulations 2003
Town and Country Planning (Determination of Appeals by Appointed Persons) (Prescribed Classes) (Amendment) (England) Regulations 2008
The Town and Country Planning (Environmental Impact Assessment) Regulations 2011
The Town and Country Planning (Environmental Impact Assessment) (Scotland) Regulations 2011
The Town and Country Planning (Tree Preservation)(England) Regulations 2012
The Town and Country Planning (Tree Preservation Order and Trees in Conservation Areas) (Scotland) regulations 2010)
The Town and Country Planning (Trees)(Amendment)(Wales) Regulations 2012
The Conservation of Habitats and Species Regulations 2017
The Conservation of Offshore Marine Habitats and Species Regulations 2017
The Invasive Alien Species (Enforcement and Permitting) Order 2019
Contaminated Land Legislation: Primary Legislation (Acts etc.)
Environmental Protection Act 1990
Contaminated Land: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Contaminated Land (Scotland) Regulations 2000
The Contaminated Land (Scotland) Regulations 2005
The Contaminated Land (England) Regulations 2006
The Contaminated Land (Wales) Regulations 2006
Materials Legislation: Primary Legislation (Acts etc.)
Finance Act 2001
Modern Slavery Act 2015
Materials Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Control of Pollution (Oil Storage) (England) Regulations 2001
The Control of Substances Hazardous to Health Regulations 2002
The REACH Enforcement Regulations 2008
The Carriage of Dangerous Goods and use of Transportable Pressure Equipment Regulations 2009
The Chemicals (Hazard Information and Packaging for Supply) Regulations 2009
The Control of Asbestos Regulations 2012
The Forest Law Enforcement, Governance and Trade Regulations 2012
The Timber and Timber Products (Placing on the Market) Regulations 2013
The Ozone - Depleting Substances Regulations 2015
Modern Slavery Act 2015 (Transparency in Supply Chains) Regulations 2015
The Water Resources (Control of Pollution) (Oil Storage) (Wales) Regulations 2016
Nuisance Legislation: Primary Legislation (Acts etc.)
Control of Pollution Act 1974
Environmental Protection Act 1990
Noise and Statutory Nuisance Act 1993
Clean Air Act 1993
Clean Neighbourhoods and Environment Act 2005
Nuisance Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Statutory Nuisance (Appeals) Regulations 1995
The Statutory Nuisance (Appeals) (Scotland) Regulations 1996
The Statutory Nuisance (Appeals) (Amendment) (England) Regulations 2006
The Statutory Nuisances (Miscellaneous Provisions) (Wales) Regulations 2007
The Noise Emissions in the Environment by Equipment for Use Outdoors Regulations 2001
The Control of Noise (Codes of Practice for Construction and Open Sites) (Scotland) Order 2002
The Control of Noise (Codes of Practice for Construction and Open Sites) (England) Order 2015
The Noise from Audible Intruder Alarms (Wales) (Revocation) and Control of Noise (Codes of Practice for Construction and Open Sites) (Wales) Order 2017
Waste Legislation: Primary Legislation (Acts etc.)
Control of Pollution (Amendment) Act 1989
Environmental Protection Act 1990
Deregulation and Contracting Out Act 1994
Finance Act 1996
Finance Act 2018
Clean Neighbourhoods and Environment Act 2005
Waste (Wales) Measure 2010
Scrap Metal Dealers Act 2013
Landfill Tax (Scotland) Act 2014
Landfill Disposals Tax (Wales) Act 2017
Waste Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Controlled Waste (Registration of Carriers and Seizure of Vehicles) Regulations 1991
The Controlled Waste Regulations 1992
The Waste Management Regulations 1996
The Special Waste Regulations 1996
The Special Waste (Scotland) Regulations 1997
The Landfill (Scotland) Regulations 2003
The Hazardous Waste (England & Wales) Regulations 2005
The Hazardous Waste (Wales) Regulations 2005
The Criteria And Procedures For The Acceptance Of Waste At Landfills (Scotland) Direction 2005
The Waste (Scotland) Regulations 2005
The Environmental Permitting (England & Wales) Regulations 2007
The Waste Batteries and Accumulators Regulations 2009
The Waste Batteries (Scotland) Regulations 2009
The Carriage of Dangerous Goods and use of Transportable Pressure Equipment Regulations 2009
The Environmental Permitting (England and Wales) Regulations 2010
The Waste Information (Scotland) Regulations 2010
The Waste (Scotland) Regulations 2011
The Waste Management Licensing (Scotland) Regulations 2011
The Waste (England and Wales) Regulations 2011
The Waste (Miscellaneous Provisions) (Wales) Regulations 2011
The Landfill Tax (Qualifying Material) Order 2011
The Waste (Scotland) Regulations 2012
The Control of Asbestos Regulations 2012
The Controlled Waste (England and Wales) Regulations 2012
The Environmental Noise, Site Waste Management Plans and Spreadable Fats etc. (Revocations and Amendments) Regulations 2013
The Waste Electrical & Electronic Equipment Regulations 2013
The Environmental Protection (Duty of Care) (Scotland) Regulations 2014
The Scottish Landfill Tax (Qualifying Material Order 2016
The Control of Waste (Dealing with Seized Property) (England and Wales) Regulations 2015
The Hazardous Waste (Miscellaneous Amendments) Regulations 2015
The Hazardous Waste (Miscellaneous Amendments) (Wales) Regulations 2015
The Hazardous Waste (Miscellaneous Amendments) (Wales) Regulations 2018
The Waste (Meaning of Hazardous Waste and European Waste Catalogue) (Miscellaneous Amendments) (Scotland) Regulations 2015
The Unauthorised Deposit of Waste (Fixed Penalties) Regulations 2016
The Environmental Permitting (England and Wales) Regulations 2016
The Unauthorised Deposit of Waste (Fixed Penalties)(Wales) Regulations 2017
The Waste Enforcement (England and Wales) Regulations 2018
The Environment, Food and Rural Affairs (Miscellaneous Amendments) (England) Regulations 2018
The Waste (Circular Economy) (Amendment) Regulations 2020
The Waste (Miscellaneous Amendments) Scotland Regulations 2020
Energy and Climate Change Legislation: Primary Legislation (Acts etc.)
Climate Change Act 2008
Climate Change Act 2008 (2050 Target Amendment) Order 2019
Climate Change (Scotland) Act 2009
Climate Change (Emissions Reduction Targets) (Scotland) Act 2019 Energy Act 2011
Energy and Climate Change Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Building (Scotland) Regulations 2004
The Energy Performance of Buildings (Scotland) Regulations 2008
The Building Regulations 2010
The Building Regulations &c. (Amendment) Regulations 2012
The Energy Performance of Buildings (England and Wales) Regulations 2012
The Energy Performance of Buildings (England and Wales) etc. (Amendment) Regulations 2013
The CRC Energy Efficiency Scheme Order 2013
The CRC Energy Efficiency Scheme (Allocation of Allowances for Payment) Regulations 2013
The Energy Savings Opportunity Scheme Regulations 2014
The Fluorinated Greenhouse Gases Regulations 2015
The CRC Energy Efficiency Scheme (Revocation and Savings) Order 2018
Water Legislation: Primary Legislation (Acts etc.)
Control of Pollution Act 1974
Salmon and Freshwater Fisheries Act 1975
Highways Act 1980
Land Drainage Act 1991
Water Resources Act 1991
Water Industry Act 1991
Water Industry Act 1999
Water Industry (Scotland) Act 2002
Water Act 2003
Water Environment and Water Services (Scotland) Act 2003
Marine and Coastal Access Act 2009
Marine (Scotland) Act 2010
Flood and Water Management Act 2010
Water Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Trade Effluent (Prescribed Processes and Substances) Regulations 1989
The Trade Effluent (Prescribed Processes and Substances) Regulations 1992
The Control of Pollution (Applications, Appeals and Registers) Regulations 1996
The Groundwater Regulations 1998
The Anti-Pollution Works Regulations 1999
The Anti-Pollution Works (Scotland) Regulations 2003
The Control of Pollution (Oil Storage) (England) Regulations 2001
The Groundwater (England and Wales) Regulations 2009
The Water Resources Act 1991 (Amendment) (England and Wales) Regulations 2009
The Water Environment (Groundwater and Priority Substances) (Scotland) Regulations 2009
The Environmental Permitting (England and Wales) Regulations 2010
The Water Environment (Controlled Activities) (Scotland) Regulations 2011
The Marine Licensing (Pre-application Consultation)(Scotland) Regulations 2013
The Water Resources (Control of Pollution) (Oil Storage) (Wales) Regulations 2016
The Environmental Permitting (England and Wales) Regulations 2016
The Water Abstraction and Impounding (Exemptions) Regulations 2017
The Water Environment (Miscellaneous) (Scotland) Regulations 2017
The Environment Protection (Miscellaneous Amendments) (England and Wales) Regulations 2018
The Sustainable Drainage (Approval and Adoption) (Wales) Order 2018
The Water Environment (Controlled Activities) (Scotland) Amendment Regulations 2021
Data Capture and Reporting Legislation: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Companies Act 2006 (Strategic Report and Director’s Report) Regulations 2013
The Companies, Partnerships and Groups (Accounts and Non-Financial Reporting) Regulations 2016
The Companies (Directors’ Report) and Limited Liability Partnerships (Energy and Carbon Report) Regulations 2018
The Companies (Strategic Report) (Climate-related Financial Disclosure) Regulations 2022.
The Limited Liability Partnerships (Climate-related Financial Disclosure) Regulations 2022
Incident Management: Primary Legislation (Acts etc.)
Planning (Hazardous Substances) Act 1990
Planning (Hazardous Substances) (Scotland) Act 1997
Incident Management: Secondary Legislation (Statutory Instruments - Regulations, Orders etc.)
The Planning (Control of Major-Accident Hazards) Regulations 1999
The Planning (Control of Major-Accident Hazards) Scotland Regulations 2000
The Planning (Control of Major-Accident Hazards) Scotland Regulations 2009
The Environmental Damage (Prevention and Remediation) (Wales) Regulations 2009
The Environmental Liability (Scotland) Regulations 2009
The Control of Major-Accident Hazards Regulations 2015
The Environmental Damage (Prevention and Remediation) (England) Regulations 2015
The Environment, Food and Rural Affairs (Miscellaneous Amendments) (England) Regulations 2018

## Sheet1 (hidden)
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5