## Sheet1
Odour Implementation Plan Didcot STW
Review Date |  | 2024-01-01
Process Stage | Owner | Summary - Plan | Action | Challenges | Measures to mitigate | Timescale for completion
OCU |  | Odour control of Imported Sludge tank, Screened sludge pumping station, Inter Site import tank, mixer buffer tanks and PFT. | Refurbish /replace media in odour control scrubbing tower | Quote gained, funding granted via APS risk system. Risk 114816 on APS | Run odour control plant with existing media | AMP8
OCU |  | Install a visual liquid flowmeter | To confirm the FE flow into the biofilter, a visual liquid flowmeter should be installed | Waiting for quotes to be delivered from Framework contractor | Risk 114816 on APS | AMP8
OCU |  | Action recommendations laid out by monthly health checks | Action recommendations laid out by monthly health checks | Funding |  | Ongoing
Sniff testing |  | Implement sniff testing procedure | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | Resource | Site Round, Monthly health checks | 6 months from permit issues