## Sheet1
Odour Implementation Plan Banbury STW
Date |  | 2023-05-05
Process Stage | Owner | Problem | Plan | Action | Expected difficulties | Measures to mitigate | Timeframe
FtFT/P Project | Jon Gilliard | Additional PFT and sludge blending tank volume requires additional air extraction and odour control | Extension/replacement of existing OCUs planned as part of the FtFT / P project | 1. Expanding the capacity of the existing OCU that connects into two existing PFTs adjacent to that OCU to allow for one additional PFT 2. Expanding the capacity of the existing OCU adjacent to the Sludge Reception Tanks to cater for an additional Sludge Blending Tank Not finalised yet whether these extensions will require replacement of the existing units or modification to cater for increased flows | Exsisting equipment not suitable for upgrade | N/A | Q2 2025
Sludge reception tanks and sludge transfer well | Diana Goodwin | hatches are not secure, but Should be closed. Issue is sometimes they are left open, which is monitored | Replace the roof on sludge reception tanks and sludge transfer well | Risk raised in APS for funding. 106699 | Gaining funding | hatches are shut and or replaced after carrying out work in this location to prolong the life of the roof. | AMP8