## Sheet1
Odour Improvement Plan Basingstoke STW
Review Date |  | 2023-11-14
Process Stage | Owner | Plan | Action | Expected difficulties | Measures to mitigate | Timeframe
Odour Control Unit | Emma Wagstaff |  | Ensure recommendations from monthly inspections are actioned | funding | Site Round, Monthly health checks | ongoing
Sniff testing | Odour Specialist | Implement sniff testing procedure | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | Resource | Site Round, Monthly health checks | 6 months from permit issues