## Sheet1
Odour Improvement Plan Crossness STW
Review Date |  | 2023-11-05
Process Stage | Owner | Plan | Action | Expected difficulties | Measures to mitigate | Timeframe
THP OCU's | Dean Horsley | Refurbishment of OCUs | Refurbishment of THP blending tank OCU and buffer tank OCU 160891 and 160892 Funding achieved for repairs on THP OCU (fan replacement and other refurbishment work) 130486 - awaiting attendance to site to undertake work | achieving funding | Continue to operate current OCUs with associated checks and maintenance until refurbishment commences. | AMP8
Storm tanks | Maintenance Projects | Storm Tank Clean | Full storm tank clean |  | drain the tanks back as soon after storm as practicable –investigating ways of cleaning the tanks following the full cleans | 2023-12-01
GBT OCU | Leigh Hughes | GBT OCU | GBT OCU is currently local, PO has been raised to get this on SCADA |  | monthly health checks and site rounds | 2023-12-01
OCU | Dean Horsley & Leigh Hughes | Action recommendations laid out by monthly health checks | Action recommendations laid out by monthly health checks | Funding |  | Ongoing
Sniff testing | Odour Specialist | Implement sniff testing procedure | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | Resource | Site Round, Monthly health checks | 6 months from permit issues