## OIP
Mogden Odour Improvement Plan (OIP)
2023-12-15
Process Stage | Owner | What is happening that may lead to Odour? (4 weeks plus) | Action taken to mitigate odour issues during longer term remedial work | Plan - long term fix | Expected Difficulties | Measures to Mitigate | Time frame
East Inlet | Chantelle Dixon | Odour Issues Persist | Washed down as required. | Investigate wider root cause of odours in this area and reinstall drain covers which are missing. | Odourous due to the nature of the material | Frequent washdowns | Ongoing
Initial Screening | Chantelle Dixon | Poor performance of West Side Screens | Tanker out the E battery channel as required. | Refurbishment of West Side Screens is delievered. RAG still within the system means that tankering continues | None | Long term fix funding approved. Tankering as required. | Ongoing
PSTs | Joshua Callaway | Failure of scum removal traps on west side uncovered PSTs. Pumps out of operation and traps blocked. | Mitigation is robust with manual cleaning undertaken as required. | Ongoing refurbishment plan for all PSTs is in delivery. 4 PSTs awaiting completion | Process compliance making release of assets difficult | Manual cleaning as required. | 2024-05-01
OCU | Joshua Callaway | Action recommendations laid out by monthly health checks | Action recommendations laid out by monthly health checks | Ensure delivery of funded OCU Refurbishment projects, and Condition-Based Monitoring (CBM) of all OCU Assets across to site to uncover future investement needs. OCU11 has had c. £800k funding released for refurbishment. | Funding | Monitoring of Asset Availability and Operability of OCUs, and deployment of reactive maintenance where required. | Ongoing
Sniff testing | Odour Specialist | Implement sniff testing procedure | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | Implementation of Sniff Testing procedure as required | Resource | Site Round, Monthly health checks | 6 months from permit issues