## 1 - Read me
Using this Risk Register
Introduction
This Risk Register has been produced as part of the ncpms Risk Management System (initially know as 'Risk 3').
The user should only use the Risk Register after reading the relevant guidance documents within the Risk Management System
Any problems with using this spreadsheet should be reported to a member of the ncpms Risk Management System Development Group
Quality assurance
Ensure that the Risk Register is quality assured before its application as part of @Risk.
Pay particular attention to the following:
1. Complete the Revision Control worksheet each time the team amends the Risk Register.
2. When inserting new rows, ensure that the relevant formulae are copied down.
3. Ensure that the @Risk Output cells for each risk owner, sum the correct range of data.
4. On the Simulation Settings/Sampling tab, ensure that the 'inputs marked with collect' is checked (this ensures that the sensitivity test uses the correct inputs).
5. Repeat a simuation until you are happy that the outputs are precise enough for budget setting. You can obtain increased precision by increasing the number of model iterations.
6. To obtain stable results for the sensitivity test, a higher number of model iterations will be required.
6. After satisfactory generation of model results, ensure that you save the results.
6. Refer to the @Risk User Guide for a detailed explanation of @Risk functions.
Key to cell colours
Fixed value cells – do not change.
Only enter data into these yellow cells.
Formula cells which update automatically. They include error messages if insufficient data has been entered.
Programme buffer
| 1 | Included within the current Risk Register is the ability to quantify the time effect of risk occurring (that is, three point estimate; Least, ML, and Max) - only at residual risk stage.
| 2 | Assess whether each risk is likely to affect the critical path (that is, extend the duration of the project). It's likely that many risks will not extend the project and can be dealt with through day-day project management (this may involve use of additional staff or managed as a parallel activity).
This assessment can be supported by analysis of the CP within MS Project, if appropriate. This assessment has to be done already as part of setting the cost budget to make sure that there is no 'double-counting' of risk costs.
| 3 | For those risks that could affect the project duration, ensure there is no duplication or double counting of time effects and estimate the potential time delay (3 point estimate).
| 4 | Quantify the schedule buffer by either doing Monte-Carlo sampling or simple Expected Value (Residual Probability * ML value; and sum for all CP risks) - a simple EV approach could be justified to start with.
| 5 | You should capture the cost associated with programme extension in the cost value of the risks - need to ensure that there is no double counting.
| 6 | Suggest we use 50 percentile value as the basis for the risk buffer (but you should agree this with the client as there is no formal guidance on this yet).
| 7 | Test the reasonableness of the result and use this to set target end dates for project completion.
| 8 | Split the total buffer into elements associated within milestone/gateway deliverables within the project (and add milestone buffers to the programme).
| 9 | Test early in the project whether assumptions regarding the ability to manage time risks are being achieved (that is, at the first milestone deliverable).
| Incentivisation and risk budgets |  | See NEECA schedules for more detailed explaination (Schedule 5 Appendix A for Project Appraisal Reports (PAR) and Appendix B for post PAR).
| 1 | For strategies and Project Appraisal Reports - consultant and contractor risk budget calculated as 50 percentile of their owned risks as determined by the results of a Monte-Carlo analysis (client project approval based on 95 percentile of all risks including client retained risks).
| 2 | Following Project Appraisal Report (that is design, construction stage to post construction) - consultants and contractors are incentivised against the 50 percentile of all project risks, excluding client retained risks (client approval based on 95 percentile of all risks including client retained risks).

## 2 - Revision control
Version # | Description | Date
1 | Original Version within ncpms Risk Management System | 2006-09-01
2 | Main revisions as follows: | 2007-03-01
Colour coding of cells (to identify where data needs inputing)
Data Missing' error messaging
Risk ID column linked to Risk name (for clarity in sensitivity testing)
Split of 'Risk Description' into 'Source' and 'Consequence'
LOOKUP table for risk prioritisation
Additional text on 'Read Me' worksheet
3 | Included Monitor worksheet and Programme buffer calculation | 2009-08-01
Changed wording in Risk Output cells
Added 'Existing Safeguards' column
Changed 'mitigation' to 'response action' - in lne with good practice
Prioritisation sheet made clearer as to what inputs are required.
Minor formating to Risk Register to make clearer.
Prioritisation grades linked to Risk Register to make filling in register easier & quicker
Added ability to use @ Risk for assessing impact on programme of risks.
Changed Qualitative Matrix from 4*4 to 5*5 - consistent with good practice and PRINCE2
Added Risk Monitor Worksheet to aid monitoring and reporting of risk
Minor terminology changes to terms in risk register - consistent with PRINCE2
| Numerous minor changes as a result of a review into PRINCE 2 compliance including change from | 2009-09-16
client to customer
Changed product name from `NCPMS Risk Register' to `Project Risk Register' consistent with national ncpms management products project on Read Me worksheet.
Changed `NCPMS' to `ncpms' - On all worksheets
4 | Amended project information on Risk Register consistent with national ncpms management products project | 2010-03-01
Revisions to Project Team Risk Register |  | Date
Revision no | Description
1 | Initial draft for comments | 2011-08-01
2 | Fisrt run of Monte Carlo analysis | 2011-09-01

## 3 - Prioritisation
The Project Team must fill in the yellow cells in the table below to agree threshold ranges for probability and consequence at the start of the project. This will make it easier to prioritise which risks to focus on.
Probability | [6 empty] | Consequence / Impact
[9 empty] | Cost |  |  | Time
Scale | Likelihood |  |  |  | Min | Max | Scale | Max % of project | Project cost (£k) | Min (£k) | Max (£k) | Project time (wks) | Min (wks) | Max (wks)
VL | Unlikely to occur |  |  |  | 0% | 10% | VL | 0.5% |  | 0 | 50 | 52 | 0 | 1
L | Fairly likely to occur |  |  |  | 11% | 30% | L | 2% |  | 51 | 250 |  | 1 | 4
M | Likely to occur |  |  |  | 31% | 50% | M | 5% |  | 251 | 1000 |  | 4 | 12
H | More likely to occur than not |  |  |  | 51% | 70% | H | 10% |  | 1000 | 5000 |  | 12 | 24
VH | Almost certainly will occur |  |  |  | 71% | 100% | VH | + |  | 5000 | ~ |  | 24 | ~
Prioritisation Matrix - Used in Risk Register to help prioritise which risks to focus on.
! Important: Do not alter this matrix
Probability
|  | VL | L | M | H | VH
Consequence | VH | H | H | H | H | H
| H | M | M | H | H | H |  | Key
| M | L | M | M | M | H |  |  | High Priority ('Red Risk')
| L | L | L | L | M | M |  |  | Medium Prority ('Amber Risk')
| VL | L | L | L | L | L |  |  | Low Priority ('Green Risk')
Note on K7: TJW Add project value here to help define intervals of cost consequences
Note on N7: TJW Add project timescale here to help define intervals of time consequences

## 4 - Risk Register
PROJECT DETAILS
|  |  | Project name | Oxford FAS | Team and location |  | ncpms Reading |  | Information to help you assign scale of probability and impact based on threshold ranges set on Sheet 3 (Prioritisation) | [10 empty] | Information to help you assign scale of probability and impact based on threshold ranges set on Sheet 3 (Prioritisation)
|  |  | Project IB1S reference | ENVIMSE500177 | Project Executive |  | Richard Harding
|  |  | National project number |  | Senior User |  | Peter Collins
|  |  | Programme name |  | Senior Supplier |  | Roland Grzybek
|  |  | Date last updated | 2016-07-08 | Project Sponsor |  | Jo Larmour
|  |  | Version number | v4 | Project Manager |  | Vicky Ye
|  |  | Top 5 risks are highlighted in red in Risk ID column | [5 empty] | Probability | Cost | Time | [9 empty] | Probability | Cost | Time
[8 empty] | VL | 0 to 10% | £0k to £50k | 0 to 1 wks | [8 empty] | VL | 0 to 10% | £0k to £50k | 0 to 1 wks
[8 empty] | L | 11 to 30% | £51k to £250k | 1 to 4 wks | [8 empty] | L | 11 to 30% | £51k to £250k | 1 to 4 wks
[8 empty] | M | 31 to 50% | £251k to £1000k | 4 to 12 wks | [8 empty] | M | 31 to 50% | £251k to £1000k | 4 to 12 wks
[8 empty] | H | 51 to 70% | £1000k to £5000k | 12 to 24 wks | [8 empty] | H | 51 to 70% | £1000k to £5000k | 12 to 24 wks
[8 empty] | VH | 71 to 100% | £5000k to £~k | 24 to ~ wks | [8 empty] | VH | 71 to 100% | £5000k to £~k | 24 to ~ wks
Prev Risk ID | Risk ID | Task ID | Risk description |  | Risk status | Proximity | Risk owner (Customer, contractor, consultant, etc.) |  | Qualitative ranking (before response action) | [5 empty] | Response Action |  |  |  |  | Qualitative Ranking (After Response Action) | [5 empty] | Data for Quantitative Analysis | [6 empty] | Assumptions (for cost and time basis) |  | Risk Owners | [6 empty] | Programme Buffer | [9 empty] | Risk Buffer (owners)
|  |  | Source of risk | Consequence on project |  | (Date when risk becomes live) |  | Lesson learnt | Probability scale | Cost impact | Time impact | Cost+time impact | Risk priority | Existing safeguards in place | Response strategy | Action | Cost of mitigation (£) | Action owner | Completion date | Residual probability (%) | Probability scale | Cost impact | Time impact | Cost+time impact | Priority | Least cost (£) | Most likely cost (£) | Max cost (£) | MEV (£) | Risk occurs (Yes=1;No=0) | PERT | Cost value (£) |  |  | Customer | Consultant | Contractor | Others | Others 1 | Others 2 | All risks | Programme ID | Critical path (Y/N) | Probability (%) | Least time (wks) | Most likely time (wks) | Max time (wks) | Risk occurs (Yes=1; No=0) | PERT | Time value (wks) |  | Customer | Consultant | Contractor | Others | Others 1 | Others 2 | All risks
|  |  | Environmental | [29 empty] | Pre construction £30k / wk. Post Const contractor prelims £115k / wk + suppliers during construction £25k = £140k
1 | 1 |  | Unknown Contaminated land (non hazardous) fill material found which needs to go off site. | Costs, time, laboratory testing and removal of contaminated land before main works | Live |  | Customer | Need to get management systems in place before start on site | L | M | M | M | M |  | Undertake further investigations, monitor during construction | Localised investigations and archaeological trial holes. |  |  |  | 60% | H | M | M | M | M | 275000 | 550000 | 1050000 | 330000 | #NAME? | #NAME? | #NAME? | Assume 5% value of total volume (300,000m3) non-hazardous = 15000m3 of material. 15000 x £30m3 extra over cost = £450,000m + £0.1m (contractor costs dealing with material, delays + other suppliers ) = £0.55m. Known non-hazardous material is incl in base cost. Least assumes 2.5% of 300,000m3 and max 10% of 300,000m3 |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
1a | 2 |  | Works open up new pollution pathways in landfill sites requiring extensive remediation. | Costs and time increase | Live |  | Contractor |  |  |  |  | Data missing | Data missing |  | Consider further SI and agree mitigation plans if risk occurs | Project team to review |  |  |  | 25% | L | M | M | M | M | 190000 | 380000 | 760000 | 95000 | #NAME? | #NAME? | #NAME? | Costs based on 2 weeks of additional time on site to seal pathways, worst case 4 weeks work, best case zero. Use £115/wk plus £25k / week other costs for time plus nominal most likely cost of £100K for plant and additional alluvium = 2*140+100= £380,000, min,half and worst case double time delays |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME?
1b | 3 |  | Hazardous material is found in landfill areas | Costs, time, laboratory testing and removal of contaminated to licenced tip | Live |  | Customer | Need to get management systems in place before start on site | L | M | M | M | M |  | Undertake further investigations | Localised investigations and archaeological trial holes. |  |  |  | 60% | H | M | M | M | M | 325000 | 650000 | 1025000 | 390000 | #NAME? | #NAME? | #NAME? | Assume 20% of 25,000m3 non-hazardous material is actually hazardous = 20% x 25,000 x £110m3 EOC = £0.55m + £0.1m (contractor costs, testing, dealing with material, delays + other suppliers ) = £0.65m. Known contaminated material is incl in base cost. Least assumes 10% of 25,000m3 and max 30% of 25,000m3 |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
2 | 4 |  | Natural England objections | Delays and costs | Live |  | Consultant | Ongoing liaison with NE | L | L | H | H | M |  | Ongoing Liaison with NE | NEAS to maintain dialogue with NE |  |  |  | 10% | L | L | L | L | L | 25000 | 50000 | 75000 | 5000 | #NAME? | #NAME? | #NAME? | Potential risk for MG4 |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME?
3 | 5 |  | Protected species | Delays in relocating protected species. | Live |  | Customer | Need to ensure that Habitat Survey Commences as early as possible | VH | L | VH | VH | H |  | Identify areas where there are protected species - surveys ongoing | Undertake surveys & habitat/ecology surveys as soon as preliminary design options have been completed |  |  |  | 10% | VL | H | VH | VH | H | 560000 | 1680000 | 1824000 | 168000 | #NAME? | #NAME? | #NAME? | Assume £115k / wk contractor prelims and £25k ncpms / suppliers costs. ML - Delay 3 mths over the construction period = 12wks x £140k = £2m. Linear working so if found work will have to potentially stop. Least 4 weeks and max 16 weeks. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 4 | 6 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
4 | 6 |  | Historic England objections | Delay and costs | Live |  | Consultant | Need to engage as early as possible with Historic England | M | L | VH | VH | H |  | Ongoing liaison with HE | NEAS to maintain dialogue |  |  |  | 50% | M | L | L | L | L | 25000 | 50000 | 75000 | 25000 | #NAME? | #NAME? | #NAME? | Peoples time - likely area of interest Old Abingdon Road |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME?
5 | 7 |  | Archaeology creates delays and additional costs associated around more trial pits and investigations when on site under main contract | Time and costs | Live |  | Customer | Need to engage with archaeologist as early as possible | VH | H | M | H | H |  | Desk study, advance 3 stage archaeology planned and possibly additional trenching on site | Complete advance archaeology and review need for further advance work with consultees |  |  |  | 50% | M | M | M | M | M | 140000 | 560000 | 1120000 | 280000 | #NAME? | #NAME? | #NAME? | Works prob trial trenches and pits at selected locations. If archaeology found the contractor would stop work. Assume 2 wks to demob and 2 weeks to remob. 4 wks x £140k. Least 1 wks delay to work around the issue and max 8 wks |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
5a | 8 |  | Heritage and mitigation at Old Abingdon Road is more complicated than expected | Additional costs | Live |  | Customer | Evaluate trial trenches |  |  |  | Data missing | Data missing |  | Trial trenches in autumn 2016 | Ensure trial trenches undertaken to programme and evaluate results. |  |  |  | 50% | M | M | L | M | M | 100000 | 500000 | 1000000 | 250000 | #NAME? | #NAME? | #NAME? | Additional mitigation required once results known. Note that major finds might result in overall costs saving if we are able to route the new culvert nearer the railway. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 5 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
6 | 9 |  | Finding archaeological finds (during the trial trench) | Time and costs | Live |  | Customer |  |  |  |  | Data missing | Data missing |  | Desk study and possibly additional trenching on site | Further Archaeological ground investigations and ongoing consultation with heritage consultees |  |  |  | 80% | VH | L | M | M | H | 30000 | 60000 | 120000 | 48000 | #NAME? | #NAME? | #NAME? | Additional archaeological fees. Assume £7.5k/wk incl 5 archaeologists and exc and banksman. Assume risk occurs twice total delay Least 4 weeks ML 8 weeks Max 16 weeks |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
7 | 10 |  | Scope creep / lack of agreement with stakeholders for environmental enhancements (Design) - covered under Optimism Bias | Additional costs | Expired |  | Customer |  | M | M | M | M | M |  | Management of stakeholders expectations and enforce design freeze | Clarity on objectives and base line |  |  |  | 0% | H | L | M | M | M | 25000 | 50000 | 75000 |  |  |  |  | Assume extra time for Lot 3 and ncpms at say £50k | [10 empty] | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
7a | 11 |  | High specification finishes to structures or other unusual landmark features requested. | Additional costs | Live |  | Customer |  |  |  |  | Data missing | Data missing |  | Ongoing dialogue with EA specialist and external interested parties | Continue discussions |  |  |  | 40% | M | L | M | M | M | 100000 | 250000 | 500000 | 100000 | #NAME? | #NAME? | #NAME? | Costs assume significant additional cladding required. Base cost already assumes 50% additional costs due to enhancements. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
7b | 12 |  | Ecological trial pits highlight issues with future land use | Additional time | Live |  | Customer |  |  |  |  | Data missing | Data missing |  | Evaluate trial pits | Confirm seeding approach to trial pits |  |  |  | 20% | L | VL | L | L | L | 25000 | 50000 | 75000 | 10000 | #NAME? | #NAME? | #NAME? | Base costs assumes EA own 2nd stage. Additional time needed to resolve. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
8 | 13 |  | Due to issue over ability to continue grazing/farming second stage channel, plus need to keep clear of fencing/hedges, there is a risk that landowners will claim blight on the remainder of their landholding and force purchase of all landholding. | Additional costs and PR issues | Live |  | Customer |  |  |  |  | Data missing | Data missing |  | Evaluate ways to enable farming to continue on land outside 1st and 2nd stage channels | Continue discussions |  |  |  | 25% | L | VL | L | L | L | 25000 | 50000 | 75000 | 12500 | #NAME? | #NAME? | #NAME? | Corpus Christi and Co-op priority. Additional costs already within base costs so this assumes additional time required. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
9 | 14 |  | Scale of mitigation increases following discussions with consultees/planners | Increased cost from any requirement for increased mitigation measures | Live |  | Customer |  | L | L | L | L | L |  | Details to be discussed as early as possible to avoid significant changes | Ascertain site conditions and carry out designs at early stage |  |  |  | 25% | L | M | M | M | M | 250000 | 450000 | 750000 | 112500 | #NAME? | #NAME? | #NAME? | additional costs at £450k |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
10 | 15 |  | Discover invasive species | Impact on time | Live |  | Customer |  | L | M | M | M | M |  | Removal of any invasive species found on site | Contact EA and arrange for contractor to remove any invasive species |  |  |  | 20% | L | L | VL | L | L | 25000 | 86000 | 100000 | 17200 | #NAME? | #NAME? | #NAME? | Baseline will incl invasive species surveys. ML is localised delay to Existing channels (Japanese knotweed ) say 2 day delay and disposal costs of 100t x £300 / t |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
Engagement / Consultation
11 | 16 |  | Changes in the design will result in re-consultation. | Re - consultation | Live |  | Customer |  | M | L | H | H | H |  | Accept | Respond accordingly |  |  |  | 20% | L | L | M | M | M | 60000 | 180000 | 240000 | 36000 | #NAME? | #NAME? | #NAME? | Full staff / supplier costs delayed for 4 - 6 weeks at £30k per week |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME?
12 | 17 |  | Final design does not utilise Network Rail. Network Rail will have planning application Re-design of scheme if culverts. | Further work to manage reputation | Expired |  | Customer |  | VL | VL | VL | VL | L |  | Early communications to manage expectations. | Ensure that when engaging with NR as much information as deemed appropriate is available |  |  |  | 0% | L | M | M | M | M | 2000000 | 5000000 | 7500000 |  |  |  |  | Possible significant re-design and delay. Suggest at least 8 weeks of current full project costs. Undertake significantly more work to undertake a difficult solution as culvert route not viable | [10 empty] | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
13 | 18 |  | Public groups and individuals creating delays and objections | Additional liaison & time delay | Live |  | Customer |  | H | L | M | M | M |  | Discuss with stakeholders early | Engage in meetings with all stakeholders at early stages |  |  |  | 50% | M | L | L | L | L | 50000 | 75000 | 100000 | 37500 | #NAME? | #NAME? | #NAME? | Extra peoples time |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 4 | 6 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
Detailed Design
14 | 19 |  | Groundwater / fluvial modelling proves more difficult than anticipated | Additional costs | Live |  | Consultant |  | L | VL | M | M | M |  | Start modelling at earliest possible date | Ensure that modelling starts early |  |  |  | 15% | L | L | L | L | L | 30000 | 60000 | 120000 | 9000 | #NAME? | #NAME? | #NAME? | Project 2 weeks delay at £30k per week |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 5 | 8 | #NAME? | #NAME? | #NAME? |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME?
15 | 20 |  | Additional data required | Additional data collection | Live |  | Customer |  | H | L | H | H | H |  | Check quality of incoming information and ensure that high enough before progressing work | Review data survey list |  |  |  | 20% | L | VL | L | L | L | 10000 | 25000 | 50000 | 5000 | #NAME? | #NAME? | #NAME? | Additional consultant/EA costs |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
16 | 21 |  | Loss of data | Need to revisit data gathering | Live |  | Consultant |  | VL | VL | VL | VL | L |  | Ensure that procedures for registering of incoming materials are followed | Ensure that all team members are aware of protocols for registering material |  |  |  | 20% | L | VL | L | L | L | 10000 | 15000 | 25000 | 3000 | #NAME? | #NAME? | #NAME? | Additional consultant/EA costs |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME?
17 | 22 |  | Cannot achieve low flow design with availability of water | Unable to achieve desired environmental benefits | Live |  | Customer |  | H | L | L | L | M |  | Start modelling at earliest possible date | Ensure that modelling starts early |  |  |  | 50% | M | L | L | L | L | 50000 | 75000 | 100000 | 37500 | #NAME? | #NAME? | #NAME? | Additional design risk. Resolution through peoples time |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
18 | 23 |  | Change to Red Line area | Additional surveys & consultation required leads to cost & time delay | Live |  | Customer |  | L | L | M | M | M |  | Consult with partners at early stages | Ongoing liaison with all stakeholders at early stages |  |  |  | 60% | H | M | L | M | M | 25000 | 50000 | 1250000 | 30000 | #NAME? | #NAME? | #NAME? | Change design drawings. Peoples time. Max assumes 1 year delay (2.5% inflation to construction costs) |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
19 | 24 |  | Network Rail and Highway Approvals for work around major infrastructure | Delays around the approvals process | Live |  | Customer |  | H | L | VH | VH | H |  | Engage appropriately with NR and Highways | Ensure that when engaging with NR/Highways as much information as deemed appropriate is available |  |  |  | 50% | M | L | M | M | M | 50000 | 100000 | 1250000 | 50000 | #NAME? | #NAME? | #NAME? | Further site Investigation and additional modelling. Max assumes 1 year delay (2.5% inflation to construction costs) |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 6 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
20 | 25 |  | Impacts of scheme on surface water management | Impacts on drainage infrastructure | Live |  | Customer |  | L | VL | M | M | M |  | Continue discussions with TW | Invite to comment on proposals at each stage, engage and ensure buy in. |  |  |  | 15% | L | VL | L | L | L | 10000 | 25000 | 50000 | 3750 | #NAME? | #NAME? | #NAME? | Additional consultation costs |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 5 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
Site Technical
21 | 26 |  | Known service diversion cost escalation | Cost & time delay to programme | Live |  | Customer |  | VH | H | M | H | H |  | Continue discussions with service providers & investigate commencement of early works | Invite to comment on proposals at each stage, engage and ensure buy in. |  |  |  | 60% | H | H | L | H | H | 400000 | 800000 | 1000000 | 480000 | #NAME? | #NAME? | #NAME? | Delay and localised diversion. Assume additional works to 3 crossing points on MP gas main at £100k each time and need to replace fibre optic cables runs on OAR rather than just divert at total of £500k |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 5 | 7 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
21a | 27 |  | Material volumes increase above base following detailed topographic survey as lidar data is known to vary across the site by plus/minus 200mm | Time & cost | Live |  | Customer |  | VH | VH | VH | VH | H |  | Develop materials management strategy within project to reduce risk of third party influences | Develop material management strategy |  |  |  | 50% | M | VH | M | VH | H | 0 | 1200000 | 2400000 | 600000 | #NAME? | #NAME? | #NAME? | Lidar is +/- 200mm. Base assumes all material taken to tip. Possibility this survey could result in no overall increase (least costs = zero); ML assumes 10% increase x £12m; max assume 20% extra works x £12m (£12m is approx earthworks costs) |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
22 | 28 |  | Topsoil re-used on site not disposed off site after further consultation | Time & cost | Live | Site | Customer |  | VH | VH | VH | VH | H |  | Develop materials management strategy within project and confirm approach with consultees and landowners | Develop material management strategy |  |  |  | 75% | VH | M | M | M | H | 250000 | 750000 | 1000000 | 562500 | #NAME? | #NAME? | #NAME? | Base cost assumes topsoil is disposed off site as preferred environmental consultee option. However, landowners might have different opinion. Overall disposal volumes would not increase off site as we'd just excavate deeper before replacing with topsoil. Overall volume 70,000m3 of topsoil (worse case) at £1m, ML assumes 75% of landowners require this option (52,500m3) at £750k. (Cost from Richard Lewis 08/07/15 |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
23 | 29 |  | Access difficulties for construction | Additional costs due to specialist access arrangements | Live |  | Customer |  | H | M | M | M | M |  | Need to review access to various sites. | Develop design & access statement |  |  |  | 20% | L | L | L | L | L | 50000 | 250000 | 500000 | 50000 | #NAME? | #NAME? | #NAME? | Additional costs of bringing materials in on different routes, need to develop dedicated site entrance to avoid villages and main roads. Hauling additional materials. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 1 | 2 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
24 | 30 |  | Pollution incidents while working in landfill sites and channels | Time, reputation & cost impact to the programme | Live | Site | Contractor |  | L | M | L | M | M |  | Robust design for temporary works | Develop plan |  |  |  | 15% | L | VL | M | M | M | 25000 | 50000 | 75000 | 7500 | #NAME? | #NAME? | #NAME? | If pollution found there may be a further issue that requires additional design |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME?
25 | 31 |  | Groundwater issues during construction | Additional pumping / temporary works leads to delays in programme | Live |  | Contractor |  | H | M | L | M | M |  | GI monitoring of watercourse to ensure that groundwater levels are low enough to avoid infiltration | Include further investigations in GI |  |  |  | 20% | L | L | VL | L | L | 100000 | 175000 | 300000 | 35000 | #NAME? | #NAME? | #NAME? | Additional temporary works over and above the base costs. There are seven structures which require temporary works. Normally a contractor risk |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME?
26 | 32 |  | Underground power cables and overhead cables / pylons need additional protection | Cost & time delay to programme | Live |  | Customer |  | H | VH | H | VH | H |  | Continue discussions with service providers | Invite to comment on proposals at each stage, engage and ensure buy in. |  |  |  | 30% | L | L | L | L | L | 100000 | 200000 | 500000 | 60000 | #NAME? | #NAME? | #NAME? | These are remote pylons / CH2M trying to design around this. Seven major pylons. Place 30m of sheet piling around each pylon. ML assumes further 7 pylons protected at 200k |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 4 | 6 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
27 | 33 |  | More onerous traffic management required | Increase in cost both on site and in approvals | Live |  | Customer |  | H | M | M | M | M |  | Discuss with planners before application to reduce conditions | Early design to TM works |  |  |  | 10% | VL | L | M | M | L | 30000 | 100000 | 250000 | 10000 | #NAME? | #NAME? | #NAME? | ML costs assume 120 max vehicles a day (approx 1 vehicle off site per 5mins). Max increased if planners impose more onerous conditions. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
28 | 34 |  | Minor flood events during construction 1 Apr - 30 Oct inclusive (risk also picks up major flood events) | Impact on time and costs, need to define risk levels | Live |  | Contractor |  | VH | VH | VH | VH | H |  | Plan temporary works to minimise impact of flood events. Most works are planned outside of the river channels but are within flood plain | Monitor and design works to account for minor floods where possible |  |  |  | 50% | H | M | M | M | M | 140000 | 560000 | 1120000 | 280000 | #NAME? | #NAME? | #NAME? | Review of Iffley Tail data indicates only 4 events since 1 Jan 2000 when river levels above bankfull between 1 April - 30 Oct with only July 2007 causing widespread flooding (and would be major event). 2007 would have been 2 weeks flooded plus 2 weeks making good. assume happen twice so 8 week at £140k. ML 1 event. Min 1 week delay |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME? |  |  | 0% | 4 | 6 | 10 | #NAME? | #NAME? | #NAME? |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME?
29 | 35 |  | Uncharted underground services | Impact on time and cost |  |  | Customer |  | M | M | M | M | M |  | Review the need | Review |  |  |  | 40% | M | L | H | H | H | 100000 | 200000 | 500000 | 80000 | #NAME? | #NAME? | #NAME? | Additional time to liaise with service providers if additional services are identified |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 4 | 6 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
Technical
| 36 |  | Left Blank. To be populated when risk identified |  | Live |  | Customer |  | L | VH | L | VH | H | [10 empty] | Data missing | Data missing |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
30 |  |  | Project Management
31 | 37 |  | Timely & effective decisions | Delays in making key decisions | Live |  | Customer |  | M | VL | M | M | M |  | Ensure that all parties are aware of responsibilities and authority | Engage in meetings with all stakeholders at early stages |  |  |  | 70% | H | L | L | L | M | 75000 | 100000 | 150000 | 70000 | #NAME? | #NAME? | #NAME? | Additional people time |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
32 | 38 |  | Resource does not meet programme needs | Delay in the program and overall project equals increase in overhead costs | Live |  | Customer |  | H | L | M | M | M |  | Create detail resource plan for future stages | Develop programme led resource plan |  |  |  | 50% | M | L | M | M | M | 75000 | 100000 | 150000 | 50000 | #NAME? | #NAME? | #NAME? |  |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  | Yes | 50% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
33 | 39 |  | Potential loss of supplier side knowledge when tendering subsequent stages | Loss of knowledge & delays to programme | Live |  | Consultant |  | H | L | M | M | M |  | Update procurement strategy | Update procurement strategy |  |  |  | 40% | L | L | H | H | M | 25000 | 75000 | 100000 | 30000 | #NAME? | #NAME? | #NAME? |  |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 13 | 26 | #NAME? | #NAME? | #NAME? |  | 0 | #NAME? | 0 | 0 | 0 | 0 | #NAME?
33 |  |  | Landowners and Third Parties
33a | 40 |  | Objections from landowners leads to Inquiry - now priced in risk 44 | Cost increases and programme delay | Expired |  | Customer |  | M | H | VH | VH | H | [10 empty] | Data missing | Data missing | [7 empty] | CPO prep costs within base costs. Assume 12-18 months delay as ML cost scenario and additional costs are for legal support (£250,000), project team (12months x £30 x .75) and 2.5% construction inflation for 1 year (£1,250,000). Inquiry costs shown within planning inquiry risk. max assumes 18 months delay. | [10 empty] | 0% | 0 | 1 | 2 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
34 | 41 |  | Insufficient compensation budget | Additional costs | Live |  | Customer |  |  |  |  | Data missing | Data missing |  | Land agent has provided ML cost (baseline) and maximum costs. | Keep under review |  |  |  | 50% | M | H | L | H | H | 500000 | 2000000 | 3000000 | 1000000 | #NAME? | #NAME? | #NAME? | Baseline costs based on Land Agent ML figure. ML based on difference between ML and maximum. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 1 | 2 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
35 | 42 |  | Future ownership and maintenance of bridges and weirs | Legal costs and commuted sums for adoption | Live |  | Customer |  | L | M | VL | M | M |  | Review asset ownership | Develop maintenance plan & explore options |  |  |  | 25% | L | M | L | M | M | 150000 | 300000 | 500000 | 75000 | #NAME? | #NAME? | #NAME? | Additional commuted sums. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 1 | 2 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
36 | 43 |  | Delays with reaching agreements with land owners regarding disposal of materials | Increased costs & delay to the programme | Live |  | Customer |  | M | VH | H | VH | H |  | Ensure that negotiation takes place early in the design process | Engage in meetings with all stakeholders at early stages |  |  |  | 15% | L | VL | L | L | L | 10000 | 50000 | 100000 | 7500 | #NAME? | #NAME? | #NAME? | Base costs assumes all material disposed to restoration sites hence minimal costs |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 44 |  | New development planned/built before commencement of construction phase | Impacts of preferred route alignment | Live |  | Customer |  | L | M | H | H | M |  | Keep up to date with any new developments within the project site area | Client to regularly liaise with other organisations or bodies to identify any new developments within project areas |  |  |  | 5% | VL | VL | L | L | L | 2000 | 20000 | 100000 | 1000 | #NAME? | #NAME? | #NAME? | Unlikely risk as works within floodplain, hence low figures |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
37 |  |  | Funding
38 | 45 |  | Separate / conflicting messages from project partners | Need to manage stakeholder, delay in securing funding and assurance. | Live |  | Customer |  | L | L | H | H | M |  | Ensure that all parties are aware of responsibilities and authority | Engage in meetings with all stakeholders at early stages |  |  |  | 15% | L | VL | M | M | M | 25000 | 50000 | 75000 | 7500 | #NAME? | #NAME? | #NAME? | Additional consultation |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 4 | 6 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
39 | 46 |  | Funding pledge is not met | Time | Live |  | Customer |  | M | L | VH | VH | H |  | Start liaising with potential contributors as early as possible | Ongoing liaison and management of investors |  |  |  | 30% | L | VL | VH | VH | H | 25000 | 50000 | 75000 | 15000 | #NAME? | #NAME? | #NAME? | Internal input increases. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 10 | 26 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
40 | 47 |  | Legal agreements with contributors not in place ready for construction award | Delays to FBC submission which has a knock on impact to construction | Live |  | Customer |  | M | L | M | M | M |  | Robust plan for time & agreements against FBC. Ensure contributions cover risks | Develop robust plan |  |  |  | 30% | L | M | M | M | M | 300000 | 600000 | 800000 | 180000 | #NAME? | #NAME? | #NAME? | Delay to construction start by 3 months at £50k / month. Incl +£20k / wk for contractor plus additional suppliers ie ECC PM / ECCSS |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 5 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
41 | 48 |  | Funding needs to be matched to contributions | Impacts on efficiency & affordability of scheme. | Live |  | Customer |  | VH | VL | L | L | M |  | Ongoing monitoring of programme need against balance sheet | Ongoing monitoring of programme need against balance sheet | [7 empty] | Data missing | Data missing |  |  |  | 0 | Data missing | Data missing | Data missing | Covered under optimism bias |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
41a | 49 |  | EA finance policy does not meet the project needs | Hinders effective delivery | Live |  | Customer |  | H | L | H | H | H |  | Early awareness and engagement with decision makers | Early engagement with key people | [7 empty] | Data missing | Data missing |  |  |  | 0 | Data missing | Data missing | Data missing | Covered under optimism bias |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 2 | 4 | 8 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
42 |  |  | Consents & Approvals
43 | 50 |  | Protracted planning process | Multiple applications results on time delays, impact to programme | Live |  | Customer |  | M | L | VH | VH | H |  | Discuss & agree planning approach with planners before application to reduce conditions | Scoping opinion and ongoing meetings. Likely to be single determination - to be confirmed. |  |  |  | 25% | L | M | H | H | M | 300000 | 600000 | 900000 | 150000 | #NAME? | #NAME? | #NAME? | Additional EA and supplier costs. Assume takes additional 5 mths x £30k/wk. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 13 | 26 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
44 | 51 |  | Old Abingdon Road Arch detailed investigations delayed due to consenting process | Possible delays to project & additional cost | Live |  | Customer |  | M | L | M | M | M |  | Discussions with highways | Early engagement with businesses & traffic management |  |  |  | 50% | M | VL | L | L | L | 25000 | 50000 | 75000 | 25000 | #NAME? | #NAME? | #NAME? | Risk currently relates to delay to investigation. Issues with travellers has increased this risk and will result in more expensive site works. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 4 | 6 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
45 | 52 |  | Inquiry (planning or CPO) | Significant Delays and cost increase (critical path) | Live |  | Customer |  | M | H | VH | VH | H |  | Ongoing dialogue with stakeholders and planners, extended consultation with parties likely to call planning in | Consultation |  |  |  | 60% | H | M | VH | VH | H | 860000 | 1360000 | 1540000 | 816000 | #NAME? | #NAME? | #NAME? | Normal CPO and planning costs within base costs. Inquiry results in 12 (ML) -18 (max) months delay. Additional costs are for external legal support plus QC (£1m) and project team (12months x £30k) or 18 months x £30k. Min assumes we resolve before Inquiry itself and therefore no QC input. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  | Yes | 60% | 0 | 75 | 120 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
45a | 53 |  | Legal challenges to scheme outside of planning inquiry | Impact on time and cost | Live |  | Customer |  | VL | H | VH | VH | H |  | Monitor any objections | Act quickly to avoid legal challenges |  |  |  | 60% | H | L | H | H | H | 80000 | 200000 | 450000 | 120000 | #NAME? | #NAME? | #NAME? | Legal fees to mount challenge |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  | Yes | 60% | 0 | 20 | 40 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
46 |  |  | Benefits
47 | 54 |  | Left Blank. To be populated when risk identified |  | Live |  | Customer |  | H | M | M | M | M | [10 empty] | Data missing | Data missing | 0 | 0 | 0 | 0 | Data missing | Data missing | Data missing | Covered under optimism bias |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 55 |  | Left Blank. To be populated when risk identified |  | Live |  | Customer |  | L | VH | VH | VH | H | [10 empty] | Data missing | Data missing | 0 | 0 | 0 | 0 | Data missing | Data missing | Data missing | Covered under optimism bias |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
48 |  |  | Commercial
| 56 |  | Tender required via OJEU | Delay to programme | Live |  | Customer |  | L | L | VH | VH | H |  | Detailed procurement strategy | Develop detailed procurement strategy |  |  |  | 5% | VL | H | VH | VH | H | 540000 | 1080000 | 1620000 | 54000 | #NAME? | #NAME? | #NAME? | Base assumes procured through WEM. OCL advised a possible 18 month delay. 18 months delay at £30k week but multiply x 50% as not all staff / suppliers required full time through this period. Least x 25% and Max 75% |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
49 |  |  | Assurance
| 57 |  | Assurance reviews identify additional work | Delay to programme | Live |  | Customer |  | H | L | M | M | M |  | Plan and follow implemented controls | Accept |  |  |  | 10% | VL | VL | VL | VL | L | 10000 | 25000 | 50000 | 2500 | #NAME? | #NAME? | #NAME? | Additional staff time |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
50 |  |  | Other Issues
51 | 58 |  | Flood events change emphasis of project / create political interference | Need to revisit decisions | Live |  | Customer |  | VL | H | H | H | M |  | Start modelling at earliest possible date | Ensure that modelling starts early |  |  |  | 50% | M | VL | M | M | M | 25000 | 50000 | 75000 | 25000 | #NAME? | #NAME? | #NAME? | Additional staff and supplier time |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 4 | 6 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
52 | 59 |  | Shortened FBC approval process cannot be agreed | Additional costs & delay to implementation | Live |  | Customer |  | M | L | VH | VH | H |  | Gain agreement from DEFRA, treasury and EA | Demonstrate in outline BC in ref to fast track approval process and gain agreement from all parties. |  |  |  | 20% | L | L | M | M | M | 100000 | 1250000 | 2500000 | 250000 | #NAME? | #NAME? | #NAME? | Additional re-writing, lobbying and inputs to gain approvals. Worst case could be delay to project by 1 year. 2.5% x £50m. Max at 5% |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 5 | 7 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
53 | 60 |  | Travellers moving into areas | Delays and costs of moving them off site | Live |  | Customer |  | L | L | M | M | M |  | No mitigation possible |  |  |  |  | 15% | L | VL | H | H | M | 10000 | 30000 | 50000 | 4500 | #NAME? | #NAME? | #NAME? | Cost for court order and bailiffs |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 2 | 5 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
54 | 61 |  | Variation in inflation | Increased or decreased costs | Live |  | Customer |  | VH | M | VL | M | H |  | Contributions cover the risk of inflation | Accept |  |  |  | 50% | M | L | VL | L | L | 150000 | 1250000 | 2500000 | 625000 | #NAME? | #NAME? | #NAME? | Base allows for 2.5% inflation. Assume a further 2 %. This will need review to understand base inclusion 2.5% x £50m. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
55 | 62 |  | The scheme has to be used before vegetation establishment | Significant remedial works | Live |  | Customer |  | H | H | VH | VH | H |  | Planning sequencing of works | Establish vegetation as you go along |  |  |  | 50% | M | H | H | H | H | 500000 | 1000000 | 1500000 | 500000 | #NAME? | #NAME? | #NAME? | 20% chance that this will occur every year 20% loss x £326t x 6000 = £390k and clean up = £790k = £1m. Max assume double and Least 50% |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
56 | 63 |  | Floods events greater than 1 in 10 delay to works - priced in minor events | Delay to programme | Expired |  | Customer |  | M | M | M | M | M |  | Review historic events | Plan historic events and allow time in the programme |  |  |  | 0% | L | H | VH | VH | H | 1360000 | 1780000 | 2900000 |  |  |  |  | Loss of production and clean up costs for one flooding of working areas. Assume 6 events at 2 weeks per event 12wks x £140k = £1.68m + £0.1m in additional works. Least 9wks and max 20 wks - why 6 events - please check. | [10 empty] | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 63 |  | Weather events preventing earthworks (below and above 1:10 years) | Delay to programme and costs | Live |  | Customer |  | M | M | M | M | M |  | Review historic events | Plan historic events and allow time in the programme |  |  |  | 80% | VH | H | VH | VH | H | 300000 | 4200000 | 5000000 | 3360000 | #NAME? | #NAME? | #NAME? | Contractor has reviewed 10 year rainfall records between 1 Apr - 30 Oct which indicates 70 days (10 working weeks) of work being stopped by rain or being too wet to work following rain. Assume £140k prelims/week = £1.4m per year totalling £4.2m. Min and max simply reflect limited movement either way as ML is evidenced based. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 64 |  | Construction start delayed due to any single or combination of risk above. | Costs (inflation) plus programme delay | Live |  | Customer |  | M | M | M | M | M |  | Keep programme under review | Ongoing programme updated |  |  |  | 60% | M | H | VH | VH | H | 1250000 | 1250000 | 1875000 | 750000 | #NAME? | #NAME? | #NAME? | Min and ML assumes 2.5% inflation on contractor costs of £50m. Max assumes 18 month delay. Internal costs embedded within other risk costs. |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
[5 empty] | Live |  |  |  | M | VH | M | VH | H | [10 empty] | Data missing | Data missing |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Identify Risk Owner | Identify Risk Owner | Identify Risk Owner | Identify Risk Owner | Identify Risk Owner | Identify Risk Owner | 0 |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | Identify Risk Owner | Identify Risk Owner | Identify Risk Owner | Identify risk owner | Identify risk owner | Identify risk owner | 0
| B7-1 | - | Employer's Risks as set down in Clause 80.1 of the NEC ECC Contract as amended by Clause Z23. |  | Live |  | Customer |  | M | M | M | M | M | [6 empty] | 35% | M | M | M | M | M |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 2 | 3 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| B7-2 | - | Major flooding event | Delays to surveys and GI | Live |  | Customer |  | M | H | H | H | H |  | Works are in flood plain and construction programme is likely to be logger than 12 months | Delay or move programmed works if necessary to minimise winter working for muck shifting works |  |  |  | 40% | M | H | H | H | H |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 2 | 3 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| B7-3 | - | Major scope change | Additional and abortive work | Live |  | Customer |  | H | H | H | H | H |  | Monitor and identify as early as possible to minimise costs | Question scope change requests to ensure valid |  |  |  | 30% | M | VH | H | VH | H |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 6 | 10 | 20 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| B7-4 | - | Legislative change not anticipated | Major scope change | Live |  | Customer |  | M | H | H | H | H |  | None | Revise project plan as soon as identified to avoid abortive work |  |  |  | 35% | M | H | H | H | H |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| B7-5 | - | Costs associated with major legal process / CPO or public enquiry | Impact on time and cost | Live |  | Customer |  | H | M | M | M | M |  | Large controversial scheme, call in for planning high risk |  |  |  |  | 60% | H | M | M | M | M |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 2 | 3 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| B7-6 | - | Programme/ budgetary changes introduced by Customer after agreement of PAR | Impact on time and cost | Live |  | Customer |  | M | M | M | M | M |  | Project has long delivery programme so changes are likely | Monitor |  |  |  | 40% | M | M | M | M | M |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 2 | 3 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| B7-7 | - | Other Exceptional Risks, National resilience review, Thames catchment strategic storage | Major scope change | Live |  | Customer |  | M | M | M | M | M |  | None | Regular risk reviews to minimise probability of this risk |  |  |  | 35% | M | M | M | M | M |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 3 | 5 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
[28 empty] | MEV | 12337950 |  |  |  |  | @RiskSum (ignore these cells) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | [9 empty] | @Risk Sum (ignore these cells) | #NAME? | #NAME? | #NAME? | #N/A | #N/A | #N/A | #N/A
[34 empty] | 50%tile (for individual supplier Incentivisation - Form A) | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | [10 empty] | 5%tile |  | Data missing |  | #N/A | #N/A | #N/A | #N/A
[34 empty] | 50%tile (for Joint Supplier Incentivisation - Construction) | [6 empty] | #NAME? | [9 empty] | 50%tile | #NAME? | #NAME? | #NAME? | #N/A | #N/A | #N/A | #N/A
[51 empty] | 95%tile | #NAME? | #NAME? | #NAME? | #N/A | #N/A | #N/A | #N/A
[35 empty] | Client Approval for SoC |  |  |  |  | @Risk Sum cell (ignore this cell) | #NAME?
[40 empty] | 50%tile Client Approval Risk Budget | #NAME? | [10 empty] | Actual Values from @risk simulation
[40 empty] | 95%tile Client Approval Risk Budget | #NAME? | [9 empty] | 5%tile | 3.6293 | 0 | 0 | 0 | 0 | 0 | 10.525
[51 empty] | 50%tile | 15.0422 | 8.0066 | 0 | 0 | 0 | 0 | 24.5203
[35 empty] | Client Approval for SoC |  | Actual Values from @risk simulation | [13 empty] | 95%tile | 28.16 | 19.1759 | 5.6502 | 0 | 0 | 0 | 42.3499
[40 empty] | 50%tile Client Approval Risk Budget | 11696745.2605
[40 empty] | 95%tile Client Approval Risk Budget | 20695646.1539
At the end of the simulation please produce @Risk output reports to identify the risk values to be used
| 27 |  | Impacts on navigation during construction | Need to specific temporary works to maintain navigation at key activities | Live |  | Contractor |  | L | L | L | L | L |  | Once solution is known develop plan with navigation | Develop plan with navigation with stakeholder input. |  |  |  | 5% | VL | M | L | M | L | 0 | 0 | 0 | 0 | #NAME? | #NAME? | #NAME? | Contractor Risk. Costs incl in construction budget |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME? |  |  | 0% | 0 | 4 | 6 | #NAME? | #NAME? | #NAME? |  | 0 | 0 | #NAME? | 0 | 0 | 0 | #NAME?
| 35 |  | Incident role/duty work removes key staff | Delays due to loss of staff | Live |  | Customer |  | H | L | L | L | M |  | Leadership team to review | Leadership team to review | [8 empty] | FALSE | 0 | 0 | 0
| 36 |  | Change in key staff in over lifetime of project | Delays to project | Live |  | Customer |  | H | L | M | M | M |  | Develop a detailed resource plan | Develop programme led resource plan |  |  |  | 15% | L | L | H | H | M | 25000 | 75000 | 100000 | 11250 | #NAME? | #NAME? | #NAME? | Could be potential duplicate of risk ID 34 |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 6 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 50 |  | Benefits do not attract 3rd party funding | Funding shortfall, project stops | Live |  | Customer |  | H | M | M | M | M |  | Start liaising with potential contributors as early as possible | Start liaising with potential contributors as early as possible |  |  |  | 50% | H | M | VL | M | M | 25000 | 50000 | 75000 | 25000 | #NAME? | #NAME? | #NAME? | Project stops, closure costs only |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 51 |  | Project does not deliver the intended benefits | Further work is require post project completion | Live |  | Customer |  | L | VH | VH | VH | H |  | Robust quality assurance | Peer review to be conducted | [7 empty] | Data missing | Data missing | 0 | 0 | 0 |  | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 52 |  | Legacy issues when framework expires | More time demand on project team | Live |  | Customer |  | VH | L | VH | VH | H |  | Detailed procurement strategy | Develop detailed procurement strategy | [8 empty] | FALSE | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 3 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 55 |  | Costs increase above budgets / cost under estimates - covered under Optimum bias | Project becomes unaffordable, monies not available to complete project | Live |  | Customer |  | M | VH | VL | VH | H |  | Ensure that as little abortive work as possible is carried out | Review cost estimates at strategic points |  |  |  | 0% | L | M | VL | M | M | 25000 | 50000 | 75000 | 0 | #NAME? | #NAME? | #NAME? |  |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME? |  |  | 0% | 4 | 7 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 57 |  | Change in political climate | Change in political support | Live |  | Customer |  | H | L | L | L | M |  | Governance structure should be robust | maintaining relationships , drivers are not politically bias |  |  |  | 0% | L | L | L | L | L |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 2 | 6 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 59 |  | Operational & maintenance assumptions are incorrect | Intended scheme benefits cannot be realised | Live |  | Customer |  | L | VH | L | VH | H |  | Strong governance body required for future maintenance & align realistic maintenance budget | Carry out detailed costing exercise |  |  |  | 40% | M | M | M | M | M |  |  |  | 0 | Data missing | Data missing | Data missing | Needs to go into Ian's long term risk line |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 0 | 6 | 10 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 62 |  | Variation in market conditions | Increased costs | Live |  | Customer |  | H | VH | L | VH | H |  | Accept |  |  |  |  | 75% | VH | VH | M | VH | H |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 63 |  | Delays caused by other risks | Delays & increased cost | Live |  | Customer |  | H | H | VL | H | H |  | Continuous risk management | Develop realistic programme and monitor |  |  |  | 30% | M | M | M | M | M |  |  |  | 0 | Data missing | Data missing | Data missing | Cost element derived from 5th, 50th and 95th%tile of project time risks |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 65 |  | Sequencing of works is affected due to unknown reasons | Cost & time delays to programme | Live |  | Customer |  | H | H | VH | VH | H |  | Agree construction sequence | Develop construction sequence | [7 empty] | Data missing | Data missing | 0 | 0 | 0 | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
| 68 |  | Additional structures | Additional costs & delay to programme | Live |  | Customer |  | M | VH | M | VH | H |  | Better understand land owners requirements | Ongoing engagement | [7 empty] | Data missing | Data missing |  |  |  | 0 | Data missing | Data missing | Data missing |  |  | Data missing | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% | 1 | 2 | 4 | #NAME? | #NAME? | #NAME? |  | #NAME? | 0 | 0 | 0 | 0 | 0 | #NAME?
Note on K16: Estimate of potential cost of consequence should the risk source occur (according to scale in 'Prioritisation' worksheet; L,M,H,VH)
Note on J16: Probability category of risk source (according to scale in 'Prioritisation' worksheet: L, M, H, VH)
Note on L16: Estimate of potential time delay to whole programme should the risk source occur (according to scale in 'Prioritisation' worksheet; L,M,H,VH)
Note on M16: Hidden Column: Combined Time and Cost Consequence (for use in risk prioritisation) Do not alter this formulae - Need to copy down when adding new rows
Note on N16: Risk Priority (based on combination of Probability and Consequence) Do not alter this formulae - Need to copy down when adding new rows
Note on Q16: Specific response action implementable within the project programme
Note on R16: Cost of mitigation action allows a decision on whether to carry it out based on the benefits or damage avoided (unlikely to be known at risk workshop)
Note on S16: Named individual who has delegated responsibility to undertake/manage the response action (could be the risk owner or other party who is best person to manage)
Note on T16: Target and Actual completion date of Response Action
Note on U16: Probability of the risk source occurring after the Response Action has been carried out. This value is used in the quantified analysis with 1-p being the probability of the hazard not occurring (i.e. consequence =0). The residual probability can be thought of as the point at which the consequence can't be absorbed within the project.
Note on AA16: Estimated least value of the consequence should the risk occur
Note on AB16: Estimated most likely value of the consequence should the risk occur
Note on AC16: Estimated maximum value of the consequence should the risk occur
Note on AE16: Part of the risk value quantification that assigns the likelihood of the @Risk PERT distribution being sampled (not user defined unless data supports the use of alternative distribution)
Note on AF16: @Risk distribution that allows the Consequence range to be sampled (Least to Maximum). (Not user defined unless data supports use of alternative distribution)
Note on AG16: Calculated risk value Values sampled with either be zero, or the value from the PERT distribution (these values are summed to give the total distribution for all risks)
Note on AH15: Assumptions used to build up the least, most likely and maximum cost values
Note on AJ15: Allocation of risk values to the particular risk owners (not user defined)
Note on Z16: Risk Priority after mitigation (based on combination of Probability and Consequence) Do not alter this formulae - Need to copy down when adding new rows
Note on Y16: Do not alter this formulae - Need to copy down when adding new rows
Note on AM16: Add correct name here will automatically change the risk owner list
Note on AN16: Add correct name here will automatically change the risk owner list
Note on AO16: Add correct name here will automatically change the risk owner list
Note on D16: Description of the initiating event that results in potential for an adverse of beneficial consequence on the project Also include initials of the person who identified the risk.
Note on E16: Description of the Consequence, should the source event occur (in terms of specific impact on the project) - not just 'cost', 'time' or 'quality'
Note on AR15: Estimation of the potential affect of the risks on the project programme. The time buffer can be estimated using a simple MEV method or full Monte-Carlo method (using the three point estimate). If MEV is used then only the Most Likely value is needed. Assessment of whether a risk affects the Critical Path can be supported by using the MS Project Programme Consideration should be given to the cumulative affect of summing individual programme risks and whether there is any double-counting
Note on AT16: Estimate of the Probability that risk will materialise on this project - Copied cell from Post Response Ranking
Note on AU16: Estimated least value of the project delay should the risk occur
Note on AV16: Most Likely value of the time delay should the risk occur - This value has most influence on the risk distribution If a simple MEV calculation is used then only this value needs to be entered and not Least and Max
Note on AW16: Maximum value of the time delay should the risk occur
Note on AY16: @Risk distribution that allows the Consequence range to be sampled (Least to Maximum). (Not user defined unless data supports use of alternative distribution)
Note on AZ16: Values sampled with either be zero, or the value from the PERT distribution (these values are summed to give the total distribution for all risks) Note: - no emphasis should be placed on any single risk value
Note on O16: Response actions already defined as part of the proposal or project
Note on P16: Generic description of response required to control/manage the risk All responses should be over and above normal best practice and quality assurance methods (i.e. Existing Safeguards) Should result in a specific action that is implementable within the programme and hence has an associated cost
Note on AX16: Part of the risk value quantification that assigns the likelihood of the @Risk PERT distribution being sampled (not user defined unless data supports the use of alternative distribution)
Note on AS16: Will the occurrence of this risk result in an extension of the project end-date (CP) or can the consequences of the risk be managed within the programme (Non CP) If 'Yes', then include estimate of time extension to develop programme buffers
Note on AD16: The Mean Expected Value (MEV) provides an estimate of the 50P. Equivalent to Probability * Most Likely Cost
Note on AI106: Delete Outputs that are not required (otherwise a high number of 'reports' will be produced when using the @Risk reporting function)
Note on I16: Include Lesson Learnt for all Materialised Risks
Note on BB15: Allocation of risk values to the particular risk owners (not user defined)
Note on U163: Environment Agency User: In reality is higher
Note on AH175: Environment Agency User: baselined against what?
Note on AH177: Environment Agency User: baselined against what?

## Customer Risk 110716
@RISK Output Report for Customer risks exc' the Big 5
Performed By: Miller, Graeme
Date: 11 July 2016 17:33:16
Simulation Summary Information
| Workbook Name |  | Modelled Oxford - Project Risk Register v4 OBC baseline 110716 GM.xls
| Number of Simulations |  | 1
| Number of Iterations |  | 10000
| Number of Inputs |  | 86
| Number of Outputs |  | 6
| Sampling Type |  | Monte Carlo
| Simulation Start Time |  | 2016-07-11 17:33
| Simulation Duration |  | 0:00
| Random # Generator |  | Mersenne Twister
| Random Seed |  | 1
Summary Statistics for Customer risks exc' the Big 5
| Statistics |  | Percentile
| Minimum | 1444618.8688 | 5% | 7003882.6105
| Maximum | 20574739.5693 | 10% | 8052578.3266
| Mean | 11656932.6874 | 15% | 8829765.3958
| Std Dev | 2694983.0143 | 20% | 9412285.444
| Variance | 7.2629e+12 | 25% | 9870169.3137
| Skewness | -0.12819 | 30% | 10290049.531
| Kurtosis | 2.8359 | 35% | 10677476.3837
| Median | 11730159.4962 | 40% | 11040769.2052
| Mode | 11896481.6151 | 45% | 11374333.66
| Left X | 7003882.6105 | 50% | 11730159.4962
| Left P | 5% | 55% | 12065778.8377
| Right X | 15932475.7219 | 60% | 12420438.7217
| Right P | 95% | 65% | 12770095.9782
| Diff X | 8928593.1113 | 70% | 13144779.2934
| Diff P | 90% | 75% | 13519813.3925
| #Errors | 0 | 80% | 13962767.8945
| Filter Min | Off | 85% | 14454511.693
| Filter Max | Off | 90% | 15090636.1023
| #Filtered | 0 | 95% | 15932475.7219
Regression and Rank Information for Customer risks exc' the Big 5
| Rank | Name | Regr | Corr
| 1 | Risk ID63 | 0.23859 | 0.23557
| 2 | Risk ID41 | 0.096485 | 0.091931
| 3 | Risk ID61 | 0.094419 | 0.09119
| 4 | Risk ID27 (AF47) | 0.06999 | 0.064143
| 5 | Risk ID23 | 0.041975 | 0.043976
| 6 | Risk ID28 | 0.040771 | 0.035509
| 7 | Risk ID59 | 0.036714 | 0.036407
| 8 | Risk ID8 | 0.034178 | 0.025434
| 9 | Risk ID24 | 0.027966 | 0.027098
| 10 | Risk ID3 | 0.024795 | 0.023802
| 11 | Risk ID53 | 0.023832 | 0.033318
| 12 | Risk ID44 (AF67) | 0.023472 | 0.016975
| 13 | Risk ID18 | -0.020424 | -0.013177
| 14 | Risk ID42 | 0.019825 | 0.027462

## Consultant Risk 110716
@RISK Output Report for Consultant risks exc' the Big 5
Performed By: Miller, Graeme
Date: 11 July 2016 16:26:24
Simulation Summary Information
| Workbook Name |  | Oxford 160711 - Project Risk Register v4 OBC baseline.xls
| Number of Simulations |  | 1
| Number of Iterations |  | 10000
| Number of Inputs |  | 86
| Number of Outputs |  | 5
| Sampling Type |  | Monte Carlo
| Simulation Start Time |  | 2016-07-11 16:26
| Simulation Duration |  | 0:01
| Random # Generator |  | Mersenne Twister
| Random Seed |  | 1
Summary Statistics for Consultant risks exc' the Big 5
| Statistics |  | Percentile
| Minimum | 0 | 5% | 0
| Maximum | 311092.2518 | 10% | 0
| Mean | 71533.3645 | 15% | 0
| Std Dev | 52883.1703 | 20% | 15132.1987
| Variance | 2796629703.4828 | 25% | 37630.9783
| Skewness | 0.49665 | 30% | 44732.4866
| Kurtosis | 2.8572 | 35% | 50279.3207
| Median | 64547.1592 | 40% | 54996.0116
| Mode | 0 | 45% | 59681.6137
| Left X | 0 | 50% | 64547.1592
| Left P | 5% | 55% | 70598.8929
| Right X | 163079.7806 | 60% | 78139.6608
| Right P | 95% | 65% | 86848.8412
| Diff X | 163079.7806 | 70% | 98270.3491
| Diff P | 90% | 75% | 109689.3864
| #Errors | 0 | 80% | 119887.3083
| Filter Min | Off | 85% | 130044.9244
| Filter Max | Off | 90% | 141608.3592
| #Filtered | 0 | 95% | 163079.7806
Regression and Rank Information for Consultant risks exc' the Big 5
| Rank | Name | Regr | Corr
| 1 | Risk ID39 | 0.107 | 0.099721
| 2 | Risk ID6 | 0.088787 | 0.09779
| 3 | Risk ID19 | 0.038081 | 0.028487
| 4 | Risk ID50 (AF165) | -0.023699 | -0.022403
| 5 | Risk ID26 | -0.019376 | -0.019787
| 6 | Risk ID56 | -0.018814 | -0.017049
| 7 | Risk ID1 | 0 | -0.017342
| 8 | Risk ID2 | 0 | -0.017062
| 9 | Risk ID3 | 0 | -0.017049
| 10 | Risk ID4 | 0 | 0.015437
| 11 | Risk ID5 | 0 | -0.01513
| 12 | Risk ID7 | 0 | -0.01466
| 13 | Risk ID8 | 0 | 0.014635
| 14 | Risk ID9 | 0 | 0.014532

## 5 - Risk monitor
User action | Risk monitoring / status spreadsheet - used to aid monitoring of project risk budgets and acts as status report for progress meetings
|  | A | B |  | C |  | D | E
| Risk budgets: Summary | Baseline total | Materialised risks (from CE's) |  | Predicted remaining risk (from @Risk) |  | Forecast risk (B+C) | Forecast outturn risk budget (A-D)
Insert values on baseline risk budgets and predicted remaining budgets (time and cost) | Project approval 95P (£k) | 300000 | 20000 |  | 280000 |  | 305000 | -5000
| Project approval 50P (£k) | 200000 |  |  | 180000 |  | 205000 | -5000
| Supplier budget 50P (£k) | 50000 | 5000 |  | 45000 |  | 50000 | 0
Complete table to enable a discussion of key risks with Client and project team | Risks to project in the next quarter
| Risk ID (from Risk Register) | Summary risk description |  | Action |  |  | Action owner
Complete Table to keep a running view of the root causes and lessons learnt of all risks (client or supplier) that have materialised - see comments for more detailed description | Materialsed Risks and Lessons Learnt
| Risk ID (from Risk Register) | Summary risk description |  | Actual cost (from CE) |  | Risk category (drop down menu) | Lesson learnt
Risk categories (Appraisal and construction)
Approvals and consents
Change in Scope
Changes to Guidance
Communications
Cost Variability
Data Availability / Quality
Design Work
Environment
Iteration of Work
Major Unforseen Risk
Modelling
Optimistic estimates
Options Appraisal
Project Management Systems
Reporting
Resources
Review Process
Site Investigations
Stakeholder Engagement
Sub Consultant Interface
Technical Problems
Third Party Interface
Weather / Natural Events
In Ground Problems
Material Delivery
Utilities
Health & Safety
Other Construction
Note on F6: Insert Budgets at the start of the project
Note on H6: Should be equal to value of CE's - updated montly from totals in Forecasts
Note on J6: Value of live risks remaining in the risk register (as predicted from @risk analysis) - updated monthly
Note on N6: Inform Clinet PM if budgets are predicted to be exceeded
Note on K28: Choose from drop-down list
Note on L28: Description ofthe 'lesson' and how we might better manage the risk in the future

## Prompt list
Risk identification prompt list - generic |  | Risk categories (General) | Risk categories (Task specific) | Key words
General engineering |  | Approvals | Project Management | Uncertainty
1 | Unforeseen ground conditions | Weather | Communications | Constraints
2 | Third Party Approvals or Actions | Ground Conditions | Options Appraisal | Limitations
3 | Unforseen Services | Design | Data Collation | Variability
4 | Weather | Services | Site Investigation | Ambiguity
5 | Adequacy of Site Investigation | Programme | Economic Appraisal | Dependencies
6 | Adverse PR | Working Methods | Stakeholder Engagement / Consultation
7 | Adverse sea/river water levels, waves, surfs, currents, wind and other climatic conditions | Resources | Modelling
8 | Failure to maintain Defence Standards | Costs | Environmental Assessment / SEA
9 | Non acceptance or delayed acceptance of asset by Operational client | Health and Safety | Reporting
10 | Security and Vandalism | Environment | Approvals
Land acquisition |  | Consultation
1 | Impact of construction and use on owners and occupiers | Security
2 | Impact of construction and use on people and businesses in the wider area | Communications
3 | Objections from landowners, occupiers and third parties | Behaviour / Relationships
4 | Notice serving powers unavailable
5 | Actions arising out of Environmental Statement or report
6 | Inadequate identification of contract access routes, working areas on site compound
7 | Damage to buildings as a result of construction and use
8 | Changes in property ownership or occupation before or during occupation
9 | Failure to communicate terms and conditions of entry prior to commencement
10 | Delays before and during construction
11 | Alterations to programme and timing
12 | Engineering and design changes
13 | Insufficient understanding of the need for permanent rights to retain and maintain works after construction
14 | Delays in completing reinstatement or unsatisfactory completion
15 | Inadequate scoping of compensation budget
16 | Live site e.g.Farmland/Commercial
Environmental
1 | Non-compliance with environmental legislation, sustainability policy, strategy or plans: (Environment Agency and external)
2 | Inadequate resources or competence to meet environmental commitments, either in-house or contracted in
3 | Consultant or contractor failure to meet and deliver environmental specification
4 | Unexpected environmental impacts or site sensitivities, e.g.new designation, archaeological find
5 | Poor communication or interpretation, resulting in inadequate information, misunderstanding, delays or objections to the project
6 | Change, influencing environmental decision making or agreement adversely
7 | Timing of environmental processes, approvals and work periods not appropriate
8 | Approvals withheld, e.g. English Nature, Land Drainage Consent or Planning Approval or legal agreement
9 | Environmental incident or objection stopping the project
10 | Added Value: Loss of opportunity to add value or identify potential environmental benefits
11 | Archaelogy
12 | Contaminated Ground