## Optimism Bias (OBC Stage)
Appendix G
OXFORD FLOOD ALLEVIATION SCHEME
Project OB for economic assessment for OBC.
Optimism Bias
Using FCDPAG3 Economic Appraisal - Supplementary Note to Operating Authorities, March 2003
From Annex 2 - Interim Optimism Bias data for flood and coastal defence strategy and scheme costs.
Starting upper bound Optimism bias factor for Strategy costs (pre-feasibility stage) 60%
Starting upper bound Optimism bias factor for Scheme costs (detailed design stage) 30%
Strategy factor
Informed by average for 'standard' and 'non-standard' civil engineering projects in 'Review of Large Public Procurement in the UK', Mott MacDonald 2002, and consultation with Defra Regional Engineers
OBC Net Estimate
Scheme factor
Informed by initial analysis of Defra account data which suggests Optimism Bias at scheme approval stage is broadly half that at strategy stage
2016-06-29
Risk components contributing to above factors (%, summing to 100) |  | Average % for FCD projects | Reasons for reducing the % for Oxford FAS OBC submission - refer to Monte Carlo risk register | Revised % | Risk Value
Procurement | Late contractor involvement - late involvement of the contractor in the design leads to redesign or problems during construction. | 1 | ESE contractor fully engaged. This will continue through detailed design development but redesign is ausual site risk | 2 | 0
| Dispute and claims occurred - disputes and claims occur where no mechanisms exist to manage effectively adversarial relationships between project stakeholders. | 11 | NEC contracts will be used throughout which encourage effective communication between parties. Outcome focused scope could risk CE's during detailed design. | 5 | 0
| Other - other factors that relate to procurement which affect the final project cost. | 1 | Not applicable at this stage. | 0 | 0
Project-specific | Design complexity - the complexity of design (including requirements, specifications and detailed design) requires significant management, impacting on final project costs. | 4 | Channel works are a simple solution involving significant muck shift. Complexity is around Redbridge area. | 4 | 0
| Degree of innovation - the degree of innovation required due to the nature of the project requires unproven methods to be used. | 4 | Standard engineering solutions. | 0 | 0
| Environmental impact - the project has a major impact on its adjacent area leading to objection from neighbours and the general public. | 13 | Ongoing discussions with statutory and non-statutory consultees. Environmental surveys underway which which help understand risk and possible preparatory works. | 5 | 0
| Other - other project specific factors which affect the final project cost. | 9 | Project specific factors covered in base cost, contractor risk and project risk. 5% allowance made for scope creep not covered elsewhere. | 5 | 0
Client specific | Inadequacy of the business case - the project scope changes as a result of the poor quality of requirement specifications and inadequate project scope definition. | 23 | Oxford FAS signed off. OBC underway. Project would not progress if business case no longer viable. Ongoing investigations on Thames catchment storage options under separate project. | 2 | 0
| Funding availability - project delays or changes in scope occur as a result of the availability of funding (e.g. departmental budget spent or insufficient contingency funds). | 2 | Project fully funded until FBC sign off. Project would close if funding shortfall not closed. | 0 | 0
| Project management team - the project management team's capabilities and/or experience impact on final project costs. | 1 | Experienced project team in place with agreed fall back options. | 1 | 0
| Poor project intelligence - the quality of initial project intelligence (e.g. preliminary site investigation, user requirements surveys etc.) Impacts on the occurrence of unforeseen problems and costs. | 8 | Site investigation complete. Further archaeological, environmental and topographic surveys underway. Further surveys will undoubtable be needed and some residual risk will remain on site as surveys only ever as good as where they are taken. | 4 | 0
Environment | Public relations - a high level of effort is required to address public concern about the project, which impacts on the final project cost. | 5 | The project is a high profile project which is likely to need a high level of effort throughout the OBC and FBC stage of the project to address public concern. Ongoing public events. | 1 | 0
| Site characteristics - the characteristics of the proposed environment for the project are highly sensitive to the project's environmental impacts (e.g. greenfield site with badger setts or contaminated brownfield site). | 4 | The Study area is in an area with many important environmental sites. Surveys underway and main site constraints/characteristics known. | 2 | 0
External influences | Economic - the project costs are sensitive to economic influences such as higher than expected construction costs inflation, oil price shocks etc. | 5 | Additional 2% inflation within risk register. This risk assume further increase as construction inflation currently running well above the inflation rate we use. | 5 | 0
| Legislation / regulations - the project costs are sensitive to legislation and regulation changes e.g. health and safety and building regulations. | 4 | Costs are sensitive to legislation changes esp. around landfill tax. | 2 | 0
| Technology - the project costs are sensitive to technological advancements e.g. the effects of obsolescence. | 4 | Tried and tested solution. | 0 | 0
| Other external influencing factors which affect the final project cost. | 1 | Inquiry priced in risk register. Utility companies engaged and costs in base cost or risk register. Unknown groundwater changes to flow routes. Uncertainty of private partnership funding following Brexit result. | 2 | 0
0
|  | 100 |  | 40
Optimism Bias factor = Sum(average % for FCD projects) /100 x 30 |  | 30 | Revised OB | 12%

## Optimism Bias (maintenance)
Appendix G
OXFORD FLOOD ALLEVIATION SCHEME
Project OB for economic assessment for OBC.
Optimism Bias
Using FCDPAG3 Economic Appraisal - Supplementary Note to Operating Authorities, March 2003
From Annex 2 - Interim Optimism Bias data for flood and coastal defence strategy and scheme costs.
Starting upper bound Optimism bias factor for Strategy costs (pre-feasibility stage) 60%
Starting upper bound Optimism bias factor for Scheme costs (detailed design stage) 30%
Strategy factor
Informed by average for 'standard' and 'non-standard' civil engineering projects in 'Review of Large Public Procurement in the UK', Mott MacDonald 2002, and consultation with Defra Regional Engineers
OBC Net Estimate
Scheme factor
Informed by initial analysis of Defra account data which suggests Optimism Bias at scheme approval stage is broadly half that at strategy stage
2016-06-29
Risk components contributing to above factors (%, summing to 100) |  | Average % for FCD projects | Reasons for reducing the % for Oxford FAS OBC submission - refer to Monte Carlo risk register | Revised % | Risk Value
Procurement | Late contractor involvement - late involvement of the contractor in the design leads to redesign or problems during construction. | 1 | Not relevant for maintenace stage | 0 | 0
| Dispute and claims occurred - disputes and claims occur where no mechanisms exist to manage effectively adversarial relationships between project stakeholders. | 11 | Low risk for maintenace period, supported by proposal to have a form of trust of Stakeholders to oversee | 1 | 0
| Other - other factors that relate to procurement which affect the final project cost. | 1 | Not applicable at this stage. | 0 | 0
Project-specific | Design complexity - the complexity of design (including requirements, specifications and detailed design) requires significant management, impacting on final project costs. | 4 | Design will be complete | 0 | 0
| Degree of innovation - the degree of innovation required due to the nature of the project requires unproven methods to be used. | 4 | Standard engineering solutions. | 0 | 0
| Environmental impact - the project has a major impact on its adjacent area leading to objection from neighbours and the general public. | 13 | Low risk following construction completion | 1 | 0
| Other - other project specific factors which affect the final project cost. | 9 | low risk due to detailed nature costs have been estimated | 1 | 0
Client specific | Inadequacy of the business case - the project scope changes as a result of the poor quality of requirement specifications and inadequate project scope definition. | 23 | Not applicable at this stage. | 1 | 0
| Funding availability - project delays or changes in scope occur as a result of the availability of funding (e.g. departmental budget spent or insufficient contingency funds). | 2 | Funding will need to have been demonstrated prior to this stage | 0 | 0
| Project management team - the project management team's capabilities and/or experience impact on final project costs. | 1 | Delivery by exisiting experienced maintenance staff | 1 | 0
| Poor project intelligence - the quality of initial project intelligence (e.g. preliminary site investigation, user requirements surveys etc.) Impacts on the occurrence of unforeseen problems and costs. | 8 | Not applicable at this stage. | 0 | 0
Environment | Public relations - a high level of effort is required to address public concern about the project, which impacts on the final project cost. | 5 | Not applicable at this stage. | 0 | 0
| Site characteristics - the characteristics of the proposed environment for the project are highly sensitive to the project's environmental impacts (e.g. greenfield site with badger setts or contaminated brownfield site). | 4 | Not applicable at this stage. | 0 | 0
External influences | Economic - the project costs are sensitive to economic influences such as higher than expected construction costs inflation, oil price shocks etc. | 5 | Consideration for changes due to inflation in future. | 1 | 0
| Legislation / regulations - the project costs are sensitive to legislation and regulation changes e.g. health and safety and building regulations. | 4 | Unlikely to have much impact based on detailed nature costs have been estimated | 0 | 0
| Technology - the project costs are sensitive to technological advancements e.g. the effects of obsolescence. | 4 | Tried and tested solution. | 0 | 0
| Other external influencing factors which affect the final project cost. | 1 | Unlikely to have much impact based on detailed nature costs have been estimated | 0 | 0
0
|  | 100 |  | 6
Optimism Bias factor = Sum(average % for FCD projects) /100 x 60 |  | 60 | Revised OB | 3.6%

## Optimism Bias Original
OXFORD FLOOD RISK MANAGEMENT STUDY | [5 empty] | As StAR
Strategy STUDY STAGE 2 | [7 empty] | Return to index
Optimism Bias
Using FCDPAG3 Economic Appraisal - Supplementary Note to Operating Authorities, March 2003
From Annex 2 - Interim Optimism Bias data for flood and coastal defence strategy and scheme costs.
Starting upper bound Optimism bias factor for Strategy costs (pre-feasibility stage) 60%
Starting upper bound Optimism bias factor for Scheme costs (detailed design stage) 30%
Strategy factor
Informed by average for 'standard' and 'non-standard' civil engineering projects in 'Review of Large Public Procurement in the UK', Mott MacDonald 2002, and consultation with Defra Regional Engineers
Scheme factor
Informed by initial analysis of Defra account data which suggests Optimism Bias at scheme approval stage is broadly half that at strategy stage
2015-03-09
Risk components contributing to above factors (%, summing to 100) |  | Average % for FCD projects | Reasons for reducing the % for Oxford FRM Study - mitigation | Revised % |  | Reasons for reducing the % for Oxford FRM Study - mitigation | Revised %
Procurement | Late contractor involvement - late involvement of the contractor in the design leads to redesign or problems during construction. | 1 | Already using a Contractor and intend to continue to use a Contractor throughout the process including the design stage to avoid problems during construction. | 1 |  | Already using a Contractor and intend to continue to use a Contractor throughout the process including the design stage to avoid problems during construction. | 0
| Dispute and claims occurred - disputes and claims occur where no mechanisms exist to manage effectively adversarial relationships between project stakeholders. | 11 | NEC contracts will be used throughout which encourage effective communication between parties and will reduce the risk of disputes and claims. | 8 |  | NEC contracts will be used throughout which encourage effective communication between parties and will reduce the risk of disputes and claims. | 7
| Other - other factors that relate to procurement which affect the final project cost. | 1 | Construction contract will be incentivised at PAR stage to improve cost certainty | 1 |  | Construction contract will be incentivised at PAR stage to imp | 1
Project-specific | Design complexity - the complexity of design (including requirements, specifications and detailed design) requires significant management, impacting on final project costs. | 4 | Although the channel design is likely to be a design which has been tried and tested, the Study Area is complex with many different factors to consider and hence the risk of requiring significant management to progress the design is high. | 4 |  | Although the channel design is likely to be a design which has been tried and tested, the Study Area is complex with many different factors to consider and hence the risk of requiring significant management to progress the design is high. | 4
| Degree of innovation - the degree of innovation required due to the nature of the project requires unproven methods to be used. | 4 | Innovation is likely to be required to take into account all the different aspects of the Study Area. However the design is unlikely to involve using unproven methods. | 1 |  | Innovation is likely to be required to take into account all the different aspects of the Study Area. However the design is unlikely to involve using unproven methods. | 2
| Environmental impact - the project has a major impact on its adjacent area leading to objection from neighbours and the general public. | 13 | Ongoing discussions with the Wildlife Forum and other key consultees and comprehensive environmental surveys will help to avoid objections on environmental grounds. (i.e. work on Port Meadow etc) | 8 | inc general public | Ongoing discussions with the Wildlife Forum and other key consultees and comprehensive environmental surveys will help to avoid objections on environmental grounds. (i.e. work on Port Meadow etc) | 4
| Other - other project specific factors which affect the final project cost. | 9 | Network rail planned works | 4 | Network Rail | Operational aspects once project is complete | 9
Client specific | Inadequacy of the business case - the project scope changes as a result of the poor quality of requirement specifications and inadequate project scope definition. | 23 | The business case will be determined at strategy level and hence the scope of the project is unlikely to be changed significantly post PAR. | 10 |  | The business case will be determined at strategy level and hence the scope of the project is unlikely to be changed significantly post PAR. | 15
| Funding availability - project delays or changes in scope occur as a result of the availability of funding (e.g. departmental budget spent or insufficient contingency funds). | 2 | Funding is being investigated at Strategy stage | 2 |  | Funding is being investigation at Strategy stage | 2
| Project management team - the project management team's capabilities and/or experience impact on final project costs. | 1 | As the project is high profile the Agency are likely to insist on a capable project management team. | 1 |  | As the project is high profile the Agency are likely to insist on a capable project management team. | 1
| Poor project intelligence - the quality of initial project intelligence (e.g. preliminary site investigation, user requirements surveys etc.) Impacts on the occurrence of unforeseen problems and costs. | 8 | Preliminary site investigations are being carried out as part of the Strategy stage and will assist in mitigating against the occurrence of unforeseen problems and costs. | 6 |  | Preliminary site investigations are being carried out as part of the Strategy stage and will assist in mitigating against the occurrence of unforeseen problems and costs. | 5
Environment | Public relations - a high level of effort is required to address public concern about the project, which impacts on the final project cost. | 5 | The project is a high profile project which is likely to need a high level fo effort throughout the life of the project to address public concern. | 5 |  | The project is a high profile project which is likely to need a high level fo effort throughout the life of the project to address public concern. | 5
| Site characteristics - the characteristics of the proposed environment for the project are highly sensitive to the project's environmental impacts (e.g. greenfield site with badger setts or contaminated brownfield site). | 4 | The Study area is in an area with many important environmental sites and hence there is a high risk of requiring environmental mitigation measures. However, this is partly covered elsewhere. | 2 |  | The Study area is in an area with many important environmental sites and hence there is a high risk of requiring environmental mitigation measures. | 4
External influences | Economic - the project costs are sensitive to economic influences such as higher than expected construction costs inflation, oil price shocks etc. | 5 | 30% of the construction costs are associated with excavation and disposal of the channels, hence the project costs are sensitive to economic influences such as higher than expected oil prices. | 5 |  | 30% of the construction costs are associated with excavation and disposal of the channels, hence the project costs are sensitive to economic influences such as higher than expected oil prices. | 5
| Legislation / regulations - the project costs are sensitive to legislation and regulation changes e.g. health and safety and building regulations. | 4 | The project costs are sensitive to legislation changes in particular changes to the waste management regulations. Quantify contaminated land risk | 4 |  | The project costs are sensitive to legislation changes in particular changes to the waste management regulations. Quantify contaminated land risk | 4
| Technology - the project costs are sensitive to technological advancements e.g. the effects of obsolescence. | 4 | The project costs are unlikely to be sensitive to technological advancement. | 1 |  | The project costs are unlikely to be sensitive to technological advancement. | 1
| Other external influencing factors which affect the final project cost. | 1 | Other factors such as changes in Defra policy. | 1 |  | Other factors such as changes in Defra policy. | 1
|  | 100 |  | 64 |  |  | 70
Optimism Bias factor = Sum(average % for FCD projects) /100 x 60 |  | 60 | Revised OB | 38.4% |  |  | 42%